## PublicDataReport
Collection Period | Department/ Agency Name | Agency Short Name | Project ID | Project Title | Government Domain | ICT Project Category | Description | Stage | Benefit Category ( Benefit Type) | Date of Closure/ Postponement | PM Methodologies | Initiation Start Date | Planned Initiation End Date | Revised Initiation End Date | Business Case Approval Date | Planned Initiation Cost | Revised initiation Cost | Planned Delivery Start Date | Revised Delivery Start Date | Planned Delivery End Date | Revised Delivery End Date | Planned Delivery Cost | Revised Delivery Cost | Q2 20-21 | Q3 20-21 | Q4 20-21 | Q1 21-22 | Q2 21-22 (Current) | Reporting Comments
Q2 21-22 | Country Fire Authority | CFA | 2151 | CFA Short Status Messaging (SSM) | Emergencies and Safety | Communication | Provide a Short Status Messaging system to allow CFA mobile radios to send status messages to fire dispatchers at ESTA. This will deliver more efficient use of radio channels by minimising voice congestion on radio dispatch channels. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2010-10-01 | 2012-07-01 | 2020-06-30 | 2020-07-01 | 0 | 45000 | 2020-07-01 |  | 2021-06-30 | 2022-06-30 | 2850000 |  | Green | Green | Green | Green | Green | The project is tracking well against scope budget and schedule.
Q2 21-22 | Department of Health | DH | 2200 | Replace Integration Solution for Patient and Clinical Information | Health | Development and Integration | Replacement of the integration solution to support Victorian acute public health services to integrate patient and clinical information. Prior legacy solution was at end of life posing a significant operational and security threat to health services. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2016-07-01 | 2016-11-30 |  | 2016-11-30 | 0 |  | 2016-12-01 |  | 2020-06-30 | 2022-03-31 | 16000000 | 16118793 | Green | Green | Green | Green | Green | Project on schedule
Q2 21-22 | Gippsland Health Alliance | GHA | 2209 | Electronic Medical Record and Community Health (EMRCH) | Health | Customer Relationship Management,Data Management,Document Management | The EMRCH project is a core component to the facilitation of highly integrated health services across all aspects of the specific services administered by the members of the Gippsland Health alliance, its implementation will facilitate the implementation of new models of care. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PMBoK | 2016-02-02 | 2017-10-30 |  | 2017-11-01 | 554038 |  | 2018-01-09 |  | 2019-12-31 | 2022-12-31 | 7419045 | 14686274 | Green | Green | Green | Amber | Amber | Timeline changes agreed to at all governance levels to push all clinical impacted service activities through to early 2022 in response to COVID workload impact.
Q2 21-22 | Hume Rural Health Alliance | HRHA | 2210 | Goulburn Valley Health Redevelopment | Health | Systems Management | The ICT component of the redevelopment of the Goulburn Valley Health Hospital to support improved health outcomes for the GV community, better access to health care in the GV community and the better use of health resources in Victoria. | Delivery | Increased Revenue (Financial) |  | PRINCE2 | 2016-04-20 | 2018-06-30 | 2018-08-01 | 2018-08-01 | 400000 | 100000 | 2018-10-31 |  | 2020-05-29 | 2022-06-30 | 4600000 | 3866000 | Green | Green | Green | Green | Green | New build works have been accelerated. Refurbishment works have been delayed as a result of response to COVID-19.
Q2 21-22 | Fire Rescue Victoria | FRV | 2241 | Purchase of Electronic Document and Records Management System (EDRMS) | Emergencies and Safety | Records Management | Procurement and implementation of a new electronic records management system to replace eDocs (DocCentral). | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | MFB Project Management Framework (PME) | 2013-07-01 | 2014-07-09 |  | 2014-07-09 | 60737 |  | 2014-07-09 |  | 2017-06-30 | 2022-01-31 | 1200000 | 2327490 | Amber | Amber | Amber | Amber | Amber | Project has taken longer than anticipated due to the numerous stakeholders involved and meetings required. Work on finalising the key elements is progressing and FRV expects to have the project completed and data migration finalised in early 2022.
Q2 21-22 | Ports Victoria | PortsVic | 2262 | Vessel Traffic Services Systems Upgrade | Transport and Vehicles | Communication | Replacement of existing / ageing Vessel Traffic Services Information Communications Technology systems with a focus on upgraded system integration, redundancy and disaster recovery. Affected systems include radio, telephony, radar, vessel AIS (Automatic Identification System), vessel DUKC (Dynamic Under-Keel Clearance), CCTV and Met Ocean (tide, wind, wave and weather). | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | VPCM (PMBoK) | 2015-12-03 | 2015-12-03 | 2018-11-30 | 2018-12-10 | 0 |  | 2019-01-10 |  | 2020-12-18 | 2022-03-31 | 9078548 |  | Green | Green | Green | Green | Green | All equipment and refurbishment works are complete. Network issues have been resolved. Final radar cutover and Final Site Acceptance testing have been delayed to the next reporting period, due to Covid border restrictions.
Q2 21-22 | Public Record Office Victoria | PROV | 2263 | Digital Archive Program | Government and Economy | Content Management,Document Management ,Records Management | This program is progressively renewing and replacing Public Record Office Victoria's digital archive infrastructure. The program is expected to enable better access to PROV records while facilitating long term preservation and reducing operating costs. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2015-07-01 | 2015-07-01 |  | 2015-07-01 | 200000 | 0 | 2015-07-01 |  | 2018-06-30 | 2022-03-31 | 4062000 | 5617000 | Amber | Amber | Amber | Amber | Amber | Internal staff assigned to complete the program and new Project Coordinator recruited following resignation of Project Manager. The implementation of the new systems to PROV's regional repositories will take place in 2022.
Q2 21-22 | Royal Victorian Eye and Ear Hospital | Eye & Ear | 2280 | ICT Redevelopment Stage 3 Hardware Tender and Implementation | Health | Systems Management | Fit-out of new IT infrastructure to support hospital redevelopment objectives | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2013-07-01 | 2014-06-30 |  | 2014-06-30 | 0 |  | 2014-06-30 |  | 2018-12-31 | 2022-10-03 | 0 | 1315265 | Green | Green | Green | Green | Green | The successful relocation of Day Surgery from the Eye and Ear on the park to the new redeveloped facility. This involved purchase and commissioning IT Infrastructure components of that move.
Q2 21-22 | Department of Transport | DOT | 2291 | ICT/ITS Infrastructure Transformation Program (Switch Program) | Transport and Vehicles | Systems Management,Security Management | Purpose of this project is to establish commercial arrangements for, and the transition into, new data centre hosting and managed infrastructure services to support DOT ( VicRoads) current and future ICT and Intelligent Transport System requirements. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2016-05-09 | 2017-08-17 |  | 2017-08-17 | 1250634 |  | 2017-08-17 |  | 2020-02-28 | 2022-02-25 | 7649366 | 19464718 | Red | Red | Green | Green | Green | Overall project status is green. VLAN gateway migrations was completed as per plan. Post migration cleanup and project closure being finalised. The revised delivery cost has changed from planned delivery cost due to the merger of other major initiatives (i.e. ICT Workplace Productivity Stream Remote access upgrade project Firewall Upgrade and additional scope items in Q4 2017-2018). The project is in final stages of delivery and is on track to meet the full benefits case.
Q2 21-22 | Northern Health | NH | 2411 | EMR Program | Health | Analyses and Statistics ,Collaboration ,Communication,Organisational Management ,Records Management | Implementation of an Electronic Medical Record at Northern Health including all sites | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2016-10-18 | 2018-05-01 | 2021-02-01 | 2021-02-02 | 0 | 4300000 | 2021-02-08 |  | 2022-12-18 | 2023-04-03 | 38700000 | 43000000 |  | Green | Amber | Red | Amber | Due to COVID Code Brown engagement with SME's is challenging but working through mitigation strategies.
Q2 21-22 | Court Services Victoria | CSV | 2452 | Courts Case Management System | Law and Justice | Tracking and Workflow | The CMS Project aims to procure and implement a new case management system for Magistrates’ Court and Children’s Court. The system will enable better information sharing between courts and other agencies, and provide better access to case information | Delivery | Efficiency/Productivity (Non Financial) |  | Project Management Excellence (PME) | 2016-07-01 | 2017-05-02 |  | 2017-05-02 | 0 |  | 2017-07-01 |  | 2022-06-30 | 2022-10-31 | 89200000 | 89233000 | Green | Green | Amber | Red | Red | The overall project status remains red. Solution build has been delayed due to COVID market resourcing constraints and other factors. The project is progressing with delivering the Business Case scope as well as replanning for the current delay. Work is progressing on addressing the current issues and is aiming to be completed and approved by April 2022.
Q2 21-22 | Department of Families, Fairness and Housing | DFFH | 2462 | Family Safety Victoria Central Information Point | Community Services | Data Management,Knowledge Management ,Records Management | Project will establish an information sharing platform and service that consolidates and provides timely risk relevant information from partner departments and agencies to frontline workers to support family violence risk assessment and management. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial), Social Improvement (Non Financial) |  | Agile | 2017-03-13 | 2018-01-29 | 2017-06-30 | 2017-07-03 | 0 |  | 2017-07-04 |  | 2019-06-30 | 2022-06-30 | 7199594 | 91422489 | Amber | Amber | Amber | Green | Green | Stages 1, 2, 3 and 4 of the project are completed and system is operational. Project has commenced Stage 5, which is scheduled for completion by 30 June 2022. Stage 5 will complete partner agency system integration and support usability enhancements to meet increased demand as The Orange Door Network continues to rollout across the State and the Risk Assessment and Management Panels are onboarded. Project is progressing to revised cost and schedule.
Q2 21-22 | North East Region Water Corporation | NE Water | 2481 | Customer Billing System | Environment and Water | Customer Relationship Management,Knowledge Management ,Management of Process | Procure a replacement for the current Billing system and implement a new self service portal for customers. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Vic Govt PM Framework | 2017-07-01 | 2017-12-31 | 2021-04-16 | 2021-04-16 | 0 | 1186673 | 2021-04-19 |  | 2022-05-31 | 2022-02-07 | 8597916 | 8944928 |  |  | Amber | Amber | Amber | The project status is amber. The plan is to provide an update to the Board on 7 December 2021 and request approval to vary the schedule.
Q2 21-22 | Victorian Electoral Commission | VEC | 2497 | EMS2 | Government and Economy | Development and Integration | The project will replace legacy Election Management System with a more robust, secure and integrated system that is in line with VEC technology strategy to enable a more efficient management of the Victorian election processes | Delivery | Efficiency/Productivity (Non Financial), Reputation (Non Financial) |  | Agile | 2017-03-01 | 2017-05-01 |  | 2017-05-01 | 50000 |  | 2017-05-01 |  | 2018-06-30 | 2022-03-31 | 2000000 | 1752344 | Green | Red | Amber | Green | Green | The project team have successfully completed development and IT testing of the all EMS modules. This is a major milestone and marks the end of development for the program after 10 years of work. The focus of the team has moved to completing the remaining user acceptance testing with a planned production release scheduled for early April.
Q2 21-22 | Department of Environment, Land, Water and Planning | DELWP | 2522 | Fuel Management System (FMS) | Emergencies and Safety | Data Management,Development and Integration ,Management of Process ,Reporting ,Assets/Materials Management,Knowledge Management | This project will deliver a Fuel Management System (FMS), a single, intuitive and flexible platform for delivering the multi-agency fuel management program in Victoria, for Forest Fire Management Victoria (FFMVic) and Country Fire Authority (CFA). | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2015-05-11 | 2015-05-12 |  | 2015-05-12 | 67500 |  | 2015-07-01 |  | 2018-12-31 | 2022-06-30 | 1900000 | 3189865 | Amber | Green | Green | Green | Green | The project is on track to be delivered on budget and on schedule. The project is being maintained in an operational state pending further funding approvals to start the next phase.
Q2 21-22 | Goulburn Valley Region Water Corporation | GVR Water | 2524 | Asset Management Information System Replacement Project | Environment and Water | Assets/Materials Management | Implement mature, industry proven Asset Management Information and Geographic Information Systems meeting the requirements of the organisation, delivering improvements and efficiencies not previously achievable with the current solutions | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Internal GVW Project Management Methodology | 2016-11-23 | 2017-12-08 |  | 2017-12-08 | 50000 |  | 2018-01-02 |  | 2021-03-31 | 2022-07-29 | 2405000 | 2429308 | Green | Green | Green | Green | Green | Project is currently engaging in discussions with the preferred RFT Tenderer.
Q2 21-22 | Goulburn Valley Region Water Corporation | GVR Water | 2525 | Intelligent Metering | Environment and Water | Assets/Materials Management | Installation of intelligent meters in four towns to provide data to target peak demand reduction, leading to: 1 . A permanent reduction in peak day water usage through leakage reduction. 2. Deferral of water network capacity upgrade projects | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Social Improvement (Non Financial), Workforce Satisfaction (Non Financial) |  | GVW Internal Project Management Methodology | 2017-07-01 | 2018-03-02 |  | 2018-03-02 | 10000 |  | 2018-07-31 |  | 2021-06-30 | 2023-05-31 | 1790000 | 4380000 | Green | Green | Green | Green | Green | Tracking OK
Q2 21-22 | Independent Broad-based Anti-corruption Commission | IBAC | 2526 | Case Management System | Law and Justice | Tracking and Workflow | The project will deliver a comprehensive case management system to manage complaints and investigations from receipt to conclusion, improving information sharing between business areas for investigations and increase timely response to complaints. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2015-07-14 | 2016-05-02 |  | 2016-05-02 | 74518 |  | 2017-12-21 |  | 2018-12-31 | 2022-06-30 | 1300000 | 1985000 | Green | Amber | Amber | Green | Amber | The new project manager has transitioned well for the project to continue. The pathway to completion is clear and core development and configuration of the platform continues, before testing commences.
Q2 21-22 | Department of Environment, Land, Water and Planning | DELWP | 2561 | Digital Cadastre Modernisation Project | Property and Planning | Knowledge Management ,Data Management | Digital Cadastre Modernisation will bring the authoritative map of Victoria’s property boundaries further into the digital age, ensuring that one of the State’s most important datasets is accurate, useful, and easy to maintain. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2018-02-12 | 2018-09-30 |  | 2018-09-30 | 0 | 200000 | 2018-11-16 |  | 2023-12-30 | 2023-12-30 | 0 | 47000000 | Amber | Red | Red | Red | Green | The project is progressing as planned, with early data now released and spatial improvements being achieved.
Q2 21-22 | Eastern Health | EH | 2563 | Single Billing System Project | Health | Data Management,Development and Integration ,Financial Management | Deliver a single billing system to replace 17 legacy systems used for patient accounts billing for Eastern Health, resulting in uplift in revenue, improved customer experience of billing and collection processes and reduction in costs | Delivery | Increased Revenue (Financial) |  | PRINCE2 | 2017-07-01 | 2018-02-04 | 2018-03-28 | 2018-03-28 | 508851 |  | 2018-04-17 |  | 2020-06-30 | 2022-04-30 | 6839088 | 11742903 | Green | Red | Green | Green | Green | Approval of the revised project plan has been received which has enabled the project to return to green.
Q2 21-22 | Coliban Region Water Corporation | Coliban Water | 2567 | Digital Customer Metering Program | Environment and Water | Data Management,Assets/Materials Management,Business Intelligence,Reporting | To automate manual meter reading to improve business intelligence, asset management and network planning to enable benefits for customers. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial) |  | PMBoK | 2016-01-18 | 2017-07-25 |  | 2017-07-25 | 72000 |  | 2017-07-25 |  | 2023-06-30 |  | 5448000 | 9001000 | Green | Green | Green | Green | Green | The program remains on target and planned benefits are still achievable.
Q2 21-22 | Westernport Region Water Corporation | WPR Water | 2568 | Business Transformation Project | Government and Economy | Systems Management,Financial Management,Human Capital / Workforce Management ,Human Resources,Reporting ,Supply Chain Management | The Project comprises 2 parts: 1st involves transitioning to a new ICT Managed Services Provider to address service continuity issues; 2nd involves replacing legacy IT systems for Finance, HR, Payroll and Utility Billing to address operational risks. | Postponed | Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) | 2020-12-01 | PRINCE2 | 2017-07-01 | 2020-06-30 | 2018-01-30 | 2018-03-19 | 2089200 | 135000 | 2018-05-07 |  | 2020-06-30 | 2021-05-31 | 1954200 | 3844038 | Amber | Amber | Amber | Amber | Amber | Payroll and HRIS implementations complete. Remaining two modules of HRIS will be considered next regulatory period. Finance system implementation remains suspended. Review confirmed MVP - now exploring alternative options for comparison to ensure value.
Q2 21-22 | Department of Health | DH | 2576 | Human Capital Management System | Employment and Workplace | Human Capital / Workforce Management | Implementation of a cloud based Human Capital Management system to uplift and modernise the department's human resources systems and deliver consistent human resources services across the department and secondly, across the Victorian Public Service. | Closed - Completed | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) | 2021-11-30 | Agile | 2017-11-30 | 2018-06-04 | 2018-03-29 | 2018-03-29 | 300000 |  | 2018-04-03 |  | 2020-06-30 | 2021-11-30 | 8987000 | 13819941 | Green | Green | Green | Green | Green | Project has successfully delivered and closeout activities are underway.
Q2 21-22 | South West Alliance of Rural Health | SWARH | 2597 | Barwon Health Optima Rostering Project | Health | Management of Process ,Human Capital / Workforce Management ,Human Resources | This project will deliver a Rostering and Time & Attendance system to automate staff rostering processes, improving workforce utilisation, accuracy of resource allocation and delivery of patient care. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2017-07-19 | 2018-05-31 |  | 2018-06-08 | 110640 |  | 2018-07-11 |  | 2019-12-31 | 2022-06-30 | 3443281 |  | Red | Red | Red | Red | Red | The project is Red due to critical implementation issues identified in testing and are being addressed in collaboration with the vendor. The project is working towards a Pilot Go Live on the 31st of January 2022. The Pilot and lessons learnt will inform the business case for the next phase.
Q2 21-22 | Department of Health | DH | 2603 | Regulatory Licensing and Registration Platform | Health | Systems Management | Replacement of the Radiation Registration and Licensing (RELIC) system utilised by the Environmental Health Regulation & Compliance Unit to administer their Act & legislation. Development of a platform configurable for other regulatory units. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Agile | 2017-10-20 | 2017-11-05 |  | 2017-11-05 | 0 |  | 2017-11-06 |  | 2019-06-30 | 2022-02-28 | 2400000 | 1911930 | Green | Green | Green | Green | Green | Project is progressing to cost and revised schedule which has been extended two months due to delays with testing.
Q2 21-22 | Hume Rural Health Alliance | HRHA | 2623 | West Hume Patient Administration System (PAS) | Health | Data Management,Management of Process ,Records Management ,Tracking and Workflow,Knowledge Management ,Visualisation | The project will deliver a new Patient Administration System across 5 health services, improving information sharing within the West Hume Region, improved information security and system availability to support timely provision of healthcare. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2018-08-01 | 2018-12-31 | 2019-12-06 | 2019-12-06 | 250000 | 62000 | 2020-03-20 |  | 2021-09-30 | 2023-04-30 | 4532536 | 5539631 | Green | Green | Green | Amber | Red | A revised end date is yet to be approved by Steering Committee and Control Board. Approvals are pending and we anticipate to change the end date in the next quarter's report.
Q2 21-22 | Hume Rural Health Alliance | HRHA | 2626 | Albury Wodonga Health Patient Administration System (PAS) | Health | Organisational Management ,Business Intelligence,Data Management,Financial Management,Management of Process ,Records Management ,Security Management ,Tracking and Workflow,Routing and Scheduling | The project will replace the current PAS to deliver a common patient database to standardise patient administration workflows and reporting across AWH, remove risks of multiple concurrent patient identifiers, and improve patient records management | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial) |  | PRINCE2 | 2018-08-01 | 2020-08-31 |  | 2020-08-31 | 1700000 | 630000 | 2020-08-31 |  | 2022-03-31 | 2022-12-31 | 250000 | 6970000 | Green | Green | Red | Red | Red | Solution vendor has advised that there will be delays in product readiness due to the number of defects they have found in testing. Solution vendor is reviewing effort estimates for remaining work.
Q2 21-22 | Transport Accident Commission | TAC | 2630 | Data Analytics | Transport and Vehicles | Business Intelligence | Implement an Enterprise Data Warehouse (EDW) that will contain the single source of truth for TAC's data. The program will also implement enterprise data policies and governance to ensure that data is of a high quality. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Reputation (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2018-06-01 | 2018-06-30 |  | 2018-07-03 | 0 | 1195727 | 2018-07-03 |  | 2019-11-30 | 2022-06-30 | 5700000 | 19004273 | Amber | Green | Green | Green | Green | Overall the program continues to progress across both project streams despite some challenges in the translation of data into the warehouse. The Technology phase is now complete with the platform delivered and transitioned to operations and all benefits realised. Data asset build is progressing with standardised data access controls added to the scope.
Q2 21-22 | Department of Health | DH | 2653 | Website Replatforming | Health | Communication | Redesigning and replatforming key strategic departmental websites to deliver improved service delivery, enhanced functionality, reduced costs and meet business and customer needs aligning with the department's digital strategy. | Closed - Completed | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) | 2021-10-28 | Agile | 2018-09-29 | 2018-12-31 | 2019-02-15 | 2019-02-25 | 1 | 76800 | 2019-02-25 |  | 2019-10-30 | 2021-10-28 | 0 | 3000000 | Green | Green | Green | Green | Green | Project has successfully delivered and is now closed.
Q2 21-22 | Ambulance Victoria | AVS | 2666 | Enterprise Resource Planning Project | Health | Human Capital / Workforce Management | The ERP project will deliver a new integrated enterprise platform to manage rosters and claims. This will automate and streamline processes to enhance and enable effective resource management to meet the demand of AV's services | Delivery | Cost Reduction (Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2018-02-01 | 2019-06-30 | 2019-08-20 | 2019-08-20 | 320000 | 343634 | 2019-08-26 |  | 2022-06-30 |  | 10137107 | 9486636 | Green | Green | Amber | Amber | Red | The project has been reported as red status reflecting an ongoing 'pause' whilst the review findings are considered and a business case with recommended path forward is developed.
Q2 21-22 | Ambulance Victoria | AVS | 2667 | Predictive Analytics Capability | Health | Business Intelligence,Analyses and Statistics ,Knowledge Discovery ,Reporting | Establish organisational real time decision support along with predictive analytics capability. The introduction of modern data analysis will ensure critical information can be provided to paramedics when they need it. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2018-04-10 | 2018-11-25 | 2019-05-27 | 2019-05-27 | 282000 | 267500 | 2019-07-17 |  | 2021-06-30 | 2021-12-31 | 12018000 | 8810721 | Amber | Red | Red | Red | Red | The program has been reported as red status due to identified defects in the platform affecting user acceptance testing. Program delivery remains paused whilst the technical expert review findings are considered and a recommended path forward determined.
Q2 21-22 | Victoria Police | VicPol | 2687 | Mobile Automated Number Plate Recognition | Law and Justice | Development and Integration ,Knowledge Management ,Search ,Visualisation | The Mobile Automated Number Plate Recognition (ANPR) project will facilitate the roll out of an integrated ANPR and in car video (ICV) system to 221 vehicles, which will improve road and community safety across the state. | Closed - Completed | Compliance (Non Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial) | 2021-12-31 | PRINCE2 | 2017-06-30 | 2017-10-02 |  | 2017-10-02 | 0 |  | 2017-10-03 |  | 2021-07-01 | 2021-12-31 | 36617000 |  | Amber | Amber | Amber | Amber | Green | The overall project status was green at project closure on 31 December 2021. The project’s funding carryover request from FY 2020-21 to FY 2021-22 was approved to support a six-month project extension through to 31 December 2021.
Q2 21-22 | Department of Education and Training | DET | 2690 | Asset Information Management Systems (AIMS) | Education | Content Management,Data Management,Assets/Materials Management | This will deliver a new Asset Information Management System to manage schools land and building assets enabling evidence-based decision making at both DET Corporate & School level and support attestation to Asset Management Accountability Framework. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2017-08-01 | 2019-07-31 | 2019-09-30 | 2019-09-30 | 2963222 | 2562342 | 2019-10-01 |  | 2022-09-30 | 2022-11-30 | 12956778 | 16420894 | Green | Green | Green | Green | Green | The AIMS school deployment for 2021 has been completed with 167 schools deployed to AIMS. A further 336 schools are scheduled for deployment to AIMS in February and March 2022. The schools deployment schedule for the remainder of 2022 has been finalised. The AIMS Investment Model has successfully gone live. Final review on Relocatable and Make safe designs are being undertaken with deployment planned in the first and second calendar quarters of 2022. Implementations are planned for the March April timeframe.
Q2 21-22 | Department of Environment, Land, Water and Planning | DELWP | 2730 | VGV Going Digital Project | Property and Planning | Management of Process ,Customer Initiated Assistance,Data Management,Records Management ,Reporting ,Knowledge Management ,Tracking and Workflow | Valuer-General Victoria Go Digital project will transfer paper-based valuation requests and records into a digital system to reduce the reliance on paper-based systems and to improve the accuracy of valuation data. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2017-06-30 | 2017-09-30 |  | 2017-11-30 | 88000 |  | 2018-11-30 |  | 2019-09-30 | 2022-06-30 | 518841 | 2425139 | Amber | Amber | Amber | Amber | Green | The project is now reporting Green as a new baseline has been approved. The project is progressing a planned.
Q2 21-22 | Alfred Health | ALFRED | 2754 | Implement eTQC Phase Two program to upgrade clinical information systems to significantly improve electronic timely quality care for our patients | Health | Collaboration ,Communication,Data Management,Knowledge Discovery ,Management of Process ,Reporting ,Tracking and Workflow | Development and implementation of Phase Two of the electronic-Timely Quality Care (eTQC) project that optimises products introduced in phase 1 and explands EMR scope to improve clinical real-time data capture management and patient care services | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2019-01-01 | 2019-06-30 |  | 2019-07-01 | 0 | 5051100 | 2019-07-01 |  | 2020-12-31 | 2022-03-31 | 14695182 |  | Green | Green | Green | Green | Green | Project has been delayed due to COVID-19. Project closure now planned for Q3 2021/2022.
Q2 21-22 | Department of Health | DH | 2770 | Windows 10 Upgrade | Community Services | Systems Management | To upgrade the department's standard operating environment on desktops and laptops to Windows 10 to leverage the wider breadth of modern IT service offerings. | Postponed | Efficiency/Productivity (Non Financial) | 2020-03-31 | PRINCE2 | 2019-03-01 | 2019-06-15 |  | 2019-06-15 | 250000 | 250000 | 2019-07-01 |  | 2020-06-30 |  | 4672022 | 5172022 | Amber | Amber | Amber | Amber | Amber | Windows 10 project remains on hold due to staff not being available to receive upgrade and training during COVID-19 response. Project expected to recommence in the next calendar year with a revised plan.
Q2 21-22 | Victorian Rail Track | VicTrack | 2778 | RRCN IT and Security Uplift | Transport and Vehicles | Security Management ,Systems Management | Virtualization of servers and security segmentation for Regional Rail Connectivity Network (RRCN). The project will deliver a more secure network that is Victorian Protective Data Security Standards (VPDSS) compliant. | Closed - Completed | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2021-12-13 | VicTrack PMF | 2017-08-01 | 2018-06-19 |  | 2018-06-19 | 0 |  | 2018-06-25 |  | 2020-06-19 | 2021-11-30 | 2600000 | 5345223 | Red | Green | Amber | Green | Green | The Regional Rail Connectivity Network (RRCN) Security Uplift project was successfully completed. Accredited Rail Operators (ARO’s) continue to operate on the new (and secure) RRCN system without any issues.
Q2 21-22 | Hume Rural Health Alliance | HRHA | 2783 | Central Hume Partnership PAS Replacement | Health | Data Management,Knowledge Management ,Management of Process ,Records Management ,Tracking and Workflow,Visualisation | The project will deliver a new Patient Administration System across 7 health services, improving information sharing within the Central Hume Partnership, improved information security and system availability to support timely provision of healthcare. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-08-05 | 2019-08-30 | 2019-08-05 | 2019-08-30 | 2400000 | 75000 | 2019-10-21 |  | 2021-06-30 | 2022-09-30 | 2200000 | 5417462 | Red | Red | Red | Red | Red | Project is being rebaselined. Project is continuing to progress with project activities while in parallel the overarching schedule is being aligned to overarching HUME Regional delivery.
Q2 21-22 | WorkSafe Victoria | WorkSafe | 2795 | Inspectors Toolkit | Government and Economy | Communication,Collaboration ,Development and Integration ,Systems Management | Implementation of the 2030 Inspector's Technology Kit, including purchase of iPads, iPhones and device configuration development. Expected benefits include increased reporting quality and operational efficiency gains. | Closed - Completed | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) | 2021-12-20 | PMBoK | 2019-05-01 | 2019-06-30 | 2019-10-31 | 2019-10-31 | 0 |  | 2019-10-31 |  | 2020-04-07 | 2021-11-30 | 1479613 | 1734295 | Green | Green | Green | Green | Green | Project completed - final closure report due Jan 2022.
Q2 21-22 | Victorian Rail Track | VicTrack | 2797 | Transport and Government Secure Network (TGSN) | Transport and Vehicles | Routing and Scheduling | To upgrade VicTrack's fixed Telecommunications network. The current network has various elements which are obsolete or becoming obsolete there is lack of spare equiments and reduced vendor support. 3 years project to deliver new technology. | Delivery | Risk Reduction (Non Financial) |  | VicTrack PMF | 2019-06-03 | 2019-10-01 | 2020-03-02 | 2020-03-02 | 0 | 0 | 2020-03-02 |  | 2023-06-30 |  | 69000000 |  | Green | Green | Green | Green | Green | The project is tracking well with the construction of the Optical Transport Network (OTN) completed.
Q2 21-22 | Department of Justice and Community Safety | DJCS | 2799 | Network Uplift Program | Law and Justice | Systems Management | To get all DJCS sites on the same comparable level of capability to support Win 10 roll-out and to apply the same service delivery principles and services to all sites. Includes centralisation of file and print services and provision of WIFI. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Project Management Excellence | 2018-11-01 | 2019-05-17 |  | 2019-05-17 | 0 |  | 2019-05-17 |  | 2021-06-30 | 2022-06-30 | 6148000 | 8938918 | Amber | Green | Green | Green | Green | 8 of 16 correctional site refreshes complete. Delivery has been affected by COVID-19, with slow delivery of network equipment, and workplace restrictions limiting ability to implement. Based on the available resources and state COVID-19 roadmap, these issues are not expected to impact the forecast project closure. Additional funds approved by Steering Committee for site remediation. Project on track.
Q2 21-22 | Melbourne Water | MELB Water | 2801 | Image processing and analytics | Environment and Water | Assets/Materials Management,Analyses and Statistics | This project will implement image processing and analytics for sewerage assets, which will efficiently analyse data captured to assist with managing risks associated with failure mechanisms such as corrosion within the sewer transfer network. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2019-04-17 | 2019-08-20 | 2020-10-15 | 2020-11-17 | 0 |  | 2020-11-17 |  | 2021-10-06 | 2022-02-24 | 1459302 | 1206029 | Green | Green | Green | Green | Green | Delay in project due to challenges around setting up the user acceptance (UAT) and Production (PROD) environments in the cloud. These issues have since been resolved and qualitative testing in in progress.
Q2 21-22 | Department of Health | DH | 2812 | Oracle Financials Upgrade | Community Services | Financial Management | The project will deliver an Oracle upgrade to the latest release of Oracle Cloud platform including the Chart of Accounts rationalisation and standard business processes to provide DH and DFFH with an efficient financial and procurement system. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-05-20 | 2019-12-31 | 2019-11-29 | 2019-11-29 | 1885550 | 964956 | 2021-05-05 |  | 2022-12-30 |  | 25475450 | 28550189 |  |  |  |  | Amber | Procurement completed based on original scope. Vendor engaged and completed an Oracle design feasibility study. Extensive analysis of interfacing applications has commenced. Program business case to be reviewed to align under the whole of Victorian Government Common Corporate Platform initiatives. Schedule and cost will then be updated to reflect any approved changes.
Q2 21-22 | Department of Education and Training | DET | 2819 | Kindergarten Information Management System (KIMS) Reform | Education | Development and Integration ,Financial Management | The project will replace the kindergarten funding system with a Cloud based technology platform to ensure ongoing functionality, rapid implementation and support for the Education State Early Childhood Reform Plan’s key reforms. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2018-04-26 | 2019-06-28 | 2019-06-28 | 2019-06-28 | 0 | 787836 | 2019-06-28 |  | 2020-03-27 | 2022-12-31 | 15637064 | 21442704 | Amber | Green | Amber | Amber | Green | The KIMS Reform project status is green. The project is on track and due to be delivered within budget by the scheduled date (December 2022). The November 2021 release went Live successfully and the deployment of the new Pre School Field Officer function (Multi-user login access) was completed in December 2021, with training for DET and external users delivered in November 2021. The remaining activities include delivery of remaining functionalities, integration and interface pieces, backlog features, and decommissioning legacy systems.
Q2 21-22 | Yarra Valley Water | YV Water | 2821 | Enterprise Historian | Environment and Water | Data Management | Acquisition, storage, analysis, and presentation of large volumes of time series data – allowing it to be combined with data from other core systems for analysis and improved decision making. | Postponed | Efficiency/Productivity (Non Financial) | 2021-04-01 | PRINCE2 | 2018-11-01 | 2019-08-30 | 2019-12-27 | 2019-12-27 | 240000 | 300000 | 2019-12-30 | 2020-01-01 | 2021-12-30 | 2022-06-30 | 4778000 | 5786280 | Green | Amber | Amber | Amber | Amber | Project on hold
Q2 21-22 | Yarra Valley Water | YV Water | 2822 | Network Communications and IoT Device Management | Environment and Water | Assets/Materials Management | IoT device telecommunications services and device management platform. | Delivery | Cost Reduction (Financial) |  | PRINCE2 | 2019-05-01 | 2020-01-31 | 2020-10-14 | 2020-10-14 | 350000 | 1300000 | 2020-10-19 |  | 2022-06-30 | 2022-12-31 | 3715000 | 3715059 | Green | Green | Green | Green | Green | System Integration Testing for the V1 Digital Meter & devices will be completed in February. The project will then focus on Digital Meter on-boarding within YVW systems.
Q2 21-22 | South East Water | SE Water | 2823 | Digital Utility Core Capability | Environment and Water | Customer Relationship Management,Data Management,Development and Integration ,Reporting | Delivery of end to end business processes across meter management, billing and alerts & alarms. This will enable customer data to be exposed via the portal and internal CSO views as well as monitoring meter and water usage behaviour. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Agile | 2019-06-10 | 2019-06-20 |  | 2019-06-21 | 25000 |  | 2019-06-24 |  | 2020-02-28 | 2023-11-03 | 0 | 19000000 | Green | Green | Green | Green | Green | December go live has been completed and new business functionality is being progressed to define future needs. This new capability will deliver digital utility process at scale and more meters are rolled out in the field.
Q2 21-22 | Department of Transport | DOT | 2824 | Rail Operational Performance Project (ROPP) | Transport and Vehicles | Systems Management,Data Management | The objective of the new Rail Operational Performance Project (ROPP) solution is to provide an efficient, future proof system that enables compliance with the MR4 contract and supports the enterprise approach to rationalise the data management proces | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | PTV Investment Lifecycle | 2018-07-02 | 2019-06-30 | 2021-05-11 | 2021-05-11 | 2200000 | 3639698 | 2021-05-12 |  | 2022-04-08 |  | 3560302 |  |  |  | Amber | Amber | Amber | Technical release 1 and 2 completed. Technical release 3 is on track for January 2022 delivery. Due to Covid impact on resourcing, Release 4 and 5 may be delayed. Support arrangement workshop scheduled to review the final support model before February 2022.
Q2 21-22 | Department of Transport | DOT | 2825 | Automated Vehicle Monitoring Replacement (AVMR) | Transport and Vehicles | Analyses and Statistics ,Assets/Materials Management,Systems Management,Communication | The tram AVM system is used for the preparation management and monitoring of all tram services across the tram network. It is used to communicate with drivers and monitor and record tram location and status. | Initiated |  |  | PTV Investment Lifecycle | 2018-07-02 | 2020-06-30 | 2022-06-30 |  | 2800000 | 4919000 | [11 empty] | Development of the Strategic Roadmap for AVM Replacement business capabilities is complete. Assessment of detailed technical functionality and development of a detailed Program plan are proposed to be undertaken as the next steps.
Q2 21-22 | Department of Justice and Community Safety | DJCS | 2832 | Practice Management System | Law and Justice | Tracking and Workflow | This project will replace the existing VGSO's Practice Management System to provide streamlined processes improved information sharing and increased data capture. | Delivery | Cost Avoidance (Financial), Increased Revenue (Financial) |  | Project Management Excellence | 2018-08-31 | 2018-09-07 |  | 2018-09-07 | 0 |  | 2019-09-30 |  | 2021-04-01 | 2022-07-01 | 1400000 | 1500000 | Green | Green | Green | Green | Green | Delays due to the impact of COVID-19 on available resources, with priorities needing to change to support staff during this period. Project is tracking well against revised schedule.
Q2 21-22 | Department of Environment, Land, Water and Planning | DELWP | 2834 | Unified Communication & Collaboration | Employment and Workplace | Collaboration ,Communication | The Unified Communication & Collaboration program will upgrade and integrate the video conference, telephony, meeting rooms and collaboration tools to improve the information sharing, communication and productivity of the staff across DELWP. | Closed - Completed | Cost Reduction (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2021-12-01 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-08-05 | 2019-11-01 | 2019-11-01 | 2020-05-29 | 176871 | 891173 | 2020-05-29 |  | 2021-02-28 | 2021-11-30 | 2999104 | 3632630 | Amber | Amber | Green | Green | Green | The program was delivered within the committed budget and schedule. The program was formally closed on 01st December.
Q2 21-22 | Department of Premier and Cabinet | DPC | 2841 | ACHRIS Phase 3 – Amalgamation of the CHMP database | Culture, Sport and Recreation | Management of Process | ACHRIS Phase 3 will integrate critical business systems to deliver a holistic approach to better manage and protect Aboriginal cultural heritage. The new system will deliver business efficiencies and reduce statutory red tape. | Postponed | Compliance (Non Financial), Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) | 2021-06-30 | Agile | 2019-07-01 | 2022-06-30 | 2019-10-14 | 2019-10-15 | 0 |  | 2019-10-15 |  | 2022-06-30 |  | 1231413 |  | Green | Amber | Amber | Amber | Amber | The project is still postponed whilst we confirm funding for 2021/2022 and 2022/2023 financial years to inform the rescoping options for the project.
Q2 21-22 | Department of Justice and Community Safety | DJCS | 2851 | Digital Radio Upgrade Program - Stage 2 | Emergencies and Safety | Communication | This Program will transition Ambulance Victoria's (AV) regional comms off analogue radio system onto the State’s shared digital network and replace AV's regional radio fleet to provide secure comms and improve community safety and health outcomes. | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Project Management Excellence | 2019-07-01 | 2019-07-02 |  | 2019-07-02 | 0 |  | 2019-07-03 |  | 2023-06-30 | 2024-12-30 | 70378000 |  | Amber | Amber | Green | Green | Green | The project is tracking well against scope budget and schedule.
Q2 21-22 | Victoria Legal Aid | VLA | 2852 | Digital Legal Aid Program | Law and Justice | Management of Process | VLA will leverage technology and data to significantly improve client service, productivity and access to justice. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2018-07-01 | 2019-02-19 |  | 2019-02-20 | 0 |  | 2019-02-22 |  | 2021-07-30 | 2021-12-30 | 14500000 |  | Amber | Amber | Amber | Green | Green | Digital Service Record pilot commenced in late November 2021. Website redevelopment is progressing to plan. Plans finalised and VLA Board approval received to extend program end date. Reporting under new structure and to revised budget and schedule will commence in Q3 FY22.
Q2 21-22 | Department of Justice and Community Safety | DJCS | 2855 | Serious Offenders Reform Program - ICT Program | Law and Justice | Development and Integration | The ICT Program supports the upgrade of existing systems to support changes to legislation, policy and business processes as part of the serious offender reform program. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Project Management Excellence | 2017-04-01 | 2017-11-30 |  | 2017-12-01 | 1375000 |  | 2017-12-01 |  | 2020-05-31 | 2021-11-29 | 11830000 | 16718486 | Amber | Red | Red | Red | Red | The final project in the SORP ICT program, the Dynamic Risk Assessment of Offender Re-entry (DRAOR), has been put on hold due to technical and schedule uncertainty, requiring an evaluation of project viability to be carried out. A critical evaluation of the revised plan was undertaken, including an assessment of further costs confidence in delivery schedule and ability to meet core business requirements. Approval of the recommended approach is being sought through the appropriate governance forums.
Q2 21-22 | Western Health | WH | 2868 | Electronic Medical Record (EMR) Phase 2 | Health | Records Management | This project represents the next phase of the EMR at Western Health (WH) on its path towards bringing it to a fully digital hospital which is expected to provide improved efficiency and quality of care across the continuum of the organisation. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2019-05-29 | 2020-02-03 | 2019-07-05 | 2019-07-05 | 0 |  | 2021-02-22 |  | 2025-12-31 | 2026-06-30 | 64400000 | 69447738 |  | Green | Green | Red | Green | Vendor resourcing constraints addressed and change to project schedule approved by WH. Quarterly status changed to Green .
Q2 21-22 | Western Health | WH | 2869 | Active Directory (AD) Seperation | Health | Organisational Management ,Security Management | Western Health (WH) shares the same Active Directory (AD) domain with Melbourne and Northern Health services. The objective is to create a WH AD, reducing potential cyber security risks and providing WH its own AD environment | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2019-05-06 | 2019-11-15 | 2019-09-30 | 2019-12-06 | 0 |  | 2020-06-01 |  | 2021-12-23 | 2022-06-29 | 1876000 | 2756677 | Green | Green | Green | Green | Green | The Project is currently in execution stage.
Q2 21-22 | Ambulance Victoria | AVS | 2877 | Connected Paramedic | Health | Communication,Collaboration ,Knowledge Management | The Connected Paramedic Program will introduce digital connectivity to paramedics and integrate internal systems, allowing the provision of digital tools for paramedics to connect and share data within AV and between AV and the broader health system. | Postponed |  | 2020-07-01 | PMBoK | 2019-07-01 | 2021-06-30 | 2020-06-30 |  | 7700000 | 827766 |  |  |  |  | 0 | [6 empty] | Project remains on hold - pending review in FY23
Q2 21-22 | CenITex | CenITex | 2882 | Regional Site Performance & Resilience Improvement | Government and Economy | Assets/Materials Management | To improve the performance and reliability of network infrastructure to support a modern and agile public-sector workforce in regional Victoria | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2019-07-04 | 2019-07-25 | 2019-09-03 | 2019-09-03 | 0 | 0 | 2019-09-03 |  | 2020-06-30 | 2022-06-30 | 8680000 | 8266956 | Amber | Amber | Amber | Amber | Green | 97 of 98 sites are complete.
Q2 21-22 | Peter MacCallum Cancer Centre | Peter MAC | 2884 | People Systems | Health | Human Capital / Workforce Management ,Human Resources | The People Systems Program will deliver HRIS and Payroll systems to increase efficiency and improve data security and integrity by eliminating paper timesheets and manual processes. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2019-07-01 | 2019-11-30 | 2021-06-30 | 2021-06-30 | 40000 | 377350 | 2021-07-19 |  | 2022-06-30 |  | 2572000 |  |  |  |  | Green | Green | Project has entered the testing phase and is presently tracking to schedule and budget.
Q2 21-22 | Department of Education and Training | DET | 2886 | FSD-Oracle Cloud Program | Education | Analyses and Statistics ,Systems Management,Financial Management | The project will deliver integrated Cloud applications to meet WoVG Finance Statement of Directions improving information consolidation and analysis across government utilising common application tools, reducing ongoing maintenance and costs. | Delivery | Compliance (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-07-29 | 2020-06-30 | 2020-09-30 | 2020-11-02 | 0 | 3391959 | 2020-11-02 |  | 2021-11-01 | 2023-03-31 | 2861041 | 5324616 | Green | Amber | Red | Red | Amber | The program has until recently been paused in line with the DPC direction regarding the Common Corporate Platform program from Digital Victoria. However, in September 2021 DPC met with DET and confirmed that DET could continue with its roll out of the Oracle Cloud Program with the scope expanded to include Sourcing to Contract (S2C). Following the requirement to engage a Functional Consultants to fulfil the development of the S2C solution, work is now progressing to understand the business requirements, timelines, and overall resourcing requirements to deliver this component successfully. Additional funding has also been secured for the Program
Q2 21-22 | Barwon Region Water Corporation | BR Water | 2890 | C1220 Sherwin 4CX Project | Environment and Water | Management of Process | Internal development of key line of business applications to improve customer experience (CX) including:- Land Development, Water & Sewer Connections, and Trade Waste. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2018-11-01 | 2019-04-01 |  | 2019-06-27 | 520000 |  | 2019-06-27 |  | 2020-11-28 | 2022-03-31 | 1846000 | 1896000 | Green | Green | Green | Green | Green | Incremental functionality is still being progressively deployed as soon as possible.
Q2 21-22 | Essential Services Commission | ESC | 2899 | VEU system development based on Dynamics 365 platform | Environment and Water | Analyses and Statistics ,Customer Relationship Management,Development and Integration | Develop and configure the new Victorian Energy Upgrades (VEU) System on Dynamics 365 platform according to the detailed business requirements utilising the Microsoft Azure Cloud services and Office 365 ecosystem. | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial), Eco Improvement (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2018-04-16 | 2019-09-26 |  | 2019-09-26 | 48822 |  | 2019-10-28 |  | 2020-10-30 | 2022-03-18 | 2291878 | 2606056 | Green | Red | Red | Green | Green | The project is on green status against the re-baselined scope. The re-baselined scope is called "project Phase 1" and has a delivery date of 18 March 2022. A project Phase 2 is required to build Phase 2 that includes new Government requirements for the VEU program and detailed workflow customisations.
Q2 21-22 | Bendigo Kangan Institute of TAFE | BKI TAFE | 2903 | Student Journey Transformation | Education | Customer Relationship Management,Data Management,Development and Integration ,Records Management ,Reporting | The program will deliver capability and user experience improvements across the end-to-end student lifecycle. The program is necessary to transform people, process and systems from a highly manual environment, using complex and out of date systems. | Delivery | Cost Reduction (Financial), Increased Revenue (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-01-07 | 2019-12-20 |  | 2019-12-20 | 2174000 | 1700000 | 2020-01-06 |  | 2022-09-30 | 2023-05-31 | 1966000 | 29228000 | Green | Green | Red | Green | Green | Project is tracking green overall. Delivery of JR Plus student management system non-production pilot/ parallel run scheduled for Q3 21-22 is on track. Inter-project dependencies are emerging and being closely monitored.
Q2 21-22 | Department of Justice and Community Safety | DJCS | 2905 | DJR Legacy Server Consolidation | Law and Justice | Systems Management | The Legacy Server Consolidation program will be responsible for the upgrade of all Windows 2003/2008 & Solaris 8/9 servers. The legacy hardware poses a high risk and this project aims to ensure a compliant and secure system. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Project Management Excellence | 2019-07-01 | 2019-09-30 |  | 2019-09-30 | 0 |  | 2019-10-01 |  | 2020-12-31 | 2022-02-28 | 1894400 | 1867786 | Green | Green | Amber | Amber | Amber | The delivery end date has now been revised to Feb 2022. DJCS has decommissioned all Windows 2003 & 2008 servers within its scope and is collaborating with teams who have dependencies to complete the remediation activities on the remaining servers.
Q2 21-22 | Department of Justice and Community Safety | DJCS | 2906 | Prison Industries Enhancement Phase 2 Project | Law and Justice | Management of Process | The primary purpose of the PIE project is to deliver value for money prison services by exploring ICT opportunities for Prison Industries (PI) cost recovery, as well as through promoting PI as a preferred supplier to internal business units. | Delivery | Cost Reduction (Financial), Increased Revenue (Financial), Social Improvement (Non Financial) |  | Project Management Excellence | 2019-09-02 | 2020-03-27 | 2020-04-30 | 2020-05-01 | 0 |  | 2020-05-04 | 2020-10-29 | 2020-10-30 | 2022-07-29 | 2140000 | 3582310 | Green | Green | Green | Green | Green | The delivery end date has been revised to July 2022 due to complex technical dependencies and limited access to correctional sites with current COVID-19 restrictions across the state. The new timeline has been approved by the Project Control Group. The project is tracking well against scope, budget and schedule.
Q2 21-22 | Dental Health Services Victoria | DHSV | 2909 | Mobile Diagnostic Imaging | Health | Records Management | The objective of this project is to enable Public Oral Health providers to access diagnostic images acquired from School Dental Program in a timely manner, and at the point of care. | Initiated |  |  | PRINCE2 | 2019-06-28 | 2020-09-30 | 2021-11-30 |  | 0 | 200000 | [11 empty] | The vendor procurement and contract negotiations have continued through the 21/22 Q2 period. The project schedule was rebaselined and approved by the project board, with initiations scheduled to conclude 2021/22 Q2
Q2 21-22 | Department of Education and Training | DET | 2919 | eduPass Authorisation | Education | Content Management,Systems Management | The eduPass Authorisation project will deliver a centralised access management system to simply and automatically ensure timely and appropriate rule-based user access to Department IT applications and data. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2015-07-01 | 2019-12-16 |  | 2019-12-16 | 435357 |  | 2019-12-17 |  | 2020-12-31 | 2022-01-31 | 4185300 | 3312200 | Green | Green | Green | Green | Green | The base solution went live on 18 December 2020. Several Applications have been successfully onboarded to the platform. The remaining applications in-scope will be integrated during Q2 2021/22. Project is on track to complete within budget and on schedule.
Q2 21-22 | Department of Education and Training | DET | 2921 | Network Evolution Project | Education | Communication,Systems Management | The project will replace end of life and end of support network hardware for Firewalls, Switches & Routers, and Application Gateway Controllers, to improve network performance, security and monitoring for the Department. | Closed - Completed | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2021-12-31 | PRINCE2 | 2019-02-21 | 2020-06-30 | 2021-01-29 | 2021-01-29 | 0 | 481571 | 2021-01-29 |  | 2021-11-11 | 2021-12-31 | 7351541 | 6162423 |  | Green | Amber | Amber | Green | The overall project RAG status is Green this reporting period. The project has successfully put into production the three new technologies into our technical environment. 1. Routing & switching 2. Firewalls and Threat Prevention 3. Gateways Services The remaining services to be migrated onto these new technology streams will be handled with BAU resources. This is the last report as the project was closed in December 2021.
Q2 21-22 | Peninsula Health | PEN Health | 2926 | Enhanced eReferral Project | Health | Systems Management | Replace UNITI within Community Health and Rehabilitation Ageing Pain and Palliative Care Services by expanding the use of MasterCare in PH (subject to procurement rules) to deliver secure messaging capability (across PH GP’s and other external party) | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial), Increased Revenue (Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2019-11-25 | 2020-05-12 |  | 2020-05-12 | 0 |  | 2020-05-12 |  | 2021-08-03 | 2022-06-30 | 1349000 |  | Green | Green | Amber | Green | Amber | The project is tracking well against scope however timeline is challenged due to current climate and the delivery of a dependent desktop virtualization project.
Q2 21-22 | Department of Transport | DOT | 2929 | DTRS Critical Service Continuity | Transport and Vehicles | Systems Management | The Digital Train Radio System (DTRS) supports safety-critical mobile radio communications for Melbourne metropolitan train services. | Delivery | Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | PTV Investment Lifecycle | 2019-10-28 | 2020-08-31 | 2019-12-16 | 2019-12-16 | 0 |  | 2019-12-16 |  | 2023-01-01 |  | 83000000 |  |  |  |  | Amber | Amber | Overall project status is reported amber due to potential risk and impacts caused by COVID related delays. First phase of transmission connectivity complete at control centers with final implementation phase underway. 75% of the radio sites are operational. First successful test call made at first data centre tracking to Go Live in mid-February 2022 .
Q2 21-22 | Department of Transport | DOT | 2931 | Human Capital Management (HCM) Project | Transport and Vehicles | Customer Initiated Assistance,Human Capital / Workforce Management ,Human Resources,Tracking and Workflow | To lead the implementation of SAP SuccessFactors (including Payroll) for DoT as the initial tranche of the broader WoVG program managed by OneVPS. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-02-03 | 2020-06-30 | 2021-07-30 | 2021-08-02 | 0 |  | 2021-08-09 |  | 2022-07-04 |  | 0 | 25858946 |  |  |  | Amber | Green | Overall status of the project is green. Sprint 1 testing has completed successfully. Configuration changes are being worked through with WoVG team and the vendor team.
Q2 21-22 | South West Alliance of Rural Health | SWARH | 2932 | SWARH Windows 2003/2008 Server Refresh and SQL server uplift | Health | Data Management,Development and Integration ,Systems Management | To move SWARH and Barwon Health applications and services from Windows 2003/2008 to a supported environment. This will address the risk of operating in a legacy environment. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | PMBoK | 2020-03-30 | 2020-05-30 |  | 2020-05-30 | 60000 |  | 2020-06-22 | 2020-09-30 | 2020-12-24 | 2022-03-30 | 2664660 | 2664660 | Green | Amber | Amber | Amber | Amber | The project reported an Amber status due to data migration and system related issues associated with migrating legacy systems and staff shortages due to COVID. The project team is working closely with vendors and application owners to identify gaps and implement specific application solutions. A change request is being prepared to be presented at the next Steering Committee meeting to approve the revised delivery end date of 30th March 22.
Q2 21-22 | WorkSafe Victoria | WorkSafe | 2935 | Digital Employee Experience & Intranet | Government and Economy | Communication | Implement a corporate intranet platform that will support WorkSafe's digital employee experience strategy and digital workplace. Delivering the project will drive significant productivity improvements and drive employee engagement. | Delivery | Efficiency/Productivity (Non Financial) |  | PMBoK | 2019-08-01 | 2020-04-30 | 2021-04-22 | 2021-04-22 | 0 | 903000 | 2021-04-22 |  | 2021-10-12 | 2022-03-08 | 1815440 |  |  |  | Green | Green | Green | Project has gone live on 13 Dec.
Q2 21-22 | WorkSafe Victoria | WorkSafe | 2937 | ACCS eCAM Replacement | Government and Economy | Customer Relationship Management | Replacement of eCam and Lotus Note systems with SalesForce, and associated applications to manage conciliation cases. Benefits realised include significant reduction in manual effort, improved usability as well as reducing legacy system dependencies. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | PMBoK | 2020-02-03 | 2020-06-30 | 2021-02-12 | 2021-02-26 | 0 | 1278689 | 2021-02-26 |  | 2021-07-30 | 2022-03-31 | 4642607 |  |  | Green | Amber | Red | Red | Overall the project's build activities have taken longer than originally anticipated due to project complexity, COVID-19 restrictions enforced on the project teams and changes to key supplier personnel.
Q2 21-22 | Greater Western Water Corporation | GW Water | 2939 | Billing and Collection | Environment and Water | Assets/Materials Management,Customer Initiated Assistance,Customer Preferences,Customer Relationship Management,Data Management,Development and Integration ,Document Management ,Financial Management,Knowledge Management ,Management of Process ,Records Management ,Reporting ,Routing and Scheduling,Tracking and Workflow | Replacement of the core Billing and Collections system with a modern ‘fit-for-purpose’ solution to allow CWW to better serve our customers and bring operational efficiencies | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-09-23 | 2021-01-31 | 2021-05-25 | 2021-05-25 | 790000 | 4575000 | 2021-05-25 |  | 2023-06-30 |  | 39965000 |  |  |  | Green | Green | Green | The project concluded expressions of Interest for a platform upgrade. Additionally, there have been three waves of functional improvements to the existing platform to ensure improved integration and efficiencies with immediate benefits.
Q2 21-22 | Victorian Funds Management Corporation | VFMC | 2943 | Data and Analytics | Business and Industry | Analyses and Statistics | The project will deliver an Enterprise Data Management Platform to underpin VFMCs comprehensive data and IT transformation strategy which will enrich and validate multiple sources of investment data into one centralised location. | Delivery | Cost Reduction (Financial), Risk Reduction (Non Financial) |  | Agile | 2018-08-13 | 2019-10-02 |  | 2019-10-02 | 778436 |  | 2020-02-03 |  | 2021-06-30 | 2022-06-30 | 19181333 |  | Amber | Green | Amber | Red | Green | Re-set/refresh of the next phase is currently underway to sequence deliverables and reset governance and sprint process.
Q2 21-22 | Department of Jobs, Precincts and Regions | DJPR | 2956 | Resources Management System Victoria (RMSVIC) Project | Business and Industry | Analyses and Statistics ,Content Management,Customer Initiated Assistance,Customer Relationship Management,Data Management,Document Management ,Management of Process ,Records Management ,Tracking and Workflow | The Project will deliver a Resources Management System Victoria (RMSVIC) in Salesforce to replace Resource Rights Allocation and Management (RRAM). Key benefits are a fit for purpose, tailored, flexible system supporting industry and the Regulator | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Reputation (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-11-01 | 2019-12-31 | 2020-02-26 | 2020-02-27 | 222500 |  | 2020-02-27 |  | 2021-12-31 | 2022-06-30 | 5920000 | 5122547 | Red | Amber | Red | Red | Red | Development of the new IT system's core foundation is progressing with 50% of the IT build complete noting continuing limitations on available resourcing and suitably qualified personnel.
Q2 21-22 | Yarra Valley Water | YV Water | 2957 | Core Switch Replacement | Environment and Water | Systems Management | Replacement of end of life core switching hardware. | Delivery | Risk Reduction (Non Financial) |  | PRINCE2 | 2020-01-01 | 2020-05-30 | 2020-05-11 | 2020-05-11 | 150000 |  | 2020-05-12 | 2020-05-12 | 2021-02-28 | 2022-03-31 | 2725600 |  | Green | Green | Green | Green | Green | Delivery end date extended. As-built documents complete. Project close process commenced.
Q2 21-22 | Victorian Funds Management Corporation | VFMC | 2970 | IT Infrastructure Enhancement Program | Business and Industry | Systems Management | Supporting the objectives of the 2020 Strategic Plan in providing support for VFMC's future needs in an evolving technology landscape. The infrastructure must be able to rapidly scale up and down, be robust and stable to ensure business continuity. | Closed - Completed | Cost Avoidance (Financial), Risk Reduction (Non Financial) | 2021-10-29 | Waterfall | 2019-09-02 | 2019-09-24 |  | 2019-09-24 | 2500 |  | 2019-09-24 |  | 2021-06-30 | 2021-10-25 | 1691258 |  | Amber | Amber | Amber | Green | Green | Project is complete and is now closed.
Q2 21-22 | Department of Justice and Community Safety | DJCS | 2978 | Road Safety Package | Law and Justice | Assets/Materials Management | The Victorian Government has provided funding to modernise and expand the Road Safety Camera Program and significantly uplift mobile road safety camera operations. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Project Management Excellence | 2019-06-30 | 2020-09-30 | 2021-05-23 | 2021-05-23 | 2787000 | 2024184 | 2021-05-24 |  | 2022-04-21 | 2022-05-15 | 6967000 |  |  |  | Green | Green | Green | Project delivery (solution design phase) completed 4 weeks behind schedule. Training and organisational change management plan completed and under internal review. Solution build is in progress.
Q2 21-22 | Department of Premier and Cabinet | DPC | 2979 | Automated Briefing and Correspondence (ABC) | Government and Economy | Tracking and Workflow | Design and deploy a single, digital document tracking system to manage all departmental briefings and correspondence, including management of drafting and approval workflows, maintenance of the historical record, and search and reporting capability. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-01-01 | 2020-08-07 | 2020-09-25 | 2020-09-25 | 348000 |  | 2020-09-28 |  | 2021-07-09 | 2022-06-30 | 1897740 |  | Amber | Green | Amber | Green | Green | ABC Solution phase 1 successfully launched on 24 November 2021. Support and continuous improvement processes established. Phase 1 operational handover complete.
Q2 21-22 | Major Transport Infrastructure Authority | MTIA | 2983 | Project Controls Solution | Transport and Vehicles | Management of Process ,Supply Chain Management | To identify and implement a preferred architecture and strategic approach for MTIA-wide project controls technology to bring process harmonisation resulting in greater efficiency, streamlined construction project delivery, and cost optimisation | Closed - Completed | Efficiency/Productivity (Non Financial) | 2021-11-25 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-05-25 | 2020-08-28 |  | 2020-09-22 | 1200000 |  | 2020-09-22 |  | 2021-06-04 | 2021-11-25 | 4052000 | 2994000 | Green | Amber | Amber | Green | Green | The PCS project closure was accepted on 25 November 2021 through formal governance. The project has transitioned to BAU Product Support.
Q2 21-22 | WorkSafe Victoria | WorkSafe | 2986 | People Experience Portal | Government and Economy | Human Capital / Workforce Management | Implementation of a Human Resources Information System to support Worksafe in the effective management of its workforce. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PMBoK | 2019-06-03 | 2020-06-30 | 2020-11-03 | 2020-11-03 | 756031 |  | 2020-11-04 |  | 2022-06-30 |  | 7159514 |  | Green | Green | Green | Green | Amber | Project is currently tracking Amber to schedule for current key internal milestones as a result of prioritisation of Chief Health Officers mandates that required implementation for COVID as well as further focus on system design and testing. Core module go live dates are under revision with stakeholders for agreement.
Q2 21-22 | WorkSafe Victoria | WorkSafe | 2987 | Enforcement & Advice | Government and Economy | Customer Relationship Management | Configuration and development of Salesforce CRM for Investigations & Prosecutions, Advisory, Licensing and Digital Channels functions. | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Social Improvement (Non Financial) |  | PMBoK | 2019-11-01 | 2020-04-30 |  | 2020-05-01 | 7000000 |  | 2020-05-01 |  | 2021-12-31 | 2022-04-22 | 60000000 | 66173077 | Green | Green | Green | Amber | Green | The project is on track to deliver to the expected quality, cost & schedule
Q2 21-22 | Melbourne Water | MELB Water | 2990 | Geospatial Program | Environment and Water | Assets/Materials Management,Content Management,Data Management,Knowledge Management ,Visualisation | Melbourne Water have wide ranging complex and critical business operations dependent on GIS technology. This project will significantly improve, modernise and extend the spatial capabilities available to business users and our operations. | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-05-15 | 2021-05-12 | 2021-05-19 | 2021-08-17 | 0 |  | 2021-08-17 |  | 2023-06-13 |  | 3718109 |  |  |  |  | Green | Green | Functional and non-functional specification is near finalisation and approval, confirmation of performance testing commitment has been requested from the vendor before the milestone is reached. Potential additional scope has been identified to the safety requirement. This may be material to delivery (3 weeks). Prototype tasks to propose next steps and progress with the evaluation with external stakeholders being worked on. All data model testing (excluding one application) has been completed. The application development environment has been rebuilt, to resolve an issue for this final application as additional patching is required in these environments before testing can be finalised.
Q2 21-22 | Transport Accident Commission | TAC | 3000 | AV Uplift TAC | Transport and Vehicles | Communication,Visualisation | AV equipment uplift to meet contemporary business needs of staff so they are able to present digital content from their device to other meeting participants and run web conferences with external parties. | Delivery | Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-04-16 | 2020-04-16 |  | 2020-04-16 | 0 |  | 2020-04-16 |  | 2020-12-31 | 2022-03-31 | 1612500 | 1612500 | Green | Green | Green | Red | Red | The overall project is tracking Red due to delays and possible additional scope. Mitigation plan is underway, including the finalisation of requirements and specifications for structural and electrical work and for hearing augmentation. The respective RFT to complete the work will be released to the market in February. A change request to revise end date will be submit for governance approval upon RFT result
Q2 21-22 | South West Alliance of Rural Health | SWARH | 3003 | Barwon Health Community Electronic Medical Record | Health | Content Management,Data Management,Forms Management,Management of Process ,Security Management ,Systems Management,Tracking and Workflow | Implementation of an Electronic Health Record (EHR) solution as part of Barwon Health (BH) Strategy and supportive of the broader DHHS and Government policy goals and focused on improving the quality and safety of the patient care that BH delivers. | Initiated |  |  | PMBoK | 2018-03-01 | 2020-10-01 | 2022-03-04 |  | 0 | 500000 | [11 empty] | The Implementation Planning Study has been completed. Negotiations are occurring with vendors to finalise documentation and present to the Board in March 2022.
Q2 21-22 | Department of Environment, Land, Water and Planning | DELWP | 3024 | Migration to Public Cloud | Emergencies and Safety | Systems Management | DELWP is moving its large suite of emergency management applications away from a legacy hybrid-cloud infrastructure into a corporate Microsoft Azure tenancy. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-09-07 | 2020-12-01 | 2021-02-12 | 2021-02-12 | 70000 |  | 2021-03-15 |  | 2022-06-30 |  | 10200000 | 4841632 |  | Green | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q2 21-22 | Department of Education and Training | DET | 3025 | eProcurement Solution Implementation | Education | Supply Chain Management ,Management of Process | This project will implement the eProcurement Solution for end-to-end source to contract functionality and contract management replacing the current Ariba platform which is approaching end of life. | Postponed | Compliance (Non Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) | 2021-04-16 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-07-06 | 2020-10-18 |  | 2020-10-18 | 0 |  | 2020-10-19 |  | 2021-06-30 |  | 1573670 |  | Green | Amber | Red | Red | Red | This project, which is part of a WoVG eProcurement initiative, has been paused at the request of the Department of Premier and Cabinet whilst processes are aligned across departments that will enable the benefits of common systems to be realised.
Q2 21-22 | Major Transport Infrastructure Authority | MTIA | 3028 | Reporting & Analytics Project | Transport and Vehicles | Business Intelligence | The project aims to implement a reporting and analytics environment for the Office of the Director-General to aggregate and store data from information systems of MTIA – thus enabling efficiency and accuracy of information reporting and analysis | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-05-01 | 2020-11-20 | 2021-05-26 | 2021-05-27 | 188000 | 486249 | 2021-05-27 |  | 2021-10-29 | 2022-02-09 | 2365751 | 2415679 |  |  | Green | Amber | Amber | Throughout this quarter the project team have focused on Phase 2 ‘Iterative Delivery’, a coordinated cycle of build/test/release for the major deliverables. Monthly Showcases have been facilitated demonstrating progress to the business.
Q2 21-22 | Fire Rescue Victoria | FRV | 3029 | Fire Rescue Portal | Emergencies and Safety | Systems Management | Design and implement an enterprise Fire and Rescue Services Portal. | Delivery | Compliance (Non Financial) |  | FRV Project Management Framework (PMF) | 2020-06-26 | 2020-12-16 |  | 2020-12-16 | 0 |  | 2020-12-17 |  | 2022-04-30 |  | 2109000 |  | Green | Amber | Green | Amber | Amber | The project is delayed due to issues identifying an appropriate vendor. An alternative approach is being planned with a Proof of Concept to be delivered this financial year.
Q2 21-22 | Fire Rescue Victoria | FRV | 3030 | Rostering and Shift Change | Emergencies and Safety | Systems Management | Purchase and implement a contemporary off the shelf Rostering and Shift Change system to replace multiple legacy systems. | Delivery | Efficiency/Productivity (Non Financial) |  | FRV Project Management Framework (PMF) | 2020-06-26 | 2020-12-08 | 2021-09-14 | 2021-09-14 | 0 |  | 2021-09-15 |  | 2022-11-02 |  | 3760000 |  |  |  |  | Green | Amber | Progress on the project has paused whilst current scope and schedule are reassessed to align with other initiatives.
Q2 21-22 | Fire Rescue Victoria | FRV | 3031 | Workplace Computing | Emergencies and Safety | Assets/Materials Management | Replacement of ex-Metropolitan Fire Brigade (MFB) workplace computing devices in excess of 4 years old. | Closed - Completed | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) | 2021-12-31 | FRV Project Management Framework (PMF) | 2020-01-20 | 2020-08-11 |  | 2020-08-12 | 0 |  | 2020-08-12 |  | 2021-06-30 | 2021-12-31 | 1496145 |  | Green | Green | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q2 21-22 | Department of Justice and Community Safety | DJCS | 3033 | Victims of Crime Financial Assistance Scheme | Community Services | Customer Initiated Assistance | The Project will deliver an ICT system centred around Case Management to deliver funds and support to Victims of Crime. The system will underpin the new financial assistance scheme approved by Cabinet. | Initiated |  |  | Project Management Excellence | 2019-01-04 | 2021-06-30 | 2022-06-30 |  | 3297000 | [12 empty] | The Victims of Crime Financial Assistance Scheme was allocated $22 million to ICT in the 2021-2022 Victorian State Budget. The ICT funds are held in contingency by Department of Treasury and Finance and requires approvals for its release. The FAS Reform Project has received endorsement by Digital Victoria and approval for the release of $2,971,000 funds is progressing well and expected in early 2022. [Note: Plan One activities are scheduled to be completed by end of November 2022, however the $2,971,000 includes funding for FTE connected to Plan Two activity through to 30 June 2023.
Q2 21-22 | WorkSafe Victoria | WorkSafe | 3047 | Data & Analytics Hub | Government and Economy | Analyses and Statistics ,Business Intelligence,Data Management | The Data & Analytics Program will deliver cloud technology platforms to uplift WSV's enterprise data management capabilities including a new enterprise datawarehouse data lake, advanced analytics and business analytics. | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Social Improvement (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-11-01 | 2020-04-30 |  | 2020-05-01 | 0 |  | 2020-05-01 |  | 2021-12-31 | 2022-06-30 | 1169000 | 15015621 | Green | Green | Green | Amber | Amber | Overall project is on track, however a release milestone was delayed by 6 weeks due to a resurfaced technical issue, since resolved following vendor support.
Q2 21-22 | Department of Transport | DOT | 3052 | Automatic Incident Detection (AID) Software Project | Transport and Vehicles | Development and Integration ,Systems Management,Visualisation | The objective of this project is to implement an Automated Incident Detection (AID) system. This system will use data from existing freeway systems and alert the operators and provide a view of road traffic incidents from the nearest CCTV camera. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-07-06 | 2021-02-28 | 2021-07-07 | 2021-07-30 | 0 |  | 2021-08-16 |  | 2022-06-30 | 2022-08-31 | 2100000 |  |  |  |  | Green | Green | Overall project status is green. Infrastructure set up and development work is ongoing.
Q2 21-22 | CenITex | CenITex | 3062 | Oracle as a Service – Solaris Sparc platform Refresh | Government and Economy | Assets/Materials Management | The purpose is to modernise the existing platform to remove capacity constraints, improve performance & back up recovery on to a supportable platform in the data centres | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2020-03-04 | 2020-04-22 |  | 2020-04-22 | 0 |  | 2020-05-19 |  | 2021-06-30 | 2022-06-30 | 4306662 |  | Amber | Amber | Green | Green | Green | Cenitex has established an Oracle Exadata platform and has now commenced migration of customer database workloads. The migration of workloads to the new infrastructure reduces the risk to business critical financial services.
Q2 21-22 | Department of Premier and Cabinet | DPC | 3066 | Wage Inspectorate Victoria case management system | Employment and Workplace | Management of Process ,Records Management ,Reporting | Design and build a case management system to support end-to-end regulatory operations of the Wage Inspectorate Victoria. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-05-25 | 2020-12-03 | 2021-01-11 | 2021-01-11 | 135000 |  | 2021-01-11 |  | 2022-03-31 |  | 1434372 | 1684914 |  | Green | Green | Green | Green | Phase 2 and 3 (Legal and ODFC) have been delivered together on 10 Dec. 2021 as per revised plan.
Q2 21-22 | Department of Education and Training | DET | 3070 | Student Insight Platform Establishment & Digital Enrolment Product | Education | Development and Integration ,Management of Process ,Organisational Management | The Digital Enrolment component on the Student Insight Platform will ease the school administrative burden, improve data quality and security and deliver efficiencies for managing student information for parents, schools, and staff. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2020-08-03 | 2021-06-30 | 2021-04-21 | 2021-04-21 | 2553958 | 773357 | 2021-04-21 |  | 2022-06-30 | 2022-01-31 | 15500000 | 7000000 |  |  | Green | Green | Green | The program has a budget until June 2022 and is tracking well, the program will re- submit its business case to the Department of Treasury and Finance in February 2022 to seek funding for future years.
Q2 21-22 | Department of Education and Training | DET | 3071 | Child Link Program | Education | Content Management,Data Management,Human Resources,Management of Process | The project will deliver an IT system to provide a thin layer of key information on Victorian children and families to inform professional practice and to provide authorised professionals the ability to be informed regarding children's welfare. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-07-01 | 2020-10-01 |  | 2020-10-01 | 2214000 | 2214000 | 2020-10-01 |  | 2022-06-30 |  | 35200000 | 56386000 | Amber | Amber | Green | Amber | Green | The Child Link program status is green due to the commencement of the system in production by the legislated date of 31 December 2021. The governance body assessed the technical readiness of the system and approved the initiation of Child Link as a production system in December 2021. User onboarding will commence with the agreed initial pilot service sites from Q1 2022.
Q2 21-22 | State Revenue Office | SRO | 3072 | Data Centre Relocation and Uplift | Government and Economy | Systems Management | SRO is relocating and updating our production data centre from the current Ballarat office to a third party 'co-location' site, and uplifting the second data centre in the Melbourne office to maintain parity for IT disaster recovery fallback. | Delivery | Compliance (Non Financial) |  | Waterfall | 2020-04-07 | 2020-05-19 |  | 2020-05-19 | 54791 |  | 2020-05-20 |  | 2021-06-30 | 2022-05-31 | 1666209 | 2504209 | Green | Amber | Amber | Amber | Amber | Project variation approved 10 November 2021 to re-phase the main Data Centre Relocation activities to late January 2022. This reflects additional complexity in the migration activities and a multi-step relocation program to manage operational risks.
Q2 21-22 | Yarra Valley Water | YV Water | 3076 | Land Development in Salesforce | Environment and Water | Customer Relationship Management | Replacement of the end of life land development customer portal (easyACCESS), including optimisation of the existing processes to deliver productivity savings and uplift the overall customer experience. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-08-05 | 2020-11-30 | 2021-06-30 | 2021-07-01 | 662000 | 1700000 | 2021-07-01 |  | 2026-06-30 |  | 2681995 |  |  |  |  | Green | Green | Delivery of foundational components underway.
Q2 21-22 | Yarra Valley Water | YV Water | 3078 | Yarra Valley Online Water (YVOW) Replacement | Environment and Water | Customer Relationship Management,Customer Relationship Management | Replacement of the end of life customer self service portal (YVOW), including a redesign of the customer experience. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-08-05 | 2020-11-30 | 2021-06-30 | 2021-07-01 | 330000 | 1400000 | 2021-07-01 |  | 2022-12-31 |  | 1886564 |  |  |  |  | Green | Green | Delivery of foundational components underway.
Q2 21-22 | Yarra Valley Water | YV Water | 3079 | Distribution Management System (DMS) | Environment and Water | Customer Relationship Management | Distribution Management System which provides staff with a single view of our asset networks including performance data, customer service levels, and contractor interactions. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-07-01 | 2020-09-28 |  | 2020-09-28 | 0 |  | 2020-09-28 | 2020-10-12 | 2023-06-30 | 2023-06-30 | 6002000 | 4851600 | Green | Green | Green | Green | Green | Production deployment planning in progress.
Q2 21-22 | Wannon Region Water Corporation | WAN Water | 3091 | Billing and Customer Relationship Management Systems | Environment and Water | Customer Relationship Management | The replacement of the organisation's Billing and Customer Relationship Management Systems | Initiated |  |  | PRINCE2 | 2020-01-01 | 2021-03-31 | 2022-05-31 |  | 100000 | 601000 | [11 empty] | RFT issued to the three shortlisted suppliers on 21 Dec 2021. Supplier discovery workshops will run until Apr 2022. Preferred supplier recommendation to Wannon Water Board in May 2022. Subject to Wannon Water Board approval to proceed, implementation to commence mid 2022 through to mid 2023.
Q2 21-22 | Department of Health | DH | 3094 | Digital Registration for Food Businesses - FoodTrader | Business and Industry | Data Management | Deliver a single online registration portal for Victorian food businesses and an application assessment, compliance management and reporting database for use by councils in managing registrations under the Food Act 1984. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Agile | 2019-06-28 | 2020-04-14 |  | 2020-07-06 | 184000 | 500000 | 2020-08-17 |  | 2022-06-30 |  | 2044600 | [5 empty] | Green | Procurement activities finalised. Project is progressing to cost and schedule.
Q2 21-22 | Department of Health | DH | 3095 | Windows Server Re-Platform and Re-Hosting | Health | Systems Management | The project will upgrade, re-host or decommission outdated servers and database instances to ensure continuity of infrastructure support of services. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-07-01 | 2020-07-12 |  | 2020-07-17 | 494548 |  | 2020-09-10 |  | 2021-06-30 | 2022-05-31 | 1048885 | 1355200 | Green | Amber | Amber | Green | Amber | Project progressing well however requires a scope change to enable completion. Project expected to return to Green in the next reporting period.
Q2 21-22 | Department of Transport | DOT | 3096 | Online L-Plate and Hazard Perception Testing Service | Transport and Vehicles | Customer Initiated Assistance,Management of Process | Purpose of this project is to deliver Learner Permit and Hazard Perception Tests through online digital solution as part of response to Covid-19 return to service. | Closed - Completed | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) | 2021-12-06 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-07-06 | 2021-01-18 |  | 2021-01-18 | 0 |  | 2021-01-18 |  | 2021-11-26 |  | 0 | 8314000 |  | Amber | Amber | Green | Green | Project completed.
Q2 21-22 | Department of Environment, Land, Water and Planning | DELWP | 3100 | Victorian Water Register Transform Project | Environment and Water | Management of Process | The project will deliver a new Victorian Water Register(VWR) to improve service delivery, information sharing and to ensure the equitable sharing of water and continuous improvement in the integrity security and reliability of Victoria's water market | Initiated |  |  | PRINCE2 | 2020-10-25 | 2021-06-30 | 2022-04-29 |  | 1467715 | 2938332 | [11 empty] | The initiation stage has been extended due to increased complexity required to be managed within the procurement process and the constrained availability of resources.
Q2 21-22 | HealthShare Victoria | HealthShare | 3102 | Setup HealthShare in FMIS | Health | Supply Chain Management | Establish HealthShare Victoria as a new operating unit with Oracle eBusiness and configuring Warehouse Management Solution for the new HealthShare Victoria supply chain. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-06-01 | 2020-06-30 |  | 2020-09-21 | 63313 |  | 2020-09-21 | 2020-09-21 | 2021-06-30 | 2022-03-28 | 1200000 | 5634687 | Amber | Amber | Red | Amber | Amber | Risk of dependency on system technology partner was realised during the reporting period resulting in delay to go-live. Risk of COVID impacts on availability if internal and sector resources to complete the project
Q2 21-22 | CenITex | CenITex | 3107 | Data Centre Core Network Refresh | Government and Economy | Assets/Materials Management | To remediate the biggest risk areas of the Cenitex core datacenter infrastructure through the procurement and installation of high performance and contemporary network infrastructure. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-09-28 | 2020-11-19 |  | 2020-11-19 | 0 |  | 2021-01-11 |  | 2021-09-10 | 2022-06-30 | 2119306 | 2311946 |  | Green | Green | Green | Green | 4 of 5 major upgrades have been successfully completed at the Ballarat and Burwood data centres.
Q2 21-22 | CenITex | CenITex | 3108 | DJCS – Custodial Site Switch refresh | Government and Economy | Assets/Materials Management | This project is to procure the equipment required to support five customer funded projects that will refresh DJCS custodial sites. | Delivery | Cost Reduction (Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2020-09-01 | 2020-12-03 |  | 2020-12-03 | 0 |  | 2020-12-07 |  | 2021-06-30 | 2022-06-30 | 1200000 | 1324160 |  | Green | Green | Amber | Green | Hardware has been received for 4 of 5 sites.
Q2 21-22 | Department of Premier and Cabinet | DPC | 3113 | WoVG Common Corporate Platforms - Human Capital Management Program | Government and Economy | Human Capital / Workforce Management | Implementation of a whole of government single instance cloud based HCM system (SAP SuccessFactors) to uplift and modernise the government's human resources systems and deliver consistent human resources services across the Victorian Public Service | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-08-28 | 2020-09-29 |  | 2020-09-29 | 808026 |  | 2020-09-30 |  | 2022-01-31 | 2022-05-31 | 7877290 | 14779707 | Green | Amber | Green | Green | Amber | Re-alignment of program schedule due to finalising the joint schedule across the program and the first implementing department.
Q2 21-22 | Chisholm Institute of TAFE | Chisholm TAFE | 3114 | Unified Communications & Audio-Visual Refresh (UC/AV) | Education | Collaboration | Deploy a technology solution that improves team productivity through enhanced communications & collaboration. The key components of the solution include deployment of Microsoft Teams Telephony and a refresh of AV equipment across campuses. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Waterfall/Agile | 2020-07-01 | 2020-09-01 |  | 2020-09-01 | 175000 |  | 2020-09-02 |  | 2021-06-30 | 2022-03-31 | 2023554 |  | Green | Green | Green | Amber | Amber | Project deliverables progressed. Date revision approved by Project Governance Forum.
Q2 21-22 | State Revenue Office | SRO | 3117 | Master Data Management Toolsets | Government and Economy | Data Management | This project aims to implement a data management toolset that provides the State Revenue Office with increased capabilities in data governance, data quality, data catalogue, master data management, data security and integration. | Closed - Completed | Increased Quality (Non Financial) | 2021-12-08 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-08-03 | 2020-09-07 |  | 2020-09-07 | 100000 | 35000 | 2020-12-07 |  | 2021-12-31 |  | 3380000 | 3395000 | Green | Green | Green | Green | Green | The solution was fully deployed with "business go-live" in late November 2021. Formal closure endorsed 8 December 2021.
Q2 21-22 | Department of Health | DH | 3118 | TIBCO Upgrade Implementation | Health | Development and Integration | The project will upgrade the existing TIBCO platform to a more recent supported version, thereby mitigating the risks associated with outdated software and ensuring continuity of Vendor support. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2019-06-01 | 2020-04-17 |  | 2020-11-13 | 271632 | 0 | 2021-06-21 |  | 2022-08-31 |  | 3900000 | 3400000 |  |  | Green | Green | Green | Project is progressing to schedule and cost.
Q2 21-22 | Western Health | WH | 3125 | Identity Access Management (IAM) | Health | Security Management | An IAM system is the means to provide a secure and trusted identity of employees across Western Health. This is currently housed and managed by Melbourne Health and this project will migrate the IAM from Melbourne Health to Western Health | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-10-30 | 2021-01-29 |  | 2021-04-19 | 0 |  | 2021-04-19 |  | 2022-02-28 | 2022-04-22 | 1896000 | 1165000 |  |  | Green | Amber | Amber | Status remains at Amber due to delays to complete preceding project caused by resource availability and reduced appetite for risk in impacting operations during critical Covid period.
Q2 21-22 | Melbourne Water | MELB Water | 3126 | Security access management for Contractors | Environment and Water | Data Management,Human Resources,Security Management | The security access management for contractors project will implement an identity and access management solution for the enterprise. The outcome will deliver further improved digital security and role based permissions. | Postponed |  | 2021-07-14 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-09-30 | 2021-01-28 | 2021-04-20 |  | 0 | [5 empty] | 0 | [6 empty] | Business Case not approved in it's current form. Change request raised and approved on 14th July to move the project from Year 1 to Year 3 of Water Plan 5. Recommencement of project and Business Case re-write to be scheduled for early 2023 calendar year.
Q2 21-22 | Department of Transport | DOT | 3127 | Payments Remediation Project | Transport and Vehicles | Financial Management,Systems Management | Objective of this project is to improve front-end and back-end payments usability and customer experience and resolve technical issues and reduce suspense payments and associated administrative support overheads. | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-09-01 | 2020-10-05 |  | 2020-10-05 | 0 |  | 2020-10-05 |  | 2021-06-30 | 2022-06-30 | 1500000 |  | Green | Green | Green | Green | Amber | Overall status is amber due to dependency on the oracle project team. Project team is working on bringing in a new oracle delivery team. Sprint 3 developments are ongoing.
Q2 21-22 | Department of Transport | DOT | 3128 | The Smarter Roads Program - Situational Awareness Platform (formerly-Creating More Road Space) | Transport and Vehicles | Analyses and Statistics ,Business Intelligence,Communication,Knowledge Discovery | Objective of this project is to develop a enterprise wide Situational Awareness (SA) Platform. The platform will provide a view of the metro transport network and provide situational awareness for the operators in the Traffic Management Centre (TMC). | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-10-05 | 2021-06-30 | 2021-06-14 | 2021-06-14 | 0 |  | 2021-06-21 |  | 2022-06-30 | 2022-12-31 | 0 | 35800128 |  |  | Green | Green | Green | Overall project status is green. Deployment planning, Testing, communications and change management activities are ongoing. .
Q2 21-22 | Department of Transport | DOT | 3129 | Zero Low Emission Vehicles (ZLEV) Project | Transport and Vehicles | Business Intelligence,Development and Integration ,Management of Process | Objective of this initiative is to cover technology changes and preparing options for consideration by DTF regarding funding to replace the fuel excise revenue projected to be foregone as the vehicle market increasing takes up ZLEV. | Delivery | Eco Improvement (Non Financial), Increased Revenue (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-11-02 | 2021-06-30 | 2021-01-29 | 2021-01-29 | 0 |  | 2021-01-29 |  | 2021-09-30 | 2022-03-31 | 1939460 | 2604593 |  | Amber | Amber | Green | Amber | Overall project status is Amber due to current scope/budget assessment and resource dependencies. Phase 1 completed successfully. Final stages of delivery scope for Phase 2 being examined with business stakeholders to determine achievability of March 2022 completion.
Q2 21-22 | Goulburn Valley Region Water Corporation | GVR Water | 3130 | Billing and Customer Relationship Management System | Environment and Water | Customer Relationship Management | The project will replace Goulburn Valley Water's existing legacy billing and CRM systems with a modern, efficient and customer focused system | Initiated |  |  | Internal project management methodology | 2018-10-01 | 2021-06-30 | 2022-02-28 |  | 75000 | 75000 | [11 empty] | GVW will seek Board approval to progress to market with an open RFT. The RFT will be written in such a manner that very specific details and requirements will be included and that a stringent scoring component will be incorporated to ensure that the submission numbers will be small.
Q2 21-22 | State Revenue Office | SRO | 3131 | Microsoft M365 | Government and Economy | Collaboration | This project will deliver a suite of Microsoft 365 products to enhance the capability of staff to collaborate more efficiently, both internally and with other government and third-party entities. | Closed - Completed | Efficiency/Productivity (Non Financial) | 2021-12-31 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-04-01 | 2020-08-31 |  | 2020-08-31 | 30000 |  | 2020-09-01 | 2020-10-01 | 2021-06-30 | 2021-12-31 | 1049200 | 1187120 | Green | Green | Green | Green | Green | A variation was approved 10 November to allow delivery of additional collaboration functions and to deal with complexity in the data cleanse of local documents migrated to the cloud. The project was successfully completed to the revised date of 31 December 2021 and within the revised budget.
Q2 21-22 | Department of Transport | DOT | 3132 | Creating More Road Space- Integrated View of Disruptions | Transport and Vehicles | Analyses and Statistics ,Business Intelligence,Customer Initiated Assistance,Customer Preferences,Visualisation | Objective of this project is to deliver value-add information to end users that will assist in understanding how congestion or disruptions are affecting a car journey and assist in shifting behaviors (i.e. mode of travel) to reduce congestion. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-10-19 | 2021-03-31 | 2022-03-07 |  | 0 | [12 empty] | Project requirements and options analysis activities are ongoing.
Q2 21-22 | Monash Health | Monash H | 3133 | Carestream/Philips Software Upgrade and Hardware Refresh | Health | Systems Management | Upgrade of Radiology Information System and Picture Archiving and Communication System to address risk of legacy operating system and improve system efficiency. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-09-01 | 2020-09-29 |  | 2020-09-29 | 1 | 0 | 2020-10-01 |  | 2021-12-03 | 2022-05-31 | 2570900 |  | Green | Green | Green | Green | Green | The project is tracking GREEN. User Acceptance Testing of the new Radiology Information System (RIS) environment (version 11.5) is progressing to schedule. The Picture Archiving and Communication System (PACS) data migration from the Storage Area Network (SAN) to the new Storage Area Network (SAN) is complete.
Q2 21-22 | Monash Health | Monash H | 3140 | The Victorian Heart Hospital (VHH) Electronic Medical Record (EMR) System | Health | Records Management | Implementation of EMR system for the Victorian Heart Hospital to streamline management of clinical documentation, results and patient medication to enable appropriate patient treatments | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-09-14 | 2020-11-04 |  | 2020-11-04 | 0 | 4867018 | 2021-01-04 |  | 2023-02-17 |  | 26005275 | 21138257 |  | Green | Green | Amber | Amber | The overall project is tracking Amber against the schedule as the design for Ambulatory Referral Management was not completed due to technical and vendor resource issues. Subsequently the timeline has been revised to complete the Design in readiness for System Integration Testing due to commence 7 February 2022. It is anticipated that the status will realign to green once this timeframe is reached.
Q2 21-22 | South East Water | SE Water | 3142 | Classic to Lightning Phase 2 | Environment and Water | Customer Relationship Management | Uplift the current Salesforce platform to the Lightning version for the remaining user groups | Delivery | Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Agile | 2021-01-04 | 2021-01-15 |  | 2021-01-18 | 10000 |  | 2021-01-18 |  | 2021-05-28 | 2022-04-14 | 1582303 |  |  | Green | Green | Green | Green | The architectural build is progressing well in line with the new functionality in April
Q2 21-22 | Department of Premier and Cabinet | DPC | 3143 | Single digital solution for coronavirus (COVID-19) reporting (Insights Victoria) | Government and Economy | Analyses and Statistics ,Reporting ,Visualisation | A single digital reporting platform containing whole of government coronavirus (COVID-19) data to increase the Government’s responsiveness during the coronavirus (COVID-19) pandemic. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2020-07-16 | 2020-07-24 |  | 2020-07-24 | 0 |  | 2020-07-27 |  | 2021-01-31 | 2022-06-30 | 4643000 | 15352813 | Green | Green | Green | Green | Green | Successful period of ongoing delivery of InisghtsVictoria.
Q2 21-22 | Department of Transport | DOT | 3147 | The Smarter Roads Program - Data Fusion Model | Transport and Vehicles | Analyses and Statistics ,Business Intelligence,Customer Initiated Assistance,Customer Preferences | Objective of this project is to provide: 1.Multi-modal journey planning that encompasses tools to help them re-plan and understand alternative journey options in real time. 2. Real-time disruption information to customers to plan their journey. | Delivery | Efficiency/Productivity (Non Financial), Social Improvement (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-11-02 | 2021-06-30 |  | 2021-06-30 | 0 |  | 2021-08-02 |  | 2022-06-30 |  | 0 | 12103458 |  |  |  | Green | Green | Overall project status is green. Development and infrastructure setup work is ongoing.
Q2 21-22 | Goulburn Ovens Institute of TAFE | GO TAFE | 3148 | Network Infrastructure upgrade | Education | Systems Management | Network infrastructure upgrade includes replacement of all IT network switches across all campuses, to enable a future state of network infrastructure with improved productivity and security. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial) |  | PMBoK | 2020-08-17 | 2020-10-29 |  | 2020-12-11 | 55000 |  | 2020-12-11 |  | 2021-10-29 | 2022-03-04 | 1350000 |  | Green | Green | Green | Green | Green | The project is progressing well. The installation and configuration of the core hardware are complete and is operational. There is a minor delay due to covid-19 restrictions and it does not impact the overall project cost or business activities.
Q2 21-22 | Kardinia Park Stadium Trust | KPST | 3151 | Connected Stadium - Digital Smart Stadium | Culture, Sport and Recreation | Communication | The project considers both an outward-facing element that addresses the customer and client experiences, and an inward-facing element that will bring the individual stands together and operate via a converged network. | Delivery | Customer Satisfaction (Non Financial) |  | Gantt charts | 2020-10-01 | 2020-12-01 |  | 2020-12-01 | 98000 |  | 2020-12-16 |  | 2022-06-30 |  | 4418000 |  | Green | Green | Green | Green | Green | Project tracking well
Q2 21-22 | Department of Health | DH | 3154 | Digital Visitation Register (DVR) Project | Health | Data Management | Provides free QR Code Service for businesses, workplaces & commercial passenger vehicles to record & share attendance records for contact tracing. Allows contact tracers to notify close contacts of positive cases to test & isolate. | Delivery | Increased Quality (Non Financial), Reputation (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2020-09-09 | 2020-10-06 |  | 2020-10-06 | 0 |  | 2020-10-07 |  | 2023-06-30 |  | 8577000 | 9459238 | Amber | Amber | Green | Green | Green | Victorian government QR Code Service is operational and being used widely by the Victorian Public. The project is progressing to schedule and cost, delivering further enhancements in response to the changing needs of managing the COVID-19 Pandemic.
Q2 21-22 | Alfred Health | ALFRED | 3156 | ARIA Database Merge and Managed Service Implementation | Health | Records Management | Database merge and consolidation of Alfred Health Radiation Oncology Application “ARIA” to a single instance, cloud-based, vendor-managed and hosted service | Delivery | Cost Avoidance (Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2021-03-01 | 2021-06-30 |  | 2021-06-30 | 0 | 235544 | 2021-07-01 |  | 2022-12-20 |  | 1708056 |  |  |  |  | Green | Green | Project is ON TRACK.
Q2 21-22 | Melbourne Health | Melb H | 3159 | Unified Communications – Telephony Upgrade Project | Health | Collaboration ,Communication,Systems Management | This project will upgrade the Melbourne Health telephony system to replace the old existing ISDN / PSTN / analogue PABX and phone infrastructure with digital SIP trunks and VoIP phones that provide unified communication and enhanced collaboration. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2021-02-01 | 2021-06-30 |  | 2021-06-30 | 0 | 50000 | 2021-07-01 |  | 2022-06-30 |  | 4326000 |  |  |  |  | Green | Green | Progressing to schedule and managing impacts relating to site access and equipment deliveries imposed by COVID pandemic.
Q2 21-22 | Melbourne Health | Melb H | 3160 | Office 365 Implementation Project | Health | Collaboration ,Content Management,Systems Management | Extensive technical and change management project to implement the required foundation, application and governance layers for Melbourne Health to deploy and adopt the full collaboration potential of the Microsoft Office 365 suite. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2021-01-04 | 2021-06-30 |  | 2021-06-30 | 0 | 50000 | 2021-07-01 |  | 2022-06-30 | 2022-09-30 | 3532700 |  |  |  |  | Green | Green | COVID Pandemic significantly impacting original project schedule. Technical preparation will continue while the roll-out to the organisation will be deferred by 3 months to reduce the level of change imposed upon the organisation at a time when the major focus is upon delivering optimal health care during a challenging time.
Q2 21-22 | Department of Premier and Cabinet | DPC | 3165 | Emergency Management Victoria-VCDI Partnership | Emergencies and Safety | Data Management,Reporting ,Visualisation ,Analyses and Statistics ,Business Intelligence | The primary objective of this partnership is to rapidly and practically enhance EMV (including the State Control Centre) and the emergency management sector’s data and analytics capability in order to help it respond to major and complex emergencies | Delivery | Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2021-01-11 | 2021-01-22 |  | 2021-01-22 | 0 |  | 2021-01-25 |  | 2022-06-30 |  | 2300000 |  |  | Green | Green | Green | Green | Successful period of working together and product delivery to give EMV enhanced insights into emergency risk locations and where it can target its efforts.
Q2 21-22 | Department of Health | DH | 3166 | COVID19 Vaccination Management System (CVMS) | Health | Systems Management | To provision a central departmental solution for registering, recording and reporting of COVID-19 vaccinations for Victorians. | Closed - Completed | Compliance (Non Financial), Reputation (Non Financial), Risk Reduction (Non Financial) | 2021-12-31 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-09-01 | 2020-12-31 |  | 2020-12-31 | 0 |  | 2021-01-01 |  | 2021-06-30 | 2021-12-31 | 11828000 | 14200000 |  | Red | Amber | Green | Green | Project successfully completed deployment of final Release 3 of CVMS. Project is now closed.
Q2 21-22 | Emergency Services Telecommunications Authority | ESTA | 3167 | Capability & Performance Project | Emergencies and Safety | Human Capital / Workforce Management | The Capability & Performance project is implementing SAP SuccessFactors (Core HR recruitment onboarding performance and goals modules) to provide ESTA with better workforce insights and improve talent and performance oversight | Delivery | Cost Avoidance (Financial) |  | Project Management Excellence | 2020-07-28 | 2020-12-04 |  | 2020-12-04 | 246940 |  | 2020-12-05 |  | 2021-08-30 | 2022-06-30 | 1537583 | 3075778 |  | Amber | Amber | Red | Red | Current critical operational pressures have resulted in project delays.
Q2 21-22 | Department of Justice and Community Safety | DJCS | 3168 | Post Sentence Authority Case Management System | Law and Justice | Tracking and Workflow | This project will deliver a fit-for-purpose case management system for the Post Sentencing Authority. | Initiated |  |  | Agile | 2021-03-30 | 2021-07-15 | 2022-02-28 |  | 150000 | 200000 | [11 empty] | Project was delayed pending the start of a new Project Manager in February 2022. However, resources are now in place and the project is expected to proceed with only minor delays.
Q2 21-22 | Department of Justice and Community Safety | DJCS | 3169 | High Risk Industries Engagement and Enforcement Project | Law and Justice | Tracking and Workflow | This project will deliver a new case management system for managing cases events and incidents for COVID-19 high risk industries. | Delivery | Compliance (Non Financial) |  | Project Management Excellence | 2021-02-01 | 2021-03-01 |  | 2021-03-01 | 550000 |  | 2021-03-02 |  | 2021-11-30 | 2022-06-30 | 7000000 | 14667722 |  | Green | Green | Amber | Amber | The original scope was for 3 phases for completion by 30 November 2021. In November 2021 an extension was approved to 4 phases with an end date of 30 June 2022. The additional phase will continue building functionality to the case management solution (including enforcement activities) prior to the transition of the platform to operation. Further work concerning data and analytics will also be undertaken which will result in further government data being available in the data lake. Amber status reflects the need to reprioritise Phase 4 work as a result the available funding envelope.
Q2 21-22 | Department of Justice and Community Safety | DJCS | 3170 | Technology and resources to support Victoria’s fines system | Law and Justice | Systems Management | Delivery of next generation of fines platform by incrementally implementing functions into the business landscape to complement existing technology, ensuring better revenue collection, assistance for vulnerable Victorians and debtor-centric services. | Initiated |  |  | Hybrid - Waterfall and Agile | 2021-03-10 | 2021-08-30 | 2021-12-30 |  | 0 | [12 empty] | The NextGen Program is tracking well against scope, budget and schedule. Within the last reporting period, program activities have concentrated on finalising the Technology RFT and selection / onboarding of preferred delivery partners to design, plan and lay the foundations in readiness for incremental delivery of the Fines solution. The NextGen Program also engaged external delivery assurance partners to undertake an independent and ‘real time’ assessment of the Program Delivery Model and effectiveness of the Co-Design phase in laying the foundations for successful program delivery. Findings have been presented to the Steering Committee and the program has been approved to formally progress to the Delivery Phase in January 2022.
Q2 21-22 | Department of Justice and Community Safety | DJCS | 3171 | Better Technology Tools Enabling Responsibility (BTTER) | Law and Justice | Development and Integration | Deliver applications to automate processes, reduce costs and risks associated with existing manual systems to deliver safety and cost benefits. The project will provide access to rehabilitation and reintegration services through in-cell technology. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Project Management Excellence | 2020-07-21 | 2021-02-19 |  | 2021-02-19 | 324114 |  | 2021-02-22 |  | 2023-06-30 |  | 18868800 |  |  | Green | Amber | Amber | Amber | Delivery of minimum viable product for operations is on track. Resourcing issue for automation stream to be resolved with project to be re-baselined and first sprint to commence January 2022.
Q2 21-22 | Department of Justice and Community Safety | DJCS | 3172 | JKE Upgrade & Linux Migration | Law and Justice | Development and Integration | This project is to transition the Justice Knowledge Exchange (JKE) Enterprise Service Bus from Solaris to Linux platforms and upgrades it to webMethods version 10. | Delivery | Compliance (Non Financial) |  | Project Management Excellence | 2020-07-01 | 2020-08-31 |  | 2020-08-31 | 26466 |  | 2020-09-01 |  | 2022-02-28 | 2022-05-31 | 1664286 | 1603403 |  | Amber | Amber | Green | Red | Delays in the availability of specialist resources and application environment for interface partners is causing delays to the JKE Upgrade project. Interface upgrades continue where Integration partners are available and the technology has been set up.
Q2 21-22 | Department of Health | DH | 3173 | Identity and Access Management Implementation | Employment and Workplace | Systems Management | Implementation of a cloud based Identity Access Management system to provide a centralised governance capability to manage external business partner access to department systems and information. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-06-01 | 2020-11-13 |  | 2020-11-13 | 0 |  | 2021-01-21 |  | 2022-06-30 |  | 3126591 |  |  |  | Green | Green | Green | Project is progressing to schedule and cost.
Q2 21-22 | Central Highlands Region Water Corporation | CHR Water | 3174 | SCADA Field Hardware Replacement Program -SCADA Radio Network Asset Replacement Program | Environment and Water | Communication,Business Intelligence,Data Management,Security Management | Replacement of end of asset life hardware used to Monitor and Control Critical Infrastructure Assets | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Internal Framework | 2018-07-01 | 2019-05-17 |  | 2019-05-17 | 0 |  | 2019-07-01 |  | 2023-06-30 |  | 2600000 |  |  | Green | Green | Green | Green | On Track
Q2 21-22 | South East Water | SE Water | 3175 | Asset Register Phase 3 | Environment and Water | Assets/Materials Management,Data Management | The third and final stage of the Asset Register will build capability to allow network, facility and building assets to be part of the asset register | Delivery | Increased Quality (Non Financial) |  | Waterfall | 2021-01-11 | 2021-01-21 |  | 2021-01-21 | 75000 |  | 2021-01-25 |  | 2021-12-31 | 2022-02-05 | 2250000 |  |  | Green | Green | Green | Green | Due to resource impacts and limitations the go live was postponed until February 2022.
Q2 21-22 | Melbourne Water | MELB Water | 3177 | Core Services: Storage Hardware Refresh | Environment and Water | Systems Management | Current storage hardware is approaching end of financial lifecycle support and therefore needs to be upgraded. This project sets out to upgrade the storage hardware for the next 5 year lifecycle. | Closed - Completed | Cost Reduction (Financial), Risk Reduction (Non Financial) | 2021-10-13 | PMBoK | 2020-11-04 | 2021-04-02 |  | 2021-05-24 | 0 |  | 2021-06-24 |  | 2021-08-10 | 2021-11-26 | 1061453 | 1096224 |  |  | Amber | Amber | Green | Project is Closed
Q2 21-22 | Melbourne Water | MELB Water | 3179 | Incident and Risk System upgrade and migration to cloud | Environment and Water | Reporting | This project will enable the continuing growth in use of Melbourne Waters Incident and Risk system by the business for reporting events completing assessments/checklists and raising completed actions via a mobile app. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-12-01 | 2021-04-30 |  | 2021-05-24 | 0 |  | 2021-06-24 |  | 2022-05-04 |  | 1067418 | 1137031 |  |  | Green | Green | Green | Vendor has completed the configuration and build as per requirements. User Management Integration build & test has been completed. Sample test cases have been created in preparation for the kick-off meeting on 17 January 2022. Training plan has been prepared and comms have been sent. Amber schedule is due to additional delays over the holiday period working through if this can be recovered.
Q2 21-22 | Melbourne Water | MELB Water | 3180 | Digital Education and Engagement Services | Environment and Water | Communication | Melbourne Water has a Water Act obligation through the Statement of Obligations to educate schools about Water Literacy and our range of services. This 3 year program will focus on encouraging water literacy across the school community. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-02-25 | 2021-07-01 | 2021-12-02 | 2021-12-20 | 0 |  | 2021-12-20 |  | 2024-05-30 |  | 1804843 | [5 empty] | Green | Business Case is approved and project execution is underway commencing with workshops.
Q2 21-22 | Department of Jobs, Precincts and Regions | DJPR | 3181 | Jobs Victoria Digital Services build | Employment and Workplace | Customer Initiated Assistance,Customer Relationship Management,Tracking and Workflow | This project will deliver the digital services to support connecting jobseekers and employers smarter, faster and effectively through a tailored and integrated digital platform. | Delivery | Efficiency/Productivity (Non Financial), Social Improvement (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-11-16 | 2021-05-16 |  | 2021-05-17 | 1000000 |  | 2021-05-17 |  | 2022-06-30 |  | 1000000 | 8301618 |  |  | Green | Amber | Amber | Program release plan is on-track, deploying solution deliverables and achieving program objectives. An iterative deployment approach is enabling delivery of business benefits incrementally as each business process is transitioned to the new system.
Q2 21-22 | Department of Health | DH | 3182 | Syndromic Surveillance (SynSurv) | Health | Business Intelligence | The primary purpose of the SynSurv platform is to provide advanced warning of new and emerging health threats to epidemiologists, emergency management staff, and public health decision makers in the department. | Delivery | Increased Quality (Non Financial), Risk Reduction (Non Financial), Social Improvement (Non Financial) |  | PRINCE2 | 2020-07-01 | 2020-09-30 |  | 2020-09-30 | 0 |  | 2020-10-01 |  | 2022-06-30 |  | 3000000 |  |  | Green | Green | Green | Green | Project is progressing to schedule and cost.
Q2 21-22 | Department of Families, Fairness and Housing | DFFH | 3184 | Rent Reform Changes | Community Services | Data Management | The project will implement maximum flexibility in how the Housing Integrated Information Program manages rent so that Homes Victoria can have a timely and sustainable implementation of new rent policy settings. | Closed - Completed | Efficiency/Productivity (Non Financial), Increased Revenue (Financial), Social Improvement (Non Financial) | 2021-10-31 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-08-05 | 2021-03-18 |  | 2021-03-19 | 0 |  | 2021-03-19 |  | 2021-08-07 | 2021-10-31 | 1160500 | 1662000 |  | Amber | Red | Amber | Green | Project has successfully delivered and closeout activities are underway.
Q2 21-22 | Department of Health | DH | 3188 | Remote Working Capability: Process Digitisation - Software Development | Employment and Workplace | Systems Management | The project will digitise a range of processes including streamlining the digital mailroom and the process for sharing sensitive data between external partners and the department, to better support remote and hybrid working. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Agile | 2020-07-01 | 2020-08-13 |  | 2020-08-14 | 0 |  | 2020-08-14 |  | 2022-06-30 |  | 2886480 | 2946480 |  | Green | Green | Green | Green | Project is progressing to schedule and cost.
Q2 21-22 | CenITex | CenITex | 3190 | Establishment of Cenitex DRaaS | Government and Economy | Assets/Materials Management | To provide a scalable elastic modern platform to allow for customer backup and data retention capacity needs improve backup and recovery on to a robust supportable hybrid cloud platform. | Closed - Completed | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) | 2021-12-31 | PRINCE2 | 2021-01-18 | 2021-02-02 |  | 2021-02-02 | 0 |  | 2021-03-01 |  | 2021-10-30 | 2021-11-30 | 1542741 |  |  |  | Green | Green | Green | 'The scope of the project has been delivered and is in the administrative closure phase
Q2 21-22 | Department of Premier and Cabinet | DPC | 3191 | Email Fraud Defence (DMARC) | Government and Economy | Security Management | Implementing DMARC (Domain-based Message Authentication, Reporting and Conformance) will make it significantly harder to send fake emails claiming to be from the Victorian government & will help prevent fraud to the Victorian government & citizens. | Delivery | Cost Reduction (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-10-26 | 2021-05-31 |  | 2021-06-04 | 170672 |  | 2021-06-04 |  | 2023-12-29 |  | 5829328 |  |  |  | Green | Green | Green | Project tracking well to the approved schedule and budget.
Q2 21-22 | Yarra Valley Water | YV Water | 3192 | Firewall Upgrade | Environment and Water | Security Management | End of life Firewalls to be upgraded as they are our first line of defence against Cyber Security attacks | Delivery | Compliance (Non Financial) |  | Waterfall | 2021-03-15 | 2021-12-31 | 2021-03-31 | 2021-04-01 | 130000 |  | 2021-04-01 |  | 2021-12-31 | 2022-03-31 | 1008000 | 1105020 |  |  | Green | Green | Green | Firewalls completed and tested. Remote Access implemented and currently being tested. Delivery end date extended to complete remote access and close the project.
Q2 21-22 | Melbourne Convention and Exhibition Centre | MCEC | 3194 | MCEC Core Systems Uplift | Business and Industry | Financial Management,Tracking and Workflow | The CSU project will provide uplifted Finance and Event & Venue Management systems. It will utilise improved technology in the form of cloud infrastructure and software to fit our future state roadmap. | Delivery | Efficiency/Productivity (Non Financial) |  | Agile | 2020-01-13 | 2020-12-18 |  | 2020-12-18 | 150000 | 221600 | 2021-01-15 |  | 2022-04-30 | 2022-06-30 | 1334184 | 1943783 |  | Green | Amber | Amber | Green | Project Phase 2 went live with software upgrade. Phase 2a technical remediation planning completed.
Q2 21-22 | Department of Justice and Community Safety | DJCS | 3199 | Registry System Replacement - RTBA | Community Services | Customer Relationship Management | This project will deliver an enhanced, updated solution to the Residential Tenancies Bond Authority legacy systems which are reaching end of life. The solution will ensure alignment to the business vision. | Initiated |  |  | Hybrid - Waterfall and Agile | 2021-04-12 | 2021-12-31 | 2022-04-22 |  | 900000 | [12 empty] | Project commenced on 12 April 2021 (note this project picks up the now terminated Registry System Replacement (2833) project). Requirements and process maps are under finalisation. Procurement of implementation vendor underway. Schedule baselined and on track in line with procurement requirements of implementation vendor.
Q2 21-22 | Department of Premier and Cabinet | DPC | 3200 | Local Jobs First Policy Intelligence Engine | Business and Industry | Analyses and Statistics ,Business Intelligence,Data Management | DJPR have partnered with DPC to develop a policy intelligence engine to improve the effectiveness of the Local Jobs First policy. The technology solution will support an uplift in capability to improve the delivery of important policy. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Agile | 2020-12-01 | 2021-02-11 |  | 2021-02-11 | 0 |  | 2021-05-01 |  | 2023-06-30 |  | 2400000 |  |  |  | Green | Green | Green | Project initiation and planning activities has resulted in a clear roadmap that the delivery team is working towards in alignment with the business owners.
Q2 21-22 | Department of Transport | DOT | 3201 | Dynamics 365 - Permits Customer Portal | Transport and Vehicles | Customer Initiated Assistance,Development and Integration ,Management of Process | Objective of this project is to develop minimum viable product for Permits Customer Portal. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-06-01 | 2021-06-30 |  | 2021-06-30 | 0 |  | 2021-07-01 |  | 2022-06-30 |  | 3200000 | 3300000 |  |  |  | Amber | Amber | Project status is amber due to dependency on alignment with corporate mapping system updates. Development for Permits Customer Portal for Pilot release is progressing well
Q2 21-22 | Department of Transport | DOT | 3202 | Learners 2 Probationary Mentorship System Procurement (L2P) | Transport and Vehicles | Customer Initiated Assistance,Development and Integration ,Management of Process | Objective of this project is to build a new mentor-ship system to assist learner drivers attain learner hours to be eligible for securing probationary licence. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-04-05 | 2021-07-30 |  | 2021-07-30 | 0 |  | 2021-08-02 |  | 2022-02-19 | 2022-05-06 | 1543840 | 1699128 |  |  |  | Amber | Green | Overall project status is green. Release 2 development is progressing as per plan. KPI calculations (for reporting) analysis & design is in progress.
Q2 21-22 | Department of Education and Training | DET | 3203 | Infrastructure Portfolio Management (IPM) | Education | Investment Management,Management of Process | This project will procure and implement a new SaaS portfolio management system to facilitate effective and efficient infrastructure planning and delivery and improve organisational capability through coordination and delivery of business functions. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-04-22 | 2021-10-31 | 2021-11-30 | 2021-12-01 | 111310 |  | 2021-12-01 |  | 2022-12-31 |  | 6738690 | [5 empty] | Green | The project is tracking well against scope, budget and schedule. The project name has been changed to Infrastructure Portfolio Management (IPM) since the last reporting period. The procurement activity has been completed following execution of contracts for the provision of SaaS and Professional services and issue of purchase requisitions to the supplier. Project has successfully progressed from Plan phase to Design stage of the Deliver phase.
Q2 21-22 | Department of Education and Training | DET | 3205 | ARC Release 1.3 | Education | Content Management,Knowledge Management | ARC will create a comprehensive solution that centralises and integrates the range of high-quality digital services and resources offered by the Department of Education and Training to support learning and teaching in Victorian schools. | Delivery | Customer Satisfaction (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-01-18 | 2021-04-30 |  | 2021-04-30 | 28782 |  | 2021-05-03 |  | 2022-02-07 |  | 1352229 | 1321061 |  |  | Green | Green | Green | The project delivered a release of new features in December. The next release is on track for January 2022.
Q2 21-22 | Department of Education and Training | DET | 3207 | VISIT 2-0 | Education | Knowledge Management ,Management of Process | This project will provide additional functionality to the first release of the Victorian International Student Information Tool (VISIT) to enable DET and Government school staff to support the International Student Program processes more efficiently. | Delivery | Compliance (Non Financial), Cost Reduction (Financial) |  | Agile | 2021-04-15 | 2021-08-27 | 2021-10-01 | 2021-10-01 | 65000 |  | 2021-10-01 |  | 2022-06-30 |  | 1500000 | [5 empty] | Green | The Project Governance Group has approved a change in scope and the recruitment of two additional developers. Twelve sprints are planned to deliver the agreed project scope. Six sprints have been completed to date.
Q2 21-22 | Department of Education and Training | DET | 3208 | eduSafe Plus – Phase 2 | Education | Human Capital / Workforce Management | The project will deliver the functionality for managing incidents, OHS and workers’ compensation using a platform-based approach. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-04-29 | 2021-06-11 |  | 2021-06-11 | 1 | 0 | 2021-06-14 |  | 2022-06-30 |  | 3192672 | 3192673 |  |  | Green | Green | Green | The Incident and Hazard Management Pilot was released to a representative group of schools on 8 November 2021 and concluded on 29 November 2021. Data migration activities are underway. Occupational Health and Safety (OHS) Audit build is complete. The remaining OHS build is underway.
Q2 21-22 | Department of Families, Fairness and Housing | DFFH | 3209 | Homes Victoria and MOG Changes | Property and Planning | Organisational Management | Housing Division has undergone an organisational restructure and is now known as Homes Victoria. This project will deliver updates to affected ICT housing systems, letters and documentation to align with the new structure. | Delivery | Compliance (Non Financial), Reputation (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-01-29 | 2021-02-12 |  | 2021-02-12 | 170000 |  | 2021-02-23 |  | 2021-11-28 | 2022-04-29 | 1872000 | 1702000 |  |  | Green | Amber | Amber | Project is progressing but has had schedule delays related to additional scope. Schedule and cost are currently being assessed and will be rebaselined in the next reporting quarter.
Q2 21-22 | Department of Health | DH | 3210 | Centre for Victorian Data Linkage (CVDL) Infrastructure Redevelopment | Health | Reporting | This project will replatform the existing CVDL infrastructure to cloud with increased processing power and improved design for data linkage integration and advanced analytics. | Closed - Completed | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) | 2021-11-26 | Agile | 2020-12-01 | 2021-03-10 |  | 2021-03-10 | 0 |  | 2021-03-15 |  | 2021-11-30 | 2021-11-26 | 2480606 | 1947090 |  |  | Green | Green | Green | Project successfully delivered and is now closed.
Q2 21-22 | Department of Health | DH | 3211 | Our Briefings Phase 3 | Government and Economy | Document Management | Extend the existing integrated document tracking solution, currently used for departmental Ministerial briefings and executive correspondence, to support Cabinet and Parliamentary processes to facilitate timely and efficient communications. | Closed - Completed | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2021-12-31 | Agile | 2020-06-04 | 2020-07-04 |  | 2020-07-04 | 0 |  | 2021-04-16 |  | 2021-12-31 |  | 2035000 | 2035000 |  |  | Green | Green | Green | Project has successfully delivered and closeout activities are underway.
Q2 21-22 | CenITex | CenITex | 3212 | DC Exit, Discovery, Re-Architecture and Migration - Stage 1 | Government and Economy | Data Management | To delivery data centre discovery for all Government Shared Platform clients. In addition to the discovery also design a new landing platform and plan for migration of the services. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2021-03-29 | 2021-04-20 |  | 2021-05-06 | 0 |  | 2021-06-10 |  | 2022-06-30 |  | 5600000 |  |  |  | Green | Green | Green | Discovery phase is complete. The design phase is in progress.
Q2 21-22 | CenITex | CenITex | 3213 | Hybrid Cloud, Mediation Layer - Stage 1 | Government and Economy | Data Management | Proposal No.1 will cover the uplift of the existing Software Defined Datacentre and VMware for all Government Shared Platform(GSP) clients. Develop service vision for a new Hybrid Cloud hosting solution. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Reputation (Non Financial) |  | PRINCE2 | 2021-03-29 | 2021-05-25 |  | 2021-06-11 | 0 |  | 2021-06-22 |  | 2022-06-30 |  | 3650000 |  |  |  | Green | Green | Green | The Software Defined Data Centre (SDDC) uplift to the new VMware cloud foundation (VCF) platform was implemented
Q2 21-22 | Melbourne Water | MELB Water | 3214 | Strategic Relationship Management Tool Phase 1-2 | Environment and Water | Collaboration | To enhance delivery of business goals by improvement in business capabilities and relationship management tools to allow ongoing management and continuity of relationships to achieve strategic improvements in organisational goals. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2020-11-25 | 2021-08-01 |  | 2021-11-04 | 0 |  | 2021-11-04 |  | 2022-06-28 |  | 3174023 | [5 empty] | Green | Sprint 3 Build has been completed and showcased. Sprint 4 was put on hold due to user requirements for marketing lists and many to many functionality was not currently solutioned. The 'way forward' has been agreed by both MW and Vendor and requirement writing and review will commence in the new year. With an expected delay of approximately 1-2 working weeks delay to Sprint 4.
Q2 21-22 | Department of Families, Fairness and Housing | DFFH | 3215 | The Integrated Client and Case Management System (ICCMS) Infrastructure Refresh and Software Upgrade | Community Services | Customer Relationship Management,Systems Management | The project will deliver a refreshed hardware/hosting and software solution to the department's primary client and case management business system to ensure a stable, responsive and reliable platform. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2020-10-01 | 2020-11-13 |  | 2020-11-16 | 0 |  | 2021-02-01 |  | 2022-12-31 | 2023-06-30 | 4350000 | 6000000 |  |  | Green | Green | Amber | Project is progressing to schedule which has been extended six months due to revised delivery approach. Project is reporting an Amber health status pending approval of rephasing of funding to align with revised schedule.
Q2 21-22 | Department of Jobs, Precincts and Regions | DJPR | 3220 | Fair Jobs Code IT System | Employment and Workplace | Customer Initiated Assistance,Customer Relationship Management,Tracking and Workflow | Delivery of digital services to businesses and suppliers to apply for Fair Jobs Code certificates. It will also provide a public registry for government agencies to confirm the certification status of the suppliers. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-03-09 | 2021-12-31 | 2021-03-23 | 2021-03-23 | 500000 |  | 2021-03-24 |  | 2021-12-31 | 2022-02-28 | 1753225 | 1965808 |  |  |  | Green | Green | System delivery via Agile methodology reaching 70% completion. System delivery and transitions to operations forecast to be completed by 31 Dec 21.
Q2 21-22 | Victorian Managed Insurance Authority | VMIA | 3223 | Client360 Release 5 | Government and Economy | Tracking and Workflow | Client360 Release 5 will focus on completing the remaining items to clear the pathway for decommissioning our legacy system Risk Console and migrate the rest of VMIA’s clients into the Client360 platform | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-04-29 | 2021-07-30 | 2021-07-30 | 2021-07-30 | 0 |  | 2021-08-02 |  | 2021-11-26 | 2022-02-28 | 3660320 |  |  |  |  | Amber | Amber | The project's amber status reflects schedule delays and replanning due to resourcing issues.
Q2 21-22 | South East Water | SE Water | 3225 | Sharepoint Online Migration | Environment and Water | Collaboration ,Content Management,Document Management ,Knowledge Management | Migrate all 2013 sharepoint sites and business content to the sharepoint online platform | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Waterfall | 2021-04-07 | 2021-04-30 |  | 2021-05-06 | 10000 |  | 2021-05-14 |  | 2021-12-10 | 2022-02-25 | 1184488 |  |  |  | Green | Amber | Green | The impacts of the technical issues have been overcome and the delivery schedule is progressing smoothly.
Q2 21-22 | Victorian Managed Insurance Authority | VMIA | 3227 | Strategic Data Infrastructure Implementation Phase 3 | Government and Economy | Tracking and Workflow | Phase 3 focus on building advanced analytics and insights use-cases, supporting Client360 project with Data Migration, Decommissioning and Coexsistence reporting outcomes. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-02-22 | 2021-04-13 |  | 2021-04-13 | 1451000 | 0 | 2021-04-19 |  | 2021-11-26 | 2022-02-28 | 1608500 |  |  |  | Green | Amber | Amber | Amber due to higher data complexity observed from the new Insurance system being implemented impacting effort and velocity, hampered by ongoing resourcing constraints. Change Request to Business Case schedule and scope approved. Data mitigation stream successfully completed for Release 5 of Client360.
Q2 21-22 | Department of Environment, Land, Water and Planning | DELWP | 3234 | Digital Twin Victoria Program (DTV Program) | Property and Planning | Data Management,Knowledge Management | The DTV Program will recreate Victoria online so that government, industry and the community can collaborate to enhance real-world outcomes through shared data and technology leveraging spatial data, artificial intelligence, sensor data and more. | Delivery | Cost Reduction (Financial), Eco Improvement (Non Financial), Increased Revenue (Financial), Social Improvement (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-06-01 | 2020-07-28 |  | 2020-11-15 | 0 |  | 2021-01-01 |  | 2024-06-30 |  | 37431600 |  |  |  |  | Amber | Green | The Program reported Green status. All workstreams are on track.
Q2 21-22 | Department of Environment, Land, Water and Planning | DELWP | 3238 | Digital Planning Reform Program | Property and Planning | Data Management,Management of Process ,Reporting ,Tracking and Workflow,Visualisation | Digital Reform program will deliver a portal for Victoria with easy access to guidance information and services to reduce complexity and to provide greater consistency and certainty to users. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-07-01 | 2020-11-01 |  | 2020-11-01 | 0 |  | 2021-03-29 |  | 2024-06-30 |  | 15755000 |  |  |  |  | Green | Amber | The Program is progressing but is delayed due to sourcing appropriately skilled personnel. A services panel is being implemented which is expected to return the Program to Green status. The planned end date is not impacted at this stage.
Q2 21-22 | Department of Justice and Community Safety | DJCS | 3239 | E*Justice Upgrade | Law and Justice | Systems Management | The ​Upgrade of the E*Justice platform will refresh outdated software versions and databases to the latest versions. This will allow better maintenance and support for future initiatives. | Delivery | Compliance (Non Financial) |  | Project Management Excellence | 2021-02-26 | 2021-04-07 |  | 2021-04-07 | 0 |  | 2021-05-14 |  | 2022-04-01 |  | 1431900 |  |  |  |  | Amber | Amber | Overall status of the project is Amber due to the Risks involved in the roll out of the upgraded software across multiple areas of user impact. All the impacted user groups have been engaged and briefed of the changes. An agreement of the roll-out plan and timeframe with all impacted user groups and technology partners will bring the project back to Green.
Q2 21-22 | Victorian Institute of Forensic Medicine | VIFM | 3241 | Replace Case Management System | Law and Justice | Customer Relationship Management | Case Management System (CRM) will be replaced to meet current business operations and reporting requirements and drive best practice in forensic investigations. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-07-01 | 2022-06-30 |  |  | 0 | 350000 | [11 empty] | Collection of functional and non-functional requirements is underway following a series of workshops.
Q2 21-22 | Victorian Institute of Forensic Medicine | VIFM | 3242 | ICT Infrastructure Migration to the Cloud | Law and Justice | Systems Management | ICT Infrastructure Cloud Migration project will reduce the risk associated with aging ICT infrastructure | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-07-01 | 2022-06-30 | 2022-02-28 |  | 0 | 585000 | [11 empty] | Technical requirements gathering is underway.
Q2 21-22 | Office of Public Prosecutions | OPP | 3243 | Digital Innovation Project Prosecution Case Management | Law and Justice | Tracking and Workflow | Project to upgrade case management system and integrate with other core systems | Initiated |  |  | Agile | 2021-07-01 | 2021-12-31 | 2022-06-30 |  | 300000 | [12 empty] | Project initiated and selective Request for Proposal (RFP) has been put to market. RFP responses from shortlisted vendors are currently being assessed as of Jan 2022.
Q2 21-22 | Department of Education and Training | DET | 3245 | Disability Inclusion Profile Facilitator | Education | Management of Process | The project will develop an IT system infrastructure that will facilitate the administration of the Disability Inclusion Profile in Victorian government schools from late 2021 to 2024 to support the Disability Inclusion Reform. | Initiated |  |  | Agile | 2021-07-15 | 2022-01-31 |  |  | 0 | [12 empty] | The project is on track with the development of initial business processes and system requirements to support Disability Inclusion Profile activity.
Q2 21-22 | Department of Education and Training | DET | 3246 | Workplace Management System | Education | Human Capital / Workforce Management | This project will explore the procurement and implementation of a new cloud-based service technology platform to facilitate real-time desk booking, space utilisation, workforce planning, and reporting across all department-owned and leased sites | Initiated |  |  | Agile | 2021-07-06 | 2022-04-30 |  |  | 0 | [12 empty] | The project has been initiated; the requirements have been defined, currently in the procurement phase.
Q2 21-22 | Department of Justice and Community Safety | DJCS | 3248 | VicEmergency Uplift | Emergencies and Safety | Communication | The VicEmergency website & mobile app require upgrades and new apps to ensure alignment with key IGEM and Royal Commission recommendations. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-11-13 | 2021-01-02 |  | 2021-03-02 | 700000 | 267000 | 2021-07-01 |  | 2022-06-30 |  | 2500000 |  |  |  |  | Green | Green | The project is tracking well against scope, budget and schedule.
Q2 21-22 | WorkSafe Victoria | WorkSafe | 3249 | Claims and Recovery Strategy - Recovery Service Model Development (RSMD) | Government and Economy | Financial Management | RSMD will develop a future service model with clear target state design and business architecture that provides definition of business benefits and builds foundation technology to enable the implementation of improved recovery and RTW services. | Delivery | Risk Reduction (Non Financial) |  | PMBoK | 2021-07-01 | 2021-10-25 |  | 2021-10-26 | 1172730 |  | 2021-10-27 |  | 2022-06-30 |  | 3818066 | [5 empty] | Green | Project is on track.
Q2 21-22 | WorkSafe Victoria | WorkSafe | 3250 | Claims and Recovery Strategy - Early Online Lodgement (EOL) | Government and Economy | Financial Management | Early Online Lodgement will deliver a digital claim form for workers and employers to submit and track claims via myWorkSafe. Using a phased and scaled rollout with ‘test and learn’ approach and expanding as solution matures and demand grows. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | PMBoK | 2021-07-01 | 2021-09-30 |  | 2021-09-30 | 1078069 |  | 2021-10-01 |  | 2022-06-30 |  | 7028815 | [5 empty] | Green | Project is on track.
Q2 21-22 | WorkSafe Victoria | WorkSafe | 3251 | Claims and Recovery Strategy - Digitisation of the Claim Form & Medical Certificate (DCFMC) | Government and Economy | Financial Management | DCFMC will deliver the digital registration of paper submitted injury claims and documents using OCR technology and integration ingesting directly into WorkSafe's systems reducing administrative overhead associated with manual data entry. | Delivery | Cost Avoidance (Financial) |  | PMBoK | 2021-07-01 | 2021-09-30 |  | 2021-09-30 | 345138 |  | 2021-10-01 |  | 2022-06-30 |  | 2015981 | [5 empty] | Green | Project is on track.
Q2 21-22 | WorkSafe Victoria | WorkSafe | 3252 | Claims and Recovery Strategy - Automated Provider Payment Expansion (APPE) | Government and Economy | Financial Management | Automated Provider Payment Expansion will deliver increased access of invoice submissions by Health Providers through implementation of two new digital claim/payment partners enabling increased volumes of invoices submitted via digital channels. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PMBoK | 2021-07-01 | 2021-09-30 |  | 2021-09-30 | 474247 |  | 2021-10-01 |  | 2022-06-30 |  | 1084529 | [5 empty] | Green | Project is on track.
Q2 21-22 | Department of Health | DH | 3253 | Security Operations Centre (SOC) 2021-22 | Health | Security Management | Continue the delivery of the Security Operations Centre (SOC) services to the Victorian Community Health Services (CHS's) and nominated allied health agencies | Delivery | Cost Reduction (Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2021-06-01 | 2021-06-30 |  | 2021-06-30 | 0 |  | 2021-07-01 |  | 2022-06-30 |  | 1615000 |  |  |  |  | Green | Green | Project on schedule
Q2 21-22 | Fire Rescue Victoria | FRV | 3254 | FRV Operational Station Connectivity | Emergencies and Safety | Assets/Materials Management | The implementation of the FRV network and FRV Station Turn Out systems across ex CFA stations. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | FRV Project Management Framework (PMF) | 2020-09-01 | 2021-03-23 |  | 2021-03-23 | 0 |  | 2021-03-25 |  | 2023-06-30 |  | 16689890 |  |  |  |  | Green | Green | The project is tracking well against scope, budget and schedule.
Q2 21-22 | Department of Premier and Cabinet | DPC | 3255 | Scaling Single Digital Presence (SDP) - Phase Two | Government and Economy | Content Management | Built for government by government SDP offers a common platform for Victorian government content publishing. SDP enables government to consolidate its disparate array of websites to a single platform. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Agile | 2021-07-01 | 2021-07-01 |  | 2021-07-01 | 0 |  | 2021-07-01 |  | 2023-06-30 |  | 29196000 |  |  |  |  | Green | Green | Continuing alignment with new Digital Victoria structure and preparing for next round of WoVG engagement to support website consolidation.
Q2 21-22 | CenITex | CenITex | 3256 | IPS Uplift | Government and Economy | Security Management | To uplift the Intrusion Protection System (IPS) of the Cenitex security services to meet current data throughput and also allow for growth in traffic for coming years. | Delivery | Customer Satisfaction (Non Financial), Eco Improvement (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Increased Revenue (Financial) |  | PRINCE2 | 2021-07-15 | 2021-12-31 | 2021-07-15 | 2021-07-15 | 0 |  | 2021-07-15 |  | 2021-12-31 | 2022-03-07 | 1478085 |  |  |  |  | Amber | Amber | New requirements were identified and the project will be re-planned to take account of the additional scope in January / February 2022.
Q2 21-22 | Department of Justice and Community Safety | DJCS | 3258 | Distracted Driver Camera Project | Law and Justice | Development and Integration | Procurement and implementation of new road safety cameras capable of automatically detecting mobile phone and seatbelt offences. | Initiated |  |  | Project Management Excellence | 2021-07-01 | 2022-03-31 | 2022-04-11 |  | 2000000 | [12 empty] | The project is tracking well against scope, budget and schedule. New cameras are anticipated to go live by 2023, in line with previous Victorian Government announcements.
Q2 21-22 | Transport Accident Commission | TAC | 3260 | Continuous Delivery 2022 | Transport and Vehicles | Systems Management | Continuous Delivery project is aimed at maturing the TAC Technology delivery model with planned releases to support the system changes and initiatives required in the areas of Business Improvement, Scheme Performance and System Stabilisation. | Delivery | Compliance (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-06-17 | 2021-06-17 |  | 2021-06-17 | 0 |  | 2021-07-01 |  | 2022-06-30 |  | 3290148 |  |  |  |  | Green | Green | As at December 31 2021 the project is tracking green against plan and will continue to focus on delivering business improvements and system changes to support scheme performance over the coming 3 months.
Q2 21-22 | Department of Health | DH | 3261 | Health Information Exchange (HIE) Project | Health | Data Management,Development and Integration | Delivery of a Health Information Exchange (HIE) for the sharing of pathology results within three pathology networks that are being established as part of the LISConnect Pathology Reform program, enabling the efficient sharing of clinical information | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2021-06-01 | 2021-06-30 |  | 2021-06-30 |  |  | 2021-07-01 |  | 2025-06-30 |  | 27220000 |  |  |  |  | Green | Green | Project is progressing to schedule. The Planned Delivery Cost was incorrectly reported as $272m in the previous quarter. The correct amount is $27.22m.
Q2 21-22 | Department of Health | DH | 3262 | Trevi Enhancements | Health | Customer Relationship Management | Enhance the Test, Trace and Isolate Case and Contact Relationship Management solution for COVID-19, with a view to scale the platform across the department to support and align with future healthcare and service requirements. | Delivery | Cost Avoidance (Financial), Risk Reduction (Non Financial), Social Improvement (Non Financial) |  | Agile | 2021-06-22 | 2021-08-12 |  | 2021-08-12 | 0 |  | 2021-08-12 |  | 2022-06-30 |  | 6007500 | 16336084 |  |  |  | Green | Green | Project is progressing to schedule and revised cost. Scope and cost increased in response to further enhancements required to address the Delta surge.
Q2 21-22 | Department of Health | DH | 3263 | COVID-19 Border Directions System (Permits) | Health | Data Management | Uplift the Case Management/Workflow system for border permit and exemption applications received either via the Hotline or ServiceVic app, to improve the Department of Health's ability to track and respond to potential sources of COVID-19 outbreaks. | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2021-05-17 | 2021-06-16 |  | 2021-06-17 | 0 |  | 2021-07-01 |  | 2021-12-31 | 2022-06-30 | 1210000 |  |  |  |  | Green | Green | Project progressing to cost and revised schedule. Schedule was extended due to competing priorities in overall COVID-19 Response program.
Q2 21-22 | Department of Families, Fairness and Housing | DFFH | 3264 | Commission for Gender Equality in the Public Sector Reporting Platform | Employment and Workplace | Data Management | Implement a reporting platform to support Victorian public sector organisations, universities and local councils (approximately 300 agencies) in meeting their legal obligation under the Gender Equality Act 2020 to improve workplace gender equality. | Closed - Completed | Customer Satisfaction (Non Financial), Reputation (Non Financial), Social Improvement (Non Financial) | 2021-12-24 | Agile | 2021-03-15 | 2021-05-07 |  | 2021-05-18 | 0 |  | 2021-06-15 |  | 2021-12-31 | 2021-12-24 | 1110000 |  |  |  |  | Green | Green | Project successfully delivered and is now closed.
Q2 21-22 | Department of Families, Fairness and Housing | DFFH | 3265 | Enterprise Outcomes Tracking and Reporting | Community Services | Tracking and Workflow | Enhance the Outcomes Tracking Information System (OTIS) for Family Services, Better Futures and Family Safety Victoria to provide improved outcomes tracking capability, including measurement and monitoring of outcomes, across agencies. | Closed - Completed | Customer Satisfaction (Non Financial), Increased Quality (Non Financial) | 2021-11-12 | Agile | 2020-04-01 | 2020-12-30 |  | 2021-01-10 | 0 |  | 2021-03-22 |  | 2021-11-12 |  | 1201054 |  |  |  |  | Green | Green | Project has successfully delivered and closeout activities are underway.
Q2 21-22 | Southern Metropolitan Cemeteries Trust | SMCT | 3266 | Next Gen Business System Program | Health | Customer Relationship Management,Financial Management | The Next Gen Business System Program will replace existing legacy systems with modern CRM and ERP platforms to fully integrate business processes and data across the enterprise, customers, and partners. | Initiated |  |  | Hybrid - Waterfall and Agile | 2021-07-26 | 2022-02-28 |  |  | 0 | 1500000 | [11 empty] | Overall project status is green. RFT closed on 5 November. Response evaluation completed mid-December with two vendors shortlisted for Solution Exploration. Solution Exploration to commence in February 2022.
Q2 21-22 | South East Water | SE Water | 3267 | OpenText Content Server Upgrade | Environment and Water | Content Management | The content server produce, opentext, requires an upgrade to a current version to ensure it is within support parameters. | Delivery | Risk Reduction (Non Financial) |  | Waterfall | 2020-07-13 | 2021-08-02 |  | 2021-08-04 | 60000 |  | 2021-08-04 |  | 2022-04-22 |  | 1163487 |  |  |  |  | Green | Green | Technical build is progressing to schedule with data migration, environment and integration all aligned to requirements.
Q2 21-22 | Ambulance Victoria | AVS | 3268 | ICT One Touch Laptop Upgrade (FY22) | Health | Assets/Materials Management,Organisational Management ,Systems Management | Uplift our information technology, to ensure our patient and business information is secure, improve the reliability of our service to support better patient care, and provide digital capability that meets the needs of our mobile workforce | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-07-01 | 2021-09-30 |  | 2021-09-30 | 0 |  | 2021-09-30 |  | 2022-12-31 | 2022-06-30 | 5150000 |  |  |  |  | Green | Green | Project tracking to roll out on schedule as anticipated.
Q2 21-22 | Ambulance Victoria | AVS | 3269 | Financial Analytics | Health | Analyses and Statistics ,Business Intelligence,Financial Management,Knowledge Discovery ,Reporting | Transition AV Financial Reporting and Analytics system to Cloud service enabling AV to mitigate the current technology risks associated with operating an out of support system while also providing additional functionality for financial reporting. | Initiated |  |  | Hybrid - Waterfall and Agile | 2021-07-01 | 2021-12-31 |  |  | 213850 | [12 empty] | Project tracking to roll out on schedule as anticipated.
Q2 21-22 | Melbourne Water | MELB Water | 3270 | Audio Visual Remediation | Environment and Water | Collaboration | Melbourne Water has a requirement to update Audio-Visual solutions in meeting rooms across multiple sites in Victoria that will provide a consistent experience for all users and allow for enhanced collaboration. | Initiated |  |  | PMBoK | 2021-07-08 | 2021-12-03 | 2022-01-20 |  | 0 | [12 empty] | Business case going through workflow approvals. Completion and endorsement of sourcing strategy and tender evaluation plan. Request for Proposal (RFP) package released to the market.
Q2 21-22 | Melbourne Water | MELB Water | 3272 | Cyber Security Uplift Program 2021 | Environment and Water | Security Management | Program of works to uplift the capability in Melbourne Waters cyber security protection. With items around Endpoint protection, documentation uplift and proactive security alert remediation. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-07-01 | 2021-11-30 | 2022-02-18 |  | 0 | [12 empty] | Business Case with Chief Information Security Officer (CISO) for review.
Q2 21-22 | Melbourne Water | MELB Water | 3273 | Enablement of Information Governance in repositories | Environment and Water | Data Management | Implement effective business rules and governance standards within information management repositories that support the Information Management Strategy, and meets the Public Records Office of Victoria compliance obligations. | Initiated |  |  | PMBoK | 2021-07-01 | 2021-10-04 | 2022-02-21 |  | 0 | [12 empty] | Design recommendations are being drafted.
Q2 21-22 | Melbourne Water | MELB Water | 3274 | Portal New Services | Environment and Water | Communication,Content Management,Customer Relationship Management | Portal went live in 2019 as a minimal viable product (MVP). In line with the Strategy and Pricing Submission 2021 (Water Plan 5) a roadmap of key enhancements will be delivered to improve customers digital experience. | Initiated |  |  | PMBoK | 2021-07-01 | 2021-10-29 |  |  | 0 | [12 empty] | Business Case has been approved. A decision was made to slow down the work on Portal for the remainder of the financial year due to the dependency on another project, which is not yet live. The delivery uplift design component with the vendor is now completed and final report will be presented to the team in January.
Q2 21-22 | Melbourne Water | MELB Water | 3275 | Website New Services | Environment and Water | Communication,Content Management,Customer Preferences,Customer Relationship Management | The Melbourne Water Website went live in October 2017 as a minimal viable product (MVP). In line with Strategy and Pricing Submission 2021 (Water Plan 5), a roadmap of key enhancements will be delivered to improve customers digital experience. | Initiated |  |  | PMBoK | 2021-07-01 | 2021-10-29 |  |  | 0 | [12 empty] | Business Case has been approved. The delivery uplift design component with the vendor is now completed and final report will be presented to the team in January.
Q2 21-22 | State Revenue Office | SRO | 3276 | Victorian Homebuyer Fund | Government and Economy | Development and Integration | This project supports the administration of the Victorian Homebuyer Fund (VHF) launched in October 2021. | Delivery | Efficiency/Productivity (Non Financial) |  | Agile | 2021-03-08 | 2021-04-30 |  | 2021-04-30 | 529846 |  | 2021-05-03 |  | 2022-06-30 |  | 10579433 | 14716944 |  |  |  | Green | Green | A variation was approved 8 December 2021 to address emergent requirements in the final delivery release of the solution. This release primarily addresses the ongoing management of the scheme after applicants have purchased a property. The implementation complexity of these arrangements was not apparent until detailed analysis was completed following scheme launch.
Q2 21-22 | Royal Children's Hospital | RCH | 3277 | Wireless Network Infrastructure Refresh | Health | Communication | Refresh of all wireless infrastructure and Wireless Access Points across the Royal Children's Hospital Campus | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2021-05-03 | 2021-11-05 |  | 2021-11-05 | 0 |  | 2021-11-08 |  | 2022-12-16 |  | 1700000 | [5 empty] | Green | Project tracking to budget, scope and plan. No issues reported for current reporting period.
Q2 21-22 | Peter MacCallum Cancer Centre | Peter MAC | 3278 | People and Payroll Transformation Program - Rostering Project | Health | Human Capital / Workforce Management ,Human Resources | The People Systems Program will deliver a Rostering solution which will increase efficiency and improve data security and integrity by eliminating paper time sheets and manual processes. | Initiated |  |  | PRINCE2 | 2021-09-01 | 2022-07-01 |  |  | 50000 | [12 empty] | Procurement activities underway.
Q2 21-22 | Dental Health Services Victoria | DHSV | 3280 | Electronic Oral Health Record (EoHR) | Health | Development and Integration | The Electronic Oral Health Record (EoHR) aims to replace and consolidate the legacy solution to deliver a single state-wide oral health record to support improved dental health outcomes in Victoria | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-04-01 | 2020-10-30 |  | 2020-10-30 | 390000 |  | 2021-09-22 |  | 2023-06-30 |  | 9490000 |  |  |  |  | Green | Green | The project has completed an IPS with the software vendor in order to validate and amend (as needed) the scope of functionality required. The Steering Committee has been established and will be endorsed at the first Steering Committee meeting in February 2022.
Q2 21-22 | Department of Jobs, Precincts and Regions | DJPR | 3281 | Sick Pay Guarantee System Build | Business and Industry | Customer Initiated Assistance,Customer Relationship Management,Tracking and Workflow | Delivery of a platform solution to manage accounts and provide payments to workers accessing the pilot scheme. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-11-23 | 2021-08-10 |  | 2021-08-10 | 100000 |  | 2021-11-04 |  | 2022-03-15 |  | 2400000 | [5 empty] | Green | The Project is tracking to its approved plan.
Q2 21-22 | South East Water | SE Water | 3292 | HSE Project | Environment and Water | Management of Process ,Tracking and Workflow | Implement a new HSE platform to enable capture and management of HSE related risks. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2021-07-05 | 2021-07-14 |  | 2021-07-14 | 25000 |  | 2021-07-14 |  | 2022-06-30 |  | 2979727 |  |  |  |  | Green | Green | System build has completed and UAT and training is progressing well ready for a go live in February.
Q2 21-22 | South East Water | SE Water | 3293 | Service Delivery Model | Environment and Water | Management of Process ,Routing and Scheduling | Enhancements to the works management system are needed to support the change in the service delivery model and commercial framework. | Delivery | Compliance (Non Financial) |  | Agile | 2021-07-13 | 2021-10-04 |  | 2021-10-25 | 100000 |  | 2021-10-25 |  | 2022-04-22 |  | 1214552 | [5 empty] | Green | The system design has been completed and the build is underway. UAT is due to commence in February
Q2 21-22 | Department of Families, Fairness and Housing | DFFH | 3295 | Housing Client Self-Service - Client and Tenancy Updates | Community Services | Customer Preferences | Implementing self serve capability into the Client facing application, Housing Vic Online Services (HVOS), to enable clients of Director of Housing to access information about their tenancy, bond and housing application. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-05-17 | 2021-05-19 |  | 2021-06-04 | 0 |  | 2021-07-01 |  | 2022-06-30 |  | 2094260 | 2301250 |  |  |  | Green | Green | Project is progressing to schedule and revised cost.
Q2 21-22 | Victorian Building Authority | VBA | 3296 | Practitioner Registration Program (PRP) | Property and Planning | Customer Relationship Management | Our strategic objective is making licensing & registration systems more efficient, simpler & transparent, we plan to create a Practitioner Registration Platform providing online web forms & internal workflows & data integrations | Delivery | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-02-05 | 2021-03-24 |  | 2021-03-24 | 0 |  | 2021-03-24 |  | 2022-01-31 | 2022-04-29 | 2030000 | 1630000 |  |  |  | Green | Amber | PRP Domestic Builder Core System: Successfully deployed to the production environment with 6 issues. 2 issues did impact BAMS permit submission and reporting. Issue 1 - permit submission fixed with 24 hours and reporting issue fixed with hours.
Q2 21-22 | Royal Children's Hospital | RCH | 3297 | Parkville EMR Virtual Care Project | Health | Management of Process | The Virtual Care Project will be implemented across the Parkville precinct supporting the provision of remote care of patients (i.e. Hospital In The Home, etc). Expanding further functionality and applications of current shared EMR. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2021-08-01 | 2023-12-31 | 2021-11-21 | 2021-11-22 | 0 |  | 2021-11-29 |  | 2022-12-31 |  | 3649900 | [5 empty] | Green | Vendor procurement and contract preparation complete. Recruitment for the project team is complete and training underway.
Q2 21-22 | Greater Western Water Corporation | GW Water | 3298 | Integration - Corporate Systems Platforms FY22 | Environment and Water | Content Management | The merger of CWW and WW requires the consolidation and update of several internal solutions, which has commenced and now requires finalisation | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-07-01 | 2021-07-01 |  | 2021-07-01 | 1 |  | 2021-07-01 |  | 2022-06-30 |  | 2999999 |  |  |  |  | Green | Green | The project concluded expressions of Interest for a platform upgrade. Additionally, there have been three waves of functional improvements to the existing platform to ensure improved integration and efficiencies with immediate benefits.
Q2 21-22 | Greater Western Water Corporation | GW Water | 3299 | Integration - Our Spatial Odyssey | Environment and Water | Assets/Materials Management,Content Management,Data Management,Development and Integration ,Management of Process | This project will define a new spatial strategy and exploit spatial information, emerging technologies and standards in order to deliver greater value, improve asset information, improve public services and enable an on-demand self-service model. | Initiated |  |  | Waterfall | 2021-07-01 | 2022-06-30 |  |  | 1500000 | [12 empty] | The project concluded expressions of Interest for a platform upgrade. Additionally, there have been three waves of functional improvements to the existing platform to ensure improved integration and efficiencies with immediate benefits.
Q2 21-22 | Greater Western Water Corporation | GW Water | 3300 | Integration - FY22 Unified Communications | Environment and Water | Analyses and Statistics ,Collaboration ,Communication,Customer Initiated Assistance,Human Capital / Workforce Management ,Management of Process ,Organisational Management ,Reporting | GWW contact centre phone services are split across two telephony platforms resulting in significant overheads. To drive operational & efficiencies the initiative will unify contact centre & back office phone services to a single telephony platform. | Delivery | Cost Reduction (Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-07-07 | 2021-08-24 |  | 2021-08-24 | 182901 |  | 2021-08-24 |  | 2022-06-30 |  | 817099 | 1017099 |  |  |  | Green | Green | The project concluded expressions of Interest for a platform upgrade. Additionally, there have been three waves of functional improvements to the existing platform to ensure improved integration and efficiencies with immediate benefits.
Q2 21-22 | Department of Health | DH | 3301 | Disaster Recovery as a Service (DRaaS) | Health | Development and Integration | Enable Victorian public health services to have a fit-for-purpose ICT disaster recovery capability for critical applications in the event of a significant disruption. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2020-09-01 | 2021-07-30 | 2021-05-28 | 2021-05-28 | 1432000 |  | 2021-07-26 |  | 2023-06-30 | 2022-06-30 | 3883000 |  |  |  |  | Amber | Amber | The project is AMBER due to agencies operational workloads impacting on response times. The project has engaged additional agencies to keep momentum and reduce impact to the schedule.
Q2 21-22 | Greater Western Water Corporation | GW Water | 3303 | Cyber Security Uplift FY22 | Environment and Water | Security Management | This project contains seven initiatives to address the security risks identified in the GWW Security Risk Assessment Report and also reduce costs reduce network infrastructure complexity reduce tech debt and reduce the load on the service desk. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Reputation (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-07-01 | 2021-09-09 |  | 2021-09-09 | 100000 |  | 2021-09-09 |  | 2022-06-30 |  | 1150000 |  |  |  |  | Green | Green | The project concluded expressions of Interest for a platform upgrade. Additionally, there have been three waves of functional improvements to the existing platform to ensure improved integration and efficiencies with immediate benefits.
Q2 21-22 | Department of Transport | DOT | 3304 | Heavy Vehicle Hazard Perception Testing | Transport and Vehicles | Content Management,Customer Initiated Assistance,Customer Preferences | Delivery of Hazard Perception Testing (HPT) capability in combination with a framework that will allow for delivery of content and knowledge testing for applicants within the context of the revised National Heavy Vehicle Driver Competency Framework | Postponed |  | 2021-12-06 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-07-01 | 2021-12-30 |  |  | 0 | [5 empty] | 0 | [6 empty] | Project is on hold.
Q2 21-22 | Greater Western Water Corporation | GW Water | 3305 | SPARC Re-Platform FY21 | Environment and Water | Data Management,Systems Management | The project aims to migrate the current ageing Oracle SPARC/Solaris to a new SPARC platform as part of the platform replacement cycle. Additionally the project will migrate data storage from legacy Hitachi to a new NetApp SAN storage platform. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-08-13 | 2021-01-08 |  | 2021-01-08 | 321348 |  | 2021-01-08 |  | 2022-06-30 |  | 1958652 |  |  |  |  | Green | Green | The project concluded expressions of Interest for a platform upgrade. Additionally, there have been three waves of functional improvements to the existing platform to ensure improved integration and efficiencies with immediate benefits.
Q2 21-22 | Department of Transport | DOT | 3306 | DoT Integration: Identity and Access Join | Transport and Vehicles | Development and Integration ,Systems Management | Enable an integrated and secure Department of Transport (DoT) through ensuring any DoT user from anywhere using a DoT issued device can access data systems and resources across the department. | Delivery | Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2021-06-07 | 2021-07-05 |  | 2021-07-05 | 0 |  | 2021-07-05 |  | 2022-03-25 |  | 5870000 |  |  |  |  | Amber | Amber | Overall status is amber due to schedule risks and multiple dependencies involving external vendors. Working with the project authority and external vendors to address the risks. Network Join -technical implementation to enable 'soft launch' was completed in Dec '21 as planned.
Q2 21-22 | Department of Transport | DOT | 3307 | DoT Integration: Transition State Operating Model and SOE Transition | Transport and Vehicles | Development and Integration ,Security Management | Objective of this project is to deliver improved operational support model and SOE management structure to support the distributed nature of DoT operations. | Delivery | Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-06-07 | 2021-07-05 |  | 2021-07-05 | 0 |  | 2021-07-05 |  | 2022-06-30 |  | 1230000 |  |  |  |  | Amber | Amber | Overall status is amber due to schedule risks. Working with external vendors to mitigate the risks.
Q2 21-22 | Department of Transport | DOT | 3308 | DoT Integration: Security Uplift and Remediation | Transport and Vehicles | Security Management | Objectives of this project is to Implement foundational security enhancements to ensure the future state technology landscape of an integrated DoT remains compliant to the operational standards required. | Delivery | Compliance (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-06-07 | 2021-07-05 |  | 2021-07-05 | 0 |  | 2021-07-05 |  | 2023-06-30 |  | 2370000 |  |  |  |  | Amber | Amber | Overall project status is amber due to schedule risks. Working through the risks with external vendors.
Q2 21-22 | Victorian Public Sector Commission | VPSC | 3310 | Jobs and Sills Exchange (JSE) digital 2.0 | Government and Economy | Human Capital / Workforce Management ,Knowledge Discovery | The project will uplift the JSE digital platform to improve employment and career services to VPS employees. This will support workforce transition, skills development, mobility and improve workforce effectiveness. | Delivery | Efficiency/Productivity (Non Financial) |  | Agile | 2020-05-01 | 2020-11-30 |  | 2020-11-30 | 0 |  | 2021-07-01 |  | 2022-06-30 |  | 2320000 |  |  |  |  | Green | Green | Project delivery is structured into fortnightly sprints. Initial work has focussed on strengthening the JSE technical platform, by upgrading all components to current, supported versions; and migrating job and member data from external system into 'core' JSE platform. This is now complete, and delivery focus is now on additional features and services aligned with delivery roadmap.
Q2 21-22 | Department of Transport | DOT | 3311 | Smarter Roads Program - Open Data | Transport and Vehicles | Analyses and Statistics ,Business Intelligence,Data Management | Objective of this project is to improve access to the department’s transport data for use in internal and external (3rd party) customer experience solutions and ensure a wider variety of important data sources are available to be used. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-03-31 | 2021-10-18 |  | 2021-10-18 | 0 |  | 2021-10-18 |  | 2022-06-30 |  | 2070043 | [5 empty] | Amber | Overall project status is amber due to schedule issues. API integration with data sources and testing in progress. In parallel project team is also reviewing/updating Data Security Control traceability matrix for the security assessment work.
Q2 21-22 | Department of Transport | DOT | 3312 | Smarter Roads Program - Timetable Systems Uplift | Transport and Vehicles | Content Management,Data Management,Systems Management | Objective of this project is to prepare an options analysis brief outlining best of breed solutions for Timetabling and Journey planning. The analysis will inform a recommended solution to build and implement. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-05-03 | 2021-12-30 | 2022-02-07 |  | 0 | [12 empty] | Project initiation activities are ongoing.
Q2 21-22 | Department of Transport | DOT | 3313 | Public Transport Real-time Vehicle Location | Transport and Vehicles | Business Intelligence,Data Management,Development and Integration | Objective of this project is to modify A,B & C-Class tram Thoreb units to enable transfer of data to Transnet & trial Traffic Light Prioritisation. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-10-19 | 2021-12-20 | 2022-02-28 |  | 0 | [12 empty] | Project initiation and procurement activities are ongoing.
Q2 21-22 | Lower Murray Urban and Rural Water Corporation | LMUR Water | 3315 | Business Transformation Program - Horizon 1 | Environment and Water | Customer Relationship Management,Data Management,Financial Management,Management of Process ,Tracking and Workflow | The program will uplift capabilities across key business functions, including customer service, data, asset and workforce management, and financial management to enable improved customer service and efficiency.​ | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-01-11 | 2021-04-27 |  | 2021-04-27 | 115137 |  | 2021-07-01 |  | 2023-06-30 |  | 5200000 | 5606626 |  |  |  | Green | Green | Project is tracking well
Q2 21-22 | Greater Western Water Corporation | GW Water | 3316 | Integration - Customer Website Consolidation | Environment and Water | Assets/Materials Management,Content Management,Customer Preferences,Data Management | To deliver a re-developed website utilising GovCMS platform with a focus on delivering functions & features in accordance with a priority of customer usage & to consolidate and then decommission the GWW Microsite & 2 legacy websites | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Reputation (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-07-01 | 2021-10-11 |  | 2021-10-11 | 311830 |  | 2021-10-11 |  | 2022-06-30 |  | 1188170 | [5 empty] | Green | The project concluded expressions of Interest for a platform upgrade. Additionally, there have been three waves of functional improvements to the existing platform to ensure improved integration and efficiencies with immediate benefits.
Q2 21-22 | South West Alliance of Rural Health | SWARH | 3317 | SWARH Modern Workplace Migration and Adoption | Health | Collaboration ,Communication,Content Management,Customer Initiated Assistance,Customer Preferences,Document Management ,Forms Management,Human Capital / Workforce Management ,Knowledge Discovery ,Knowledge Management ,Management of Process ,Organisational Management ,Records Management ,Search ,Security Management ,Tracking and Workflow | To migrate all SWARH-supported Health Services to modern workplace cloud services, and promote the adoption of these services. This will drive improved communication, collaboration and productivity, across and within each of these Health Services. | Initiated |  |  | PMBoK | 2021-12-03 | 2022-05-16 |  |  | 224344 | [12 empty] | Project is mobilising, with recruitment of a Business Analyst and Technical resources, to run Tender (RFT) to select Service Provider with modern workplace migration and adoption capabilities.
Q2 21-22 | Department of Transport | DOT | 3318 | Automatic Vehicle Monitoring Sustainment (AVMS) | Transport and Vehicles | Systems Management | Address key short-term challenges affecting Melbourne’s tram network through targeted initiatives to sustain the AVM system in the short-term while the Department continues to develop options for a future Tram Monitoring and Control (TMC) system. | Initiated |  |  | PTV Investment Lifecycle | 2021-07-01 | 2022-04-29 |  |  | 1785000 | [12 empty] | The Operating System Upgrade is progressing on track as a Franchisee Project. The Project has briefed stakeholders on detailed financials, approach for fitment of new on-board AVM units and alignment with tram traffic light priority / passenger counting. Planning and preparation for procurement of 'on-board' AVM components is progressing.
Q2 21-22 | Fire Rescue Victoria | FRV | 3320 | Response Monitoring and Move-Up Monitoring | Emergencies and Safety | Business Intelligence | • Improve emergency response benchmarks, predicative deployment analysis and aid decision making to improve operational response utilising historical CAD response data. • Efficient resource planning and use based on real time data to inform operation | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | FRV PMF | 2021-06-01 | 2021-10-01 |  | 2021-10-01 | 1 | 0 | 2021-12-01 |  | 2023-06-30 |  | 3000000 | [5 empty] | Amber | As a result of COVID there has been a slight delay in this project. However, new person in the CAD area will be trained, and this will allow us to have another person in this team. The project plan prepared contains activities to bring the appropriate project “back on line”. A revised project plan has been prepared and significant work will be completed in the next quarter.
Q2 21-22 | Fire Rescue Victoria | FRV | 3325 | HRIS | Emergencies and Safety | Human Resources | HRIS Project is in the initiation stage, with the primary focus this year to address foundation data issues, collaborate with the Rostering and Shift Change project and build a business case for approval around mid 2022. Scope includes Payroll and HR | Initiated |  |  | FRV Project Management Framework (PMF) | 2021-12-10 | 2022-06-30 |  |  | 0 | [12 empty] | The project is tracking well against scope, budget and schedule.
Q2 21-22 | Fire Rescue Victoria | FRV | 3326 | Desktop Replacement | Emergencies and Safety | Assets/Materials Management | Replacement of ex-Metropolitan Fire Brigade (MFB) workplace computing devices in excess of 4 years old. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | FRV Project Management Framework (PMF) | 2021-07-01 | 2021-11-10 |  | 2021-11-10 | 0 |  | 2021-11-11 |  | 2024-06-30 |  | 2520000 | [5 empty] | Green | The project is tracking well against scope, budget and schedule.
Q2 21-22 | Office of the Special Investigator | OSI | 3327 | Digital Forensic Investigation platform | Law and Justice | Document Management | A digital forensic investigation platform operating a range of forensic evidence processing, analysis and investigation tools will be established and used to provide secure management and use of data obtained by the Office of the Special Investigator | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2021-09-15 | 2021-12-17 |  | 2021-12-17 | 0 |  | 2021-12-23 |  | 2023-06-30 |  | 3254990 | [5 empty] | Green | The project has received approval and is in its initial planning and delivery stage.
Q2 21-22 | Transport Accident Commission | TAC | 3329 | Financial Management & Procurement System | Transport and Vehicles | Financial Management | The project will replace the existing Finance and Procurement management systems in order to ensure compliance requirements are met, mitigate the risk of fraud and corruption and move processes towards industry practice. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-10-19 | 2021-12-16 |  | 2021-12-16 | 270115 |  | 2021-12-16 | 2021-12-16 | 2023-02-06 |  | 2412927 | [5 empty] | Green | On Track.
Q2 21-22 | Transport Accident Commission | TAC | 3330 | ConTACt | Transport and Vehicles | Communication | The project will deliver an upgrade to the core configuration of the IVR to improve the way we use the phone channel to communicate with our clients & providers. It will provide staff with the right tool to perform their role, ensuring consistency. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Reputation (Non Financial) |  | Waterfall | 2021-05-20 | 2021-10-21 |  | 2021-10-21 | 509322 |  | 2021-10-21 |  | 2022-04-30 |  | 1468774 | [5 empty] | Green | On Track.
Q2 21-22 | Department of Health | DH | 3333 | Central Immunisation Records Victoria (CIRV) | Health | Security Management | To deliver a state of the art, centralised, long-term strategic solution to replace end of life legacy local immunisation system (ImPS) in use by over 70 councils and 3 health services enabling more seamless delivery of immunisation services. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-10-01 | 2021-11-30 |  |  | 0 | [12 empty] | Business case approved. Procurement activities are currently being finalised.
Q2 21-22 | South West Alliance of Rural Health | SWARH | 3334 | SWARH Electronic Health Record Upgrade | Health | Customer Relationship Management,Data Management,Development and Integration ,Management of Process ,Records Management ,Systems Management,Tracking and Workflow | Major upgrade to the Electronic Health Record (EHR) solution that supports 11 health services across South West Victoria. The project will improve clinician and patient user experience, focusing on quality and safety of patient care. | Initiated |  |  | PRINCE2 | 2019-10-16 | 2022-03-31 |  |  | 180000 | [12 empty] | Implementation Planning Study presented to the CEOs November 30th. This is expected to be tabled to each health service's board throughout March and April to formally endorse the project.
Q2 21-22 | William Angliss Institute of TAFE | WA TAFE | 3335 | Core Infrastructure Refresh | Education | Systems Management | To replace 5+ year old core infrastructure for Production Backup and Disaster Recovery. This include production servers backup platforms and storage | Initiated |  |  | Waterfall | 2021-11-01 | 2022-02-28 |  |  | 30000 | [12 empty] | The project is due to go to the WAI Change Control Board on 8 February for endorsement for Executive consideration
Q2 21-22 | Department of Families, Fairness and Housing | DFFH | 3337 | Service Agreements Management System (SAMS2) Reporting Solution | Community Services | Business Intelligence | Project will replace the existing reporting solution with a fit for purpose, cloud based and scalable solution for SAMS2 data including a purpose built data mart that will enable end users to self serve reports. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Agile | 2021-03-22 | 2021-09-16 |  | 2021-09-16 | 0 |  | 2021-11-01 |  | 2022-12-31 |  | 1412500 | [5 empty] | Green | Project is progressing to schedule and cost.
Q2 21-22 | Melbourne Water | MELB Water | 3338 | Electronic Content Management Phase 1 | Environment and Water | Content Management | This project will upgrade Melbourne Waters current document storage repositories and migrate to a new Electronic Document and Records Management System (EDRMS) | Initiated |  |  | PMBoK | 2021-10-08 | 2022-09-22 |  |  | 0 | [12 empty] | Sourcing strategy prepared pending procurement team review and feedback.
Q2 21-22 | Melbourne Water | MELB Water | 3339 | Network Hardware Refresh 21/22 | Environment and Water | Security Management | Melbourne Water is ensuring continued investment in our IT network through ongoing refresh of IT Hardware as it approaches end of life rather than extending support reducing risk of unplanned network outages. Priority 1 & 2 devices. | Initiated |  |  | PMBoK | 2021-10-29 | 2022-01-31 |  |  | 0 | [12 empty] | Business case has been submitted and awaiting approval.
Q2 21-22 | Austin Health | AH | 3341 | EMR Documentation and Infusions Project | Health | Communication,Document Management ,Forms Management,Tracking and Workflow | The project will implement electronic clinical documentation and the administration of fluid medication and nutrition infusions, reducing the risks associated with paper-based document management and improving patient safety. | Initiated |  |  | Waterfall | 2021-10-04 | 2021-11-02 |  |  | 0 | [12 empty] | Delivery is planned to commence from 24 January 2022
Q2 21-22 | Department of Health | DH | 3342 | OurService Phase 3 | Health | Tracking and Workflow | Build on existing Service Management Platform to further uplift and modernise the department’s Corporate Service functions delivering a consistent enterprise service management experience for DH & DFFH staff and external agencies who use OurService. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Agile | 2021-07-01 | 2021-07-20 |  | 2021-07-20 | 0 |  | 2021-08-02 |  | 2022-07-31 |  | 2400000 | [5 empty] | Green | Project is progressing to schedule and cost.
Q2 21-22 | Department of Families, Fairness and Housing | DFFH | 3343 | Housing Integrated Information Program (HiiP) Windows Server Upgrade | Community Services | Systems Management | The project will upgrade outdated application servers to the supported 2019 version which will mitigate risk and enable for future transitioning to the cloud. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-06-08 | 2021-12-01 |  | 2021-12-01 | 0 |  | 2021-12-01 |  | 2022-06-30 |  | 2225000 | [5 empty] | Green | Project is progressing to schedule and cost.
Q2 21-22 | Department of Families, Fairness and Housing | DFFH | 3344 | Property Acquisition and Sales and Lease-In Management Systems Replacement | Property and Planning | Systems Management | Replace existing systems, used to manage property acquisitions and sales and lease acquisitions, to a fit for purpose solution that will meet the increased demands on property acquisitions to support Homes Victoria initiatives. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-12-16 | 2021-05-31 |  |  | 1 | [12 empty] | Procurement activities are underway.
Q2 21-22 | State Revenue Office | SRO | 3345 | Mental Health and Wellbeing Surcharge | Government and Economy | Development and Integration | The Mental Health and Wellbeing Surcharge was announced in the May 2021 budget to support mental health initiatives. It is payable from 1 January 2022 by larger employers and groups with wages over certain thresholds. | Delivery | Increased Revenue (Financial) |  | Agile | 2021-08-31 | 2021-08-31 |  | 2021-08-31 | 0 |  | 2021-08-31 |  | 2022-12-31 |  | 3668000 | [5 empty] | Green | The project is on track to deliver the first milestone - the initial submission of returns at the end of the January period.
Q2 21-22 | Department of Health | DH | 3346 | G2G Now Home Isolation Digital Solution - Proof of Concept | Health | Communication | This project is a proof of concept to utilise a digital solution for compliance check-in within Victoria for members of the public who are required to isolate or quarantine due to COVID-19. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-08-03 | 2021-08-07 |  | 2021-08-07 | 0 |  | 2021-09-01 |  | 2022-02-15 |  | 1210687 | [5 empty] | Green | Project is progressing to schedule and cost.
Q2 21-22 | Department of Health | DH | 3347 | Consultative Councils Unit (CCU) Project - Phase 2 | Health | Data Management | Implement a robust integrated solution to facilitate secure collection, storage, linkage, analysis and visualization of data for mortality, morbidity and congenital anomalies in Victoria to support timely case resolution and reporting. | Delivery | Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2020-12-14 | 2021-11-24 |  | 2021-11-25 | 0 |  | 2021-11-25 |  | 2022-04-29 |  | 1353750 | [5 empty] | Green | Project is progressing to schedule and cost.
Q2 21-22 | Bendigo Kangan Institute of TAFE | BKI TAFE | 3348 | Business Intelligence and Enterprise Reporting | Education | Business Intelligence | This project will establish the Enterprise Data Foundation to enable implementation of the Business Intelligence capability. Business Intelligence will provide key insights and visualisations, to enable improvements toward financial sustainability. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Increased Revenue (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-09-11 | 2021-10-29 |  | 2021-10-29 | 0 |  | 2021-10-29 |  | 2022-08-31 |  | 1032346 | [5 empty] | Green | Overall Status is green project is tracking to plan. A BI specialist has been engaged and procurement has been finalised. Project has started gathering detailed data requirements.
Q2 21-22 | Bendigo Kangan Institute of TAFE | BKI TAFE | 3350 | Wide Area Network (WAN) | Education | Communication,Systems Management | This project will replace the current outdated Wide Area Network (WAN) with a transformational uplift in capacity resilience and security, providing upgraded, cost efficient connectivity for the next 5+ years. | Delivery | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-07-30 | 2021-12-16 |  | 2021-12-16 | 40700 |  | 2021-12-16 |  | 2022-09-30 |  | 1602284 | [5 empty] | Green | Project is currently green. Procurement activities have been completed, and project governance has been established.
Q2 21-22 | Bendigo Kangan Institute of TAFE | BKI TAFE | 3351 | Website Redevelopment | Education | Systems Management | Rebuild and launch Kangan Institute and Bendigo TAFE externally facing websites with focus on customer acquisition. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Revenue (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-05-25 | 2021-12-16 |  | 2021-12-16 | 56350 |  | 2021-12-16 |  | 2022-07-31 |  | 978751 | [5 empty] | Green | Project is tracking green in overall scope, project initiation has occurred. Procurement is complete and business case has been approved.
Q2 21-22 | CenITex | CenITex | 3352 | CTX - Cenitex Backup Platform Modernisation | Government and Economy | Assets/Materials Management | The purpose of this initiative is it to refresh and uplift the current Cenitex Backup and Data Protection platform, ensuring that Cenitex can continue to offer contemporary and in demand services to its customer base. | Delivery | Cost Avoidance (Financial) |  | PRINCE2 | 2021-10-27 | 2021-10-30 |  | 2021-10-30 | 0 |  | 2021-11-01 |  | 2022-06-30 |  | 2467000 | [5 empty] | Green | The Delivery is tracking to plan to deliver new backup services.
Q2 21-22 | Environment Protection Authority | EPA | 3353 | Waste Tracker Enhancement project | Environment and Water | Tracking and Workflow,Business Intelligence,Data Management | Waste Tracker will replace the Waste Transport Certificate system to allow relevant data to be entered by industry in a reliable manner, ensuring the timely reports by the waste industry and allow live tracking of waste movements | Initiated |  |  | Agile | 2021-12-17 | 2022-02-01 |  |  | 50000 | [12 empty] | Project was initiated in Q2 with internal documentation provided for internal approvals and to allow the signing of Schedule of Works by EPA CEO and will be applicable in the next quarter reporting
Q2 21-22 | Greater Western Water Corporation | GW Water | 3354 | Growth & Development Systems | Environment and Water | Assets/Materials Management,Collaboration ,Data Management,Forms Management,Management of Process ,Records Management ,Reporting ,Tracking and Workflow | This multi-year initiative will adopt a strategic roadmap for the Urban Development ecosystem by performing analysis & prioritisation of work to support the growth of GWW service areas & improve agility to better service our customers. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-07-01 | 2022-06-30 |  |  | 1650000 | [12 empty] | The project concluded expressions of Interest for a platform upgrade. Additionally, there have been three waves of functional improvements to the existing platform to ensure improved integration and efficiencies with immediate benefits.