## PublicDataReport
Collection Period | Department/ Agency Name | Agency Short Name | Project ID | Project Title | Government Domain | ICT Project Category | Description | Stage | Benefit Category ( Benefit Type) | Date of Closure/ Postponement | PM Methodologies | Initiation Start Date | Planned Initiation End Date | Revised Initiation End Date | Business Case Approval Date | Planned Initiation Cost | Revised initiation Cost | Planned Delivery Start Date | Revised Delivery Start Date | Planned Delivery End Date | Revised Delivery End Date | Planned Delivery Cost | Revised Delivery Cost | Q3 20-21 | Q4 20-21 | Q1 21-22 | Q2 21-22 | Q3 21-22 (Current) | Reporting Comments
Q3 21-22 | Country Fire Authority | CFA | 2151 | CFA Short Status Messaging (SSM) | Emergencies and Safety | Communication | Provide a Short Status Messaging system to allow CFA mobile radios to send status messages to fire dispatchers at ESTA. This will deliver more efficient use of radio channels by minimising voice congestion on radio dispatch channels. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2010-10-01 | 2012-07-01 | 2020-06-30 | 2020-07-01 | 0 | 45000 | 2020-07-01 |  | 2021-06-30 | 2023-06-30 | 2850000 |  | Green | Green | Green | Green | Red | Integration into CAD environment has been delayed due to state wide review of integration solutions.
Q3 21-22 | Department of Health | DH | 2200 | Replace Integration Solution for Patient and Clinical Information | Health | Development and Integration | Replacement of the integration solution to support Victorian acute public health services to integrate patient and clinical information. Prior legacy solution was at end of life posing a significant operational and security threat to health services. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2016-07-01 | 2016-11-30 |  | 2016-11-30 | 0 |  | 2016-12-01 |  | 2020-06-30 | 2022-04-30 | 16000000 | 16118793 | Green | Green | Green | Green | Green | Project completed on schedule with 17 health services migrated to the replacement integration solution. Project closure anticipated end April 2022.
Q3 21-22 | Gippsland Health Alliance | GHA | 2209 | Electronic Medical Record and Community Health (EMRCH) | Health | Customer Relationship Management,Data Management,Document Management | The EMRCH project is a core component to the facilitation of highly integrated health services across all aspects of the specific services administered by the members of the Gippsland Health alliance, its implementation will facilitate the implementation of new models of care. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PMBoK | 2016-02-02 | 2017-10-30 |  | 2017-11-01 | 554038 |  | 2018-01-09 |  | 2019-12-31 | 2022-12-31 | 7419045 | 14686274 | Green | Green | Amber | Amber | Amber | COVID-19 impacts continue to complicate resourcing of project activities. Governance processes put in place to mitigate limited attendance to project activities.
Q3 21-22 | Hume Rural Health Alliance | HRHA | 2210 | Goulburn Valley Health Redevelopment | Health | Systems Management | The ICT component of the redevelopment of the Goulburn Valley Health Hospital to support improved health outcomes for the GV community, better access to health care in the GV community and the better use of health resources in Victoria. | Delivery | Increased Revenue (Financial) |  | PRINCE2 | 2016-04-20 | 2018-06-30 | 2018-08-01 | 2018-08-01 | 400000 | 100000 | 2018-10-31 |  | 2020-05-29 | 2022-09-30 | 4600000 | 3866000 | Green | Green | Green | Green | Green | New build works have been accelerated. Refurbishment works have been delayed as a result of response to COVID-19.
Q3 21-22 | Fire Rescue Victoria | FRV | 2241 | Purchase of Electronic Document and Records Management System (EDRMS) | Emergencies and Safety | Records Management | Procurement and implementation of a new electronic records management system to replace eDocs (DocCentral). | Closed - Completed | Compliance (Non Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) | 2022-01-31 | MFB Project Management Framework (PME) | 2013-07-01 | 2014-07-09 |  | 2014-07-09 | 60737 |  | 2014-07-09 |  | 2017-06-30 | 2022-01-31 | 1200000 | 2327490 | Amber | Amber | Amber | Amber | Amber | The project reported an Amber status due to a solution implementation issue. Data migration activities are now complete and all sites have gone live. Project closure and lessons learnt documentation is being drafted to close out the project.
Q3 21-22 | Ports Victoria | PortsVic | 2262 | Vessel Traffic Services Systems Upgrade | Transport and Vehicles | Communication | Replacement of existing / ageing Vessel Traffic Services Information Communications Technology systems with a focus on upgraded system integration, redundancy and disaster recovery. Affected systems include radio, telephony, radar, vessel AIS (Automatic Identification System), vessel DUKC (Dynamic Under-Keel Clearance), CCTV and Met Ocean (tide, wind, wave and weather). | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | VPCM (PMBoK) | 2015-12-03 | 2015-12-03 | 2018-11-30 | 2018-12-10 | 0 |  | 2019-01-10 |  | 2020-12-18 | 2022-06-30 | 9078548 |  | Green | Green | Green | Green | Green | All equipment and refurbishment works are complete. Network issues have been resolved. Final radar cutover and Final Site Acceptance testing have been delayed to the next reporting period, due to Covid border restrictions.
Q3 21-22 | Public Record Office Victoria | PROV | 2263 | Digital Archive Program | Government and Economy | Content Management,Document Management ,Records Management | This program is progressively renewing and replacing Public Record Office Victoria's digital archive infrastructure. The program is expected to enable better access to PROV records while facilitating long term preservation and reducing operating costs. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2015-07-01 | 2015-07-01 |  | 2015-07-01 | 200000 | 0 | 2015-07-01 |  | 2018-06-30 | 2022-09-05 | 4062000 | 5617000 | Amber | Amber | Amber | Amber | Amber | Performance issues with the warehouse management system database have been addressed. An interim solution for repository move functionality has been developed; that will allow transfer of records to the SLV facility in Ballarat (BOSS II). A revised timeframe for for regional implementation has been.
Q3 21-22 | Royal Victorian Eye and Ear Hospital | Eye & Ear | 2280 | ICT Redevelopment Stage 3 Hardware Tender and Implementation | Health | Systems Management | Fit-out of new IT infrastructure to support hospital redevelopment objectives | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2013-07-01 | 2014-06-30 |  | 2014-06-30 | 0 |  | 2014-06-30 |  | 2018-12-31 | 2022-10-03 | 0 | 1315265 | Green | Green | Green | Green | Green | Purchasing and Commissioning of Hardware continues and remains a focus as we continue to experience long lead times for items such as CISCO Switches.
Q3 21-22 | Department of Transport | DOT | 2291 | ICT/ITS Infrastructure Transformation Program (Switch Program) | Transport and Vehicles | Systems Management,Security Management | Purpose of this project is to establish commercial arrangements for, and the transition into, new data centre hosting and managed infrastructure services to support DOT ( VicRoads) current and future ICT and Intelligent Transport System requirements. | Closed - Completed | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2022-02-28 | PRINCE2 | 2016-05-09 | 2017-08-17 |  | 2017-08-17 | 1250634 |  | 2017-08-17 |  | 2020-02-28 | 2022-02-25 | 7649366 | 19464718 | Red | Green | Green | Green | Green | Project Completed.
Q3 21-22 | Northern Health | NH | 2411 | EMR Program | Health | Analyses and Statistics ,Collaboration ,Communication,Organisational Management ,Records Management | Implementation of an Electronic Medical Record at Northern Health including all sites | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2016-10-18 | 2018-05-01 | 2021-02-01 | 2021-02-02 | 0 | 4300000 | 2021-02-08 |  | 2022-12-18 | 2023-04-03 | 38700000 | 46024365 | Green | Amber | Red | Amber | Amber | The project is amber due to the level of resourcing issues the project is encountering. Mitigation strategies are in place
Q3 21-22 | Court Services Victoria | CSV | 2452 | Courts Case Management System | Law and Justice | Tracking and Workflow | The CMS Project aims to procure and implement a new case management system for Magistrates’ Court and Children’s Court. The system will enable better information sharing between courts and other agencies, and provide better access to case information | Delivery | Efficiency/Productivity (Non Financial) |  | Project Management Excellence (PME) | 2016-07-01 | 2017-05-02 |  | 2017-05-02 | 0 |  | 2017-07-01 |  | 2022-06-30 | 2022-10-31 | 89200000 | 89233000 | Green | Amber | Red | Red | Red | The overall project status remains red. Solution build has been delayed due to COVID, market resourcing constraints, and other factors. The project is progressing with delivering the Business Case scope, as well as replanning for the current delay.
Q3 21-22 | Department of Families, Fairness and Housing | DFFH | 2462 | Family Safety Victoria Central Information Point | Community Services | Data Management,Knowledge Management ,Records Management | Project will establish an information sharing platform and service that consolidates and provides timely risk relevant information from partner departments and agencies to frontline workers to support family violence risk assessment and management. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial), Social Improvement (Non Financial) |  | Agile | 2017-03-13 | 2018-01-29 | 2017-06-30 | 2017-07-03 | 0 |  | 2017-07-04 |  | 2019-06-30 | 2022-06-30 | 7199594 | 91422489 | Amber | Amber | Green | Green | Green | Stages 1, 2, 3 and 4 of the project are completed and system is operational. Work is continuing on Stage 5, which is scheduled for completion by 30 June 2022. Stage 5 will complete partner agency system integration and support usability enhancements to meet increased demand as The Orange Door Network continues to rollout across the State and the Risk Assessment and Management Panels are onboarded. Project is progressing to cost and schedule.
Q3 21-22 | North East Region Water Corporation | NE Water | 2481 | Customer Billing System | Environment and Water | Customer Relationship Management,Knowledge Management ,Management of Process | Procure a replacement for the current Billing system and implement a new self service portal for customers. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Vic Govt PM Framework | 2017-07-01 | 2017-12-31 | 2021-04-16 | 2021-04-16 | 0 | 1186673 | 2021-04-19 |  | 2022-05-31 | 2022-06-20 | 8597916 | 12500000 |  | Amber | Amber | Amber | Amber | In December 2021 Board members requested a review which was presented 7th February. Board agreed to extend the project until June 2022. All components now delivered. Testing remains. Subsequent request to allow additional test cycle is being prepared for Board consideration this month.
Q3 21-22 | Victorian Electoral Commission | VEC | 2497 | EMS2 | Government and Economy | Development and Integration | The project will replace legacy Election Management System with a more robust, secure and integrated system that is in line with VEC technology strategy to enable a more efficient management of the Victorian election processes | Delivery | Efficiency/Productivity (Non Financial), Reputation (Non Financial) |  | Agile | 2017-03-01 | 2017-05-01 |  | 2017-05-01 | 50000 |  | 2017-05-01 |  | 2018-06-30 | 2022-04-29 | 2000000 | 1752344 | Red | Amber | Green | Green | Green | EMS has been successfully released into production and has entered hyper-care period until the end of April. A full program closure report including lessons learned will be presented at the end of April and will signify the final closure of the program.
Q3 21-22 | Department of Environment, Land, Water and Planning | DELWP | 2522 | Fuel Management System (FMS) | Emergencies and Safety | Data Management,Development and Integration ,Management of Process ,Reporting ,Assets/Materials Management,Knowledge Management | This project will deliver a Fuel Management System (FMS), a single, intuitive and flexible platform for delivering the multi-agency fuel management program in Victoria, for Forest Fire Management Victoria (FFMVic) and Country Fire Authority (CFA). | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2015-05-11 | 2015-05-12 |  | 2015-05-12 | 67500 |  | 2015-07-01 |  | 2018-12-31 | 2022-06-30 | 1900000 | 3189865 | Green | Green | Green | Green | Green | The project is on track to be delivered on budget and on schedule.
Q3 21-22 | Goulburn Valley Region Water Corporation | GVR Water | 2524 | Asset Management Information System Replacement Project | Environment and Water | Assets/Materials Management | Implement mature, industry proven Asset Management Information and Geographic Information Systems meeting the requirements of the organisation, delivering improvements and efficiencies not previously achievable with the current solutions | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Internal GVW Project Management Methodology | 2016-11-23 | 2017-12-08 |  | 2017-12-08 | 50000 |  | 2018-01-02 |  | 2021-03-31 | 2024-06-30 | 2405000 | 2429308 | Green | Green | Green | Green | Green | Project is currently engaging in discussions with the preferred RFT Tenderer.
Q3 21-22 | Goulburn Valley Region Water Corporation | GVR Water | 2525 | Intelligent Metering | Environment and Water | Assets/Materials Management | Installation of intelligent meters in four towns to provide data to target peak demand reduction, leading to: 1 . A permanent reduction in peak day water usage through leakage reduction. 2. Deferral of water network capacity upgrade projects | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Social Improvement (Non Financial), Workforce Satisfaction (Non Financial) |  | GVW Internal Project Management Methodology | 2017-07-01 | 2018-03-02 |  | 2018-03-02 | 10000 |  | 2018-07-31 |  | 2021-06-30 | 2023-05-31 | 1790000 | 4380000 | Green | Green | Green | Green | Green | Tracking OK
Q3 21-22 | Independent Broad-based Anti-corruption Commission | IBAC | 2526 | Case Management System | Law and Justice | Tracking and Workflow | The project will deliver a comprehensive case management system to manage complaints and investigations from receipt to conclusion, improving information sharing between business areas for investigations and increase timely response to complaints. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2015-07-14 | 2016-05-02 |  | 2016-05-02 | 74518 |  | 2017-12-21 |  | 2018-12-31 | 2022-06-30 | 1300000 | 1985000 | Amber | Amber | Green | Amber | Amber | The project is at a critical point as core development and configuration comes to an end, before moving into user acceptance testing. Resources, processes, roles and responsibilities are being primed and prepared ahead of testing.
Q3 21-22 | Department of Environment, Land, Water and Planning | DELWP | 2561 | Digital Cadastre Modernisation Project | Property and Planning | Knowledge Management ,Data Management | Digital Cadastre Modernisation will bring the authoritative map of Victoria’s property boundaries further into the digital age, ensuring that one of the State’s most important datasets is accurate, useful, and easy to maintain. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2018-02-12 | 2018-09-30 |  | 2018-09-30 | 0 | 200000 | 2018-11-16 |  | 2023-12-30 | 2023-12-30 | 0 | 47000000 | Red | Red | Red | Green | Green | The project is progressing as planned, with early data now released and spatial improvements being achieved.
Q3 21-22 | Eastern Health | EH | 2563 | Single Billing System Project | Health | Data Management,Development and Integration ,Financial Management | Deliver a single billing system to replace 17 legacy systems used for patient accounts billing for Eastern Health, resulting in uplift in revenue, improved customer experience of billing and collection processes and reduction in costs | Delivery | Increased Revenue (Financial) |  | PRINCE2 | 2017-07-01 | 2018-02-04 | 2018-03-28 | 2018-03-28 | 508851 |  | 2018-04-17 |  | 2020-06-30 | 2022-06-30 | 6839088 | 11742903 | Red | Green | Green | Green | Green | Approval of the revised project plan has been received which has enabled the project to retain the status of green.
Q3 21-22 | Coliban Region Water Corporation | Coliban Water | 2567 | Digital Customer Metering Program | Environment and Water | Data Management,Assets/Materials Management,Business Intelligence,Reporting | To automate manual meter reading to improve business intelligence, asset management and network planning to enable benefits for customers. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial) |  | PMBoK | 2016-01-18 | 2017-07-25 |  | 2017-07-25 | 72000 |  | 2017-07-25 |  | 2023-06-30 |  | 5448000 | 9001000 | Green | Green | Green | Green | Green | The program remains on target and planned benefits are still achievable.
Q3 21-22 | Westernport Region Water Corporation | WPR Water | 2568 | Business Transformation Project | Government and Economy | Systems Management,Financial Management,Human Capital / Workforce Management ,Human Resources,Reporting ,Supply Chain Management | The Project comprises 2 parts: 1st involves transitioning to a new ICT Managed Services Provider to address service continuity issues; 2nd involves replacing legacy IT systems for Finance, HR, Payroll and Utility Billing to address operational risks. | Closed - Terminated | Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) | 2022-02-22 | PRINCE2 | 2017-07-01 | 2020-06-30 | 2018-01-30 | 2018-03-19 | 2089200 | 135000 | 2018-05-07 |  | 2020-06-30 | 2022-02-22 | 1954200 | 3844465 | Amber | Amber | Amber | Amber | Amber | Payroll and HRIS implementations complete. Remaining two modules of HRIS will be considered next regulatory period. Finance system implementation remains suspended. Alternative option finance system investment decision developed, tabled and supported by the Board.
Q3 21-22 | South West Alliance of Rural Health | SWARH | 2597 | Barwon Health Optima Rostering Project | Health | Management of Process ,Human Capital / Workforce Management ,Human Resources | This project will deliver a Rostering and Time & Attendance system to automate staff rostering processes, improving workforce utilisation, accuracy of resource allocation and delivery of patient care. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2017-07-19 | 2018-05-31 |  | 2018-06-08 | 110640 |  | 2018-07-11 |  | 2019-12-31 | 2022-06-30 | 3443281 |  | Red | Red | Red | Red | Amber | Pilot 1 commenced successfully in March and has been running smoothly through the first 2 pay cycles. Project team is planning for Pilot 2 rollout. The project is Amber due to risks identified with the Pilot 2 implementation likely to cause delays in the project schedule. The Pilot and lessons learnt will inform the business case for the next phase.
Q3 21-22 | Department of Health | DH | 2603 | Regulatory Licensing and Registration Platform | Health | Systems Management | Replacement of the Radiation Registration and Licensing (RELIC) system utilised by the Environmental Health Regulation & Compliance Unit to administer their Act & legislation. Development of a platform configurable for other regulatory units. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Agile | 2017-10-20 | 2017-11-05 |  | 2017-11-05 | 0 |  | 2017-11-06 |  | 2019-06-30 | 2022-06-30 | 2400000 | 1911930 | Green | Green | Green | Green | Green | Project is progressing to cost and revised schedule and will close on 30 June.
Q3 21-22 | Hume Rural Health Alliance | HRHA | 2623 | West Hume Patient Administration System (PAS) | Health | Data Management,Management of Process ,Records Management ,Tracking and Workflow,Knowledge Management ,Visualisation | The project will deliver a new Patient Administration System across 5 health services, improving information sharing within the West Hume Region, improved information security and system availability to support timely provision of healthcare. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2018-08-01 | 2018-12-31 | 2019-12-06 | 2019-12-06 | 250000 | 62000 | 2020-03-20 |  | 2021-09-30 | 2023-04-30 | 4532536 | 5539631 | Green | Green | Amber | Red | Red | A revised end date is yet to be approved by Steering Committee and Control Board. Approvals are pending and we anticipate to change the end date in the next quarter's report.
Q3 21-22 | Hume Rural Health Alliance | HRHA | 2626 | Albury Wodonga Health Patient Administration System (PAS) | Health | Organisational Management ,Business Intelligence,Data Management,Financial Management,Management of Process ,Records Management ,Security Management ,Tracking and Workflow,Routing and Scheduling | The project will replace the current PAS to deliver a common patient database to standardise patient administration workflows and reporting across AWH, remove risks of multiple concurrent patient identifiers, and improve patient records management | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial) |  | PRINCE2 | 2018-08-01 | 2020-08-31 |  | 2020-08-31 | 1700000 | 630000 | 2020-08-31 |  | 2022-03-31 | 2022-12-31 | 250000 | 6970000 | Green | Red | Red | Red | Red | Solution vendor has advised that there will be delays in product readiness due to the number of defects they have found in testing. Solution vendor is reviewing effort estimates for remaining work.
Q3 21-22 | Transport Accident Commission | TAC | 2630 | Data Analytics | Transport and Vehicles | Business Intelligence | Implement an Enterprise Data Warehouse (EDW) that will contain the single source of truth for TAC's data. The program will also implement enterprise data policies and governance to ensure that data is of a high quality. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Reputation (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2018-06-01 | 2018-06-30 |  | 2018-07-03 | 0 | 1195727 | 2018-07-03 |  | 2019-11-30 | 2022-07-31 | 5700000 | 20604273 | Green | Green | Green | Green | Amber | Overall the program continues to deliver as planned across data governance and people change streams. Asset delivery continues to experience challenges in the translation of business rules into the new warehouse as a result the schedule with the Analytics vendor has slipped beyond tolerances moving the schedule to red and overall program to Amber mitigation plans are developed and next steps to bring delivery back on track are underway.
Q3 21-22 | Ambulance Victoria | AVS | 2666 | Enterprise Resource Planning Project | Health | Human Capital / Workforce Management | The ERP project will deliver a new integrated enterprise platform to manage rosters and claims. This will automate and streamline processes to enhance and enable effective resource management to meet the demand of AV's services | Postponed | Cost Reduction (Financial), Increased Quality (Non Financial) | 2021-12-31 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2018-02-01 | 2019-06-30 | 2019-08-20 | 2019-08-20 | 320000 | 343634 | 2019-08-26 |  | 2022-06-30 |  | 10137107 | 9486636 | Green | Amber | Amber | Red | Red | This project continues to be reported as red status reflecting an ongoing 'pause' whilst the review findings are considered and a business case with recommended path forward to be considered by Ambulance Victoria Board in Quarter 4 2022
Q3 21-22 | Ambulance Victoria | AVS | 2667 | Predictive Analytics Capability | Health | Business Intelligence,Analyses and Statistics ,Knowledge Discovery ,Reporting | Establish organisational real time decision support along with predictive analytics capability. The introduction of modern data analysis will ensure critical information can be provided to paramedics when they need it. | Postponed | Efficiency/Productivity (Non Financial) | 2021-12-31 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2018-04-10 | 2018-11-25 | 2019-05-27 | 2019-05-27 | 282000 | 267500 | 2019-07-17 |  | 2021-06-30 | 2021-12-31 | 12018000 | 8810721 | Red | Red | Red | Red | Red | This project continues to be reported as red status, reflecting an ongoing pause, whilst review findings are considered. A recommended pathway forward will be considered by the Ambulance Victoria Board in Q4, FY22.
Q3 21-22 | Department of Education and Training | DET | 2690 | Asset Information Management Systems (AIMS) | Education | Content Management,Data Management,Assets/Materials Management | This will deliver a new Asset Information Management System to manage schools land and building assets enabling evidence-based decision making at both DET Corporate & School level and support attestation to Asset Management Accountability Framework. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2017-08-01 | 2019-07-31 | 2019-09-30 | 2019-09-30 | 2963222 | 2562342 | 2019-10-01 |  | 2022-09-30 | 2022-11-30 | 12956778 | 16420894 | Green | Green | Green | Green | Green | The AIMS school deployment for 2021 has been completed with 167 schools deployed to AIMS. Despite pressure from increased community transmission of COVID19 at the start of 2022, schools remain positive concerning the deployment of AIMS with relatively few withdrawal requests. The AIMS school deployment continues. As at the end of March 2022, a further 250 schools have been trained in AIMS. The full deployment by the end of November 2022 remains on track. The AIMS Investment Model has successfully gone live.
Q3 21-22 | Department of Environment, Land, Water and Planning | DELWP | 2730 | VGV Going Digital Project | Property and Planning | Management of Process ,Customer Initiated Assistance,Data Management,Records Management ,Reporting ,Knowledge Management ,Tracking and Workflow | Valuer-General Victoria Go Digital project will transfer paper-based valuation requests and records into a digital system to reduce the reliance on paper-based systems and to improve the accuracy of valuation data. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2017-06-30 | 2017-09-30 |  | 2017-11-30 | 88000 |  | 2018-11-30 |  | 2019-09-30 | 2022-06-30 | 518841 | 2529250 | Amber | Amber | Amber | Green | Green | The project reported a Green status for this period.
Q3 21-22 | Alfred Health | ALFRED | 2754 | Implement eTQC Phase Two program to upgrade clinical information systems to significantly improve electronic timely quality care for our patients | Health | Collaboration ,Communication,Data Management,Knowledge Discovery ,Management of Process ,Reporting ,Tracking and Workflow | Development and implementation of Phase Two of the electronic-Timely Quality Care (eTQC) project that optimises products introduced in phase 1 and explands EMR scope to improve clinical real-time data capture management and patient care services | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2019-01-01 | 2019-06-30 |  | 2019-07-01 | 0 | 5051100 | 2019-07-01 |  | 2020-12-31 | 2022-06-30 | 14695182 |  | Green | Green | Green | Green | Amber | Project has been delayed due to COVID-19 and vendor development delays. Project closure now planned for Q4 2021/2022.
Q3 21-22 | Department of Health | DH | 2770 | Windows 10 Upgrade | Community Services | Systems Management | To upgrade the department's standard operating environment on desktops and laptops to Windows 10 to leverage the wider breadth of modern IT service offerings. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2019-03-01 | 2019-06-15 |  | 2019-06-15 | 250000 | 250000 | 2019-07-01 |  | 2020-06-30 | 2022-06-30 | 4672022 | 4828097 | Amber | Amber | Amber | Amber | Green | Project has re-commenced and progressing to revised cost and schedule.
Q3 21-22 | Hume Rural Health Alliance | HRHA | 2783 | Central Hume Partnership PAS Replacement | Health | Data Management,Knowledge Management ,Management of Process ,Records Management ,Tracking and Workflow,Visualisation | The project will deliver a new Patient Administration System across 7 health services, improving information sharing within the Central Hume Partnership, improved information security and system availability to support timely provision of healthcare. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-08-05 | 2019-08-30 | 2019-08-05 | 2019-08-30 | 2400000 | 75000 | 2019-10-21 |  | 2021-06-30 | 2022-09-30 | 2200000 | 5417462 | Red | Red | Red | Red | Red | Project is continuing to progress with project activities while in parallel the delays in finalising a program level plan are being addressed with all senior stakeholders
Q3 21-22 | Victorian Rail Track | VicTrack | 2797 | Transport and Government Secure Network (TGSN) | Transport and Vehicles | Routing and Scheduling | To upgrade VicTrack's fixed Telecommunications network. The current network has various elements which are obsolete or becoming obsolete there is lack of spare equiments and reduced vendor support. 3 years project to deliver new technology. | Delivery | Risk Reduction (Non Financial) |  | VicTrack PMF | 2019-06-03 | 2019-10-01 | 2020-03-02 | 2020-03-02 | 0 | 0 | 2020-03-02 |  | 2023-06-30 |  | 69000000 |  | Green | Green | Green | Green | Amber | The project is tracking well on service migrations to TGSN. However some delays were experienced due to resourcing constraints. The project team is working with the vendor to explore options to rectify the delay.
Q3 21-22 | Department of Justice and Community Safety | DJCS | 2799 | Network Uplift Program | Law and Justice | Systems Management | To get all DJCS sites on the same comparable level of capability to support Win 10 roll-out and to apply the same service delivery principles and services to all sites. Includes centralisation of file and print services and provision of WIFI. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Project Management Excellence | 2018-11-01 | 2019-05-17 |  | 2019-05-17 | 0 |  | 2019-05-17 |  | 2021-06-30 | 2022-06-30 | 6148000 | 8938918 | Green | Green | Green | Green | Green | 12 of 16 correctional site refreshes complete. Delivery has been affected by COVID-19 with slow delivery of network equipment and workplace restrictions limiting ability to implement. Work is continuing on multiple sites simultaneously to try and minimize the time impact.
Q3 21-22 | Melbourne Water | MELB Water | 2801 | Image processing and analytics | Environment and Water | Assets/Materials Management,Analyses and Statistics | This project will implement image processing and analytics for sewerage assets, which will efficiently analyse data captured to assist with managing risks associated with failure mechanisms such as corrosion within the sewer transfer network. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2019-04-17 | 2019-08-20 | 2020-10-15 | 2020-11-17 | 0 |  | 2020-11-17 |  | 2021-10-06 | 2022-04-27 | 1459302 | 1229512 | Green | Green | Green | Green | Green | Qualitative testing is in progress. The financial forecast now includes the extra cost for labour due to extending timelines, this is still within approved budget.
Q3 21-22 | Department of Health | DH | 2812 | Oracle Financials Upgrade | Community Services | Financial Management | The project will deliver an Oracle upgrade to the latest release of Oracle Cloud platform including the Chart of Accounts rationalisation and standard business processes to provide DH and DFFH with an efficient financial and procurement system. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-05-20 | 2019-12-31 | 2019-11-29 | 2019-11-29 | 1885550 | 964956 | 2021-05-05 |  | 2022-12-30 |  | 25475450 | 28550189 |  |  |  | Amber | Amber | Program is Amber as delivery approach and plan to be reviewed to align with the whole of Victorian Government Common Corporate Platform initiatives. On completion of review, schedule and cost will be updated to reflect any future approved changes.
Q3 21-22 | Department of Education and Training | DET | 2819 | Kindergarten Information Management System (KIMS) Reform | Education | Development and Integration ,Financial Management | The project will replace the kindergarten funding system with a Cloud based technology platform to ensure ongoing functionality, rapid implementation and support for the Education State Early Childhood Reform Plan’s key reforms. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2018-04-26 | 2019-06-28 | 2019-06-28 | 2019-06-28 | 0 | 787836 | 2019-06-28 |  | 2020-03-27 | 2022-12-31 | 15637064 | 21342704 | Green | Amber | Amber | Green | Green | The annual Confirmations function was enabled on Tuesday 18 Jan and Service Providers can begin submitting their Annual Confirmations into KIMS, including the 3YO enrolment and funding functionality. The Early Years Management (EYM) development pieces of work continue to progress. The MuleSoft Integration pieces with SAMS2 application continue to progress
Q3 21-22 | Yarra Valley Water | YV Water | 2821 | Operational Historian | Environment and Water | Data Management | Acquisition, storage, analysis, and presentation of large volumes of time series data – allowing it to be combined with data from other core systems for analysis and improved decision making. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2018-11-01 | 2019-08-30 | 2019-12-27 | 2019-12-27 | 240000 | 300000 | 2019-12-30 | 2020-01-01 | 2021-12-30 | 2023-11-30 | 4778000 | 5786280 | Amber | Amber | Amber | Amber | Green | Project re-named from Enterprise Historian to Operational Historian. Project Manager onboarded and project recommenced March 2022. GTS -Vendor SOW undergoing revision and moving into the final stages. Project team being reformed and historical work being reviewed and revalidated. Draft project Schedule and estimates developed.
Q3 21-22 | Yarra Valley Water | YV Water | 2822 | Network Communications and IoT Device Management | Environment and Water | Assets/Materials Management | IoT device telecommunications services and device management platform. | Delivery | Cost Reduction (Financial) |  | PRINCE2 | 2019-05-01 | 2020-01-31 | 2020-10-14 | 2020-10-14 | 350000 | 1300000 | 2020-10-19 |  | 2022-06-30 | 2022-12-31 | 3715000 | 3715059 | Green | Green | Green | Green | Green | Completed system integration testing for Telstra communications and the Nokia Platform. Working with Solution Architect on integration processes for on-boarding new Digital Meters.
Q3 21-22 | South East Water | SE Water | 2823 | Digital Utility Core Capability | Environment and Water | Customer Relationship Management,Data Management,Development and Integration ,Reporting | Delivery of end to end business processes across meter management, billing and alerts & alarms. This will enable customer data to be exposed via the portal and internal CSO views as well as monitoring meter and water usage behaviour. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Agile | 2019-06-10 | 2019-06-20 |  | 2019-06-21 | 25000 |  | 2019-06-24 |  | 2020-02-28 | 2023-11-03 | 0 | 19000000 | Green | Green | Green | Green | Green | Business design for multiple new processes has been completed and system scope and technical design is now underway.
Q3 21-22 | Department of Transport | DOT | 2824 | Rail Operational Performance Project (ROPP) | Transport and Vehicles | Systems Management,Data Management | The objective of the new Rail Operational Performance Project (ROPP) solution is to provide an efficient, future proof system that enables compliance with the MR4 contract and supports the enterprise approach to rationalise the data management proces | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | PTV Investment Lifecycle | 2018-07-02 | 2019-06-30 | 2021-05-11 | 2021-05-11 | 2200000 | 3639698 | 2021-05-12 |  | 2022-04-08 | 2022-08-31 | 3560302 |  |  | Amber | Amber | Amber | Green | Technical release 3 is on track for April delivery. Variation negotiation including ROPP Support cost is in progress with Telstra Purple. Revised Project schedule with August 2022 delivery date was approved at PSC in March 2022. Procurement activities to identify security and performance testing and external audit is scheduled to start by end of April 2022.
Q3 21-22 | Department of Transport | DOT | 2825 | Automated Vehicle Monitoring Replacement (AVMR) | Transport and Vehicles | Analyses and Statistics ,Assets/Materials Management,Systems Management,Communication | The tram AVM system is used for the preparation management and monitoring of all tram services across the tram network. It is used to communicate with drivers and monitor and record tram location and status. | Initiated |  |  | PTV Investment Lifecycle | 2018-07-02 | 2020-06-30 | 2022-06-30 |  | 2800000 | 4919000 | [11 empty] | Development of scope and costs to undertake a cohesive Program Plan and AVM Functionality study are progressing well. Both of these activities are on track for completion by 30 June 2022.
Q3 21-22 | Department of Justice and Community Safety | DJCS | 2832 | Practice Management System | Law and Justice | Tracking and Workflow | This project will replace the existing VGSO's Practice Management System to provide streamlined processes improved information sharing and increased data capture. | Delivery | Cost Avoidance (Financial), Increased Revenue (Financial) |  | Project Management Excellence | 2018-08-31 | 2018-09-07 |  | 2018-09-07 | 0 |  | 2019-09-30 |  | 2021-04-01 | 2022-12-01 | 1400000 | 1500000 | Green | Green | Green | Green | Amber | Project Stream 1 delivered on time and Project Stream 2 delivery date changed. The revised delivery date is due to the impact of COVID-19 on available resources with priorities needing to change to support staff during this period.
Q3 21-22 | Department of Premier and Cabinet | DPC | 2841 | ACHRIS Phase 3 – Amalgamation of the CHMP database | Culture, Sport and Recreation | Management of Process | ACHRIS Phase 3 will integrate critical business systems to deliver a holistic approach to better manage and protect Aboriginal cultural heritage. The new system will deliver business efficiencies and reduce statutory red tape. | Postponed | Compliance (Non Financial), Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) | 2021-06-30 | Agile | 2019-07-01 | 2022-06-30 | 2019-10-14 | 2019-10-15 | 0 |  | 2019-10-15 |  | 2022-06-30 |  | 1231413 |  | Amber | Amber | Amber | Amber | Amber | The project is still postponed whilst we wait on the budget outcome which will provide a clear path beyond this financial year as the project requires multiple year funding to proceed.
Q3 21-22 | Department of Justice and Community Safety | DJCS | 2851 | Digital Radio Upgrade Program - Stage 2 | Emergencies and Safety | Communication | This Program will transition Ambulance Victoria's (AV) regional comms off analogue radio system onto the State’s shared digital network and replace AV's regional radio fleet to provide secure comms and improve community safety and health outcomes. | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Project Management Excellence | 2019-07-01 | 2019-07-02 |  | 2019-07-02 | 0 |  | 2019-07-03 |  | 2023-06-30 | 2024-12-30 | 70378000 |  | Amber | Green | Green | Green | Green | The project is tracking well against scope budget and schedule.
Q3 21-22 | Victoria Legal Aid | VLA | 2852 | Digital Legal Aid Program | Law and Justice | Management of Process | VLA will leverage technology and data to significantly improve client service, productivity and access to justice. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2018-07-01 | 2019-02-19 |  | 2019-02-20 | 0 |  | 2019-02-22 | 2022-01-01 | 2021-07-30 | 2023-12-31 | 14500000 | 5850000 | Amber | Amber | Green | Green | Green | Digital Service Record pilot commenced in late November 2021 and continues to be on track in Q3. Our Legal Help Triage tool project was finalised in January 2022. Website redevelopment is due to launch in mid May 2022. Plans finalised and VLA Board approval received to extend program end date to 31 December 2023. This report is specific to the extension period from Jan 22 - Dec 23 including budget, benefits and schedule.
Q3 21-22 | Department of Justice and Community Safety | DJCS | 2855 | Serious Offenders Reform Program - ICT Program | Law and Justice | Development and Integration | The ICT Program supports the upgrade of existing systems to support changes to legislation, policy and business processes as part of the serious offender reform program. | Postponed | Compliance (Non Financial), Efficiency/Productivity (Non Financial) | 2021-10-25 | Project Management Excellence | 2017-04-01 | 2017-11-30 |  | 2017-12-01 | 1375000 |  | 2017-12-01 |  | 2020-05-31 | 2021-11-29 | 11830000 | 16718486 | Red | Red | Red | Red | Red | The final component of the multi-year SORP ICT program has been placed on hold due to technical and schedule uncertainty. A critical evaluation of the vendor's revised plan has been undertaken by the Department and consideration of how to deliver the final component is underway.
Q3 21-22 | Western Health | WH | 2868 | Electronic Medical Record (EMR) Phase 2 | Health | Records Management | This project represents the next phase of the EMR at Western Health (WH) on its path towards bringing it to a fully digital hospital which is expected to provide improved efficiency and quality of care across the continuum of the organisation. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2019-05-29 | 2020-02-03 | 2019-07-05 | 2019-07-05 | 0 |  | 2021-02-22 |  | 2025-12-31 | 2026-06-30 | 64400000 | 69447738 | Green | Green | Red | Green | Amber | Vendor resourcing constraints have reoccurred during this reporting period. Quarterly status changed to Amber .
Q3 21-22 | Western Health | WH | 2869 | Active Directory (AD) Seperation | Health | Organisational Management ,Security Management | Western Health (WH) shares the same Active Directory (AD) domain with Melbourne and Northern Health services. The objective is to create a WH AD, reducing potential cyber security risks and providing WH its own AD environment | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2019-05-06 | 2019-11-15 | 2019-09-30 | 2019-12-06 | 0 |  | 2020-06-01 |  | 2021-12-23 | 2022-08-28 | 1876000 | 2756677 | Green | Green | Green | Green | Green | The Project is currently in execution stage.
Q3 21-22 | Ambulance Victoria | AVS | 2877 | Connected Paramedic | Health | Communication,Collaboration ,Knowledge Management | The Connected Paramedic Program will introduce digital connectivity to paramedics and integrate internal systems, allowing the provision of digital tools for paramedics to connect and share data within AV and between AV and the broader health system. | Postponed |  | 2020-07-01 | PMBoK | 2019-07-01 | 2021-06-30 | 2020-06-30 |  | 7700000 | 827766 |  |  |  |  | 0 | [6 empty] | Project remains on hold - pending review in FY23
Q3 21-22 | CenITex | CenITex | 2882 | Regional Site Performance & Resilience Improvement | Government and Economy | Assets/Materials Management | To improve the performance and reliability of network infrastructure to support a modern and agile public-sector workforce in regional Victoria | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2019-07-04 | 2019-07-25 | 2019-09-03 | 2019-09-03 | 0 | 0 | 2019-09-03 |  | 2020-06-30 | 2022-06-30 | 8680000 | 8680000 | Amber | Amber | Amber | Green | Green | 97 of 98 sites are complete.
Q3 21-22 | Peter MacCallum Cancer Centre | Peter MAC | 2884 | People Systems | Health | Human Capital / Workforce Management ,Human Resources | The People Systems Program will deliver HRIS and Payroll systems to increase efficiency and improve data security and integrity by eliminating paper timesheets and manual processes. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2019-07-01 | 2019-11-30 | 2021-06-30 | 2021-06-30 | 40000 | 377350 | 2021-07-19 |  | 2022-06-30 | 2022-08-31 | 2572000 |  |  |  | Green | Green | Green | Project has entered the testing phase and is in UAT.
Q3 21-22 | Department of Education and Training | DET | 2886 | FSD-Oracle Cloud Program | Education | Analyses and Statistics ,Systems Management,Financial Management | The project will deliver integrated Cloud applications to meet WoVG Finance Statement of Directions improving information consolidation and analysis across government utilising common application tools, reducing ongoing maintenance and costs. | Delivery | Compliance (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-07-29 | 2020-06-30 | 2020-09-30 | 2020-11-02 | 0 | 3391959 | 2020-11-02 |  | 2021-11-01 | 2023-03-31 | 2861041 | 5324616 | Amber | Red | Red | Amber | Green | The program is highly focussed on the delivery of Oracle Procurement Cloud - Source to Contract and Purchase to Pay modules. Delivery is on track for implementation in May 2022. Post Oracle Procurement Cloud implementation, the project will be better positioned to map and confirm the remaining program milestones and timelines for Oracle ERP Finance and Chart of Accounts.
Q3 21-22 | Barwon Region Water Corporation | BR Water | 2890 | C1220 Sherwin 4CX Project | Environment and Water | Management of Process | Internal development of key line of business applications to improve customer experience (CX) including:- Land Development, Water & Sewer Connections, and Trade Waste. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2018-11-01 | 2019-04-01 |  | 2019-06-27 | 520000 |  | 2019-06-27 |  | 2020-11-28 | 2022-05-31 | 1846000 | 1896000 | Green | Green | Green | Green | Green | Incremental functionality is still being progressively deployed as soon as possible.
Q3 21-22 | Essential Services Commission | ESC | 2899 | VEU system development based on Dynamics 365 platform | Environment and Water | Analyses and Statistics ,Customer Relationship Management,Development and Integration | Develop and configure the new Victorian Energy Upgrades (VEU) System on Dynamics 365 platform according to the detailed business requirements utilising the Microsoft Azure Cloud services and Office 365 ecosystem. | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial), Eco Improvement (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2018-04-16 | 2019-09-26 |  | 2019-09-26 | 48822 |  | 2019-10-28 |  | 2020-10-30 | 2022-06-30 | 2291878 | 2606056 | Red | Red | Green | Green | Amber | The project is 90% complete and is on amber status against the re-baselined scope. The re-baselined scope is called "project Phase 1" . A project Phase 2 is required to build all remaining functionality including new Government requirements for the VEU program and detailed workflow customisations. The contract with the current vendor is ending and the project is being rescoped and other delivery options are being sought.
Q3 21-22 | Bendigo Kangan Institute of TAFE | BKI TAFE | 2903 | Student Journey Transformation | Education | Customer Relationship Management,Data Management,Development and Integration ,Records Management ,Reporting | The program will deliver capability and user experience improvements across the end-to-end student lifecycle. The program is necessary to transform people, process and systems from a highly manual environment, using complex and out of date systems. | Delivery | Cost Reduction (Financial), Increased Revenue (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-01-07 | 2019-12-20 |  | 2019-12-20 | 2174000 | 1700000 | 2020-01-06 |  | 2022-09-30 | 2023-05-31 | 1966000 | 29228000 | Green | Red | Green | Green | Green | Project is tracking green overall.
Q3 21-22 | Department of Justice and Community Safety | DJCS | 2905 | DJR Legacy Server Consolidation | Law and Justice | Systems Management | The Legacy Server Consolidation program will be responsible for the upgrade of all Windows 2003/2008 & Solaris 8/9 servers. The legacy hardware poses a high risk and this project aims to ensure a compliant and secure system. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Project Management Excellence | 2019-07-01 | 2019-09-30 |  | 2019-09-30 | 0 |  | 2019-10-01 |  | 2020-12-31 | 2022-05-31 | 1894400 | 2000048 | Green | Amber | Amber | Amber | Amber | The delivery end date has now been revised to May 2022.. DJCS has decommissioned all Windows 2003 & 2008 servers within its scope and is collaborating with teams who have dependencies to complete the remediation activities on the remaining servers.
Q3 21-22 | Department of Justice and Community Safety | DJCS | 2906 | Prison Industries Enhancement Phase 2 Project | Law and Justice | Management of Process | The primary purpose of the PIE project is to deliver value for money prison services by exploring ICT opportunities for Prison Industries (PI) cost recovery, as well as through promoting PI as a preferred supplier to internal business units. | Delivery | Cost Reduction (Financial), Increased Revenue (Financial), Social Improvement (Non Financial) |  | Project Management Excellence | 2019-09-02 | 2020-03-27 | 2020-04-30 | 2020-05-01 | 0 |  | 2020-05-04 | 2020-10-29 | 2020-10-30 | 2022-09-29 | 2140000 | 3582310 | Green | Green | Green | Green | Green | Delivery is complete for two of the three solutions. Delivery end date has been revised to September 2022, to accommodate a 6 month delay requested by one of the 13 sites. This is due to building works underway at that site. The timeline has been approved by the Project Control Group. The project is tracking well against scope, budget and schedule.
Q3 21-22 | Dental Health Services Victoria | DHSV | 2909 | Mobile Diagnostic Imaging | Health | Records Management | The objective of this project is to enable Public Oral Health providers to access diagnostic images acquired from School Dental Program in a timely manner, and at the point of care. | Delivery | Social Improvement (Non Financial) |  | PRINCE2 | 2019-06-28 | 2020-09-30 | 2021-11-30 | 2021-11-30 | 0 | 200000 | 2021-12-01 |  | 2023-02-28 |  | 2972693 | [5 empty] | Amber | The vendor procurement and contract negotiations are now complete. The project has commenced project activities around Infrastructure while waiting for the vendor to mobilise resources and complete project onboarding.
Q3 21-22 | Department of Education and Training | DET | 2919 | eduPass Authorisation | Education | Content Management,Systems Management | The eduPass Authorisation project will deliver a centralised access management system to simply and automatically ensure timely and appropriate rule-based user access to Department IT applications and data. | Closed - Completed | Efficiency/Productivity (Non Financial) | 2022-01-31 | PRINCE2 | 2015-07-01 | 2019-12-16 |  | 2019-12-16 | 435357 |  | 2019-12-17 |  | 2020-12-31 | 2022-01-31 | 4185300 | 3411160 | Green | Green | Green | Green | Green | The project has completed delivery as per the schedule and is on budget and is in the process of closure. The project board approved the closure of the project on 25/3/2022, as a result this will be the last report.
Q3 21-22 | Peninsula Health | PEN Health | 2926 | Enhanced eReferral Project | Health | Systems Management | Replace UNITI within Community Health and Rehabilitation Ageing Pain and Palliative Care Services by expanding the use of MasterCare in PH (subject to procurement rules) to deliver secure messaging capability (across PH GP’s and other external party) | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial), Increased Revenue (Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2019-11-25 | 2020-05-12 |  | 2020-05-12 | 0 |  | 2020-05-12 |  | 2021-08-03 | 2022-06-30 | 1349000 |  | Green | Amber | Green | Amber | Amber | The application is running very well in the areas live however our network desktop virtualisation software is legacy and proving unreliable. To counter this the project team are investigating the possibility of a Software As A Service (SAAS) solution once more is understood regards schedule budget and resources the project artefacts will be updated to reflect any changes.
Q3 21-22 | Department of Transport | DOT | 2929 | DTRS Critical Service Continuity | Transport and Vehicles | Systems Management | The Digital Train Radio System (DTRS) supports safety-critical mobile radio communications for Melbourne metropolitan train services. | Delivery | Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | PTV Investment Lifecycle | 2019-10-28 | 2020-08-31 | 2019-12-16 | 2019-12-16 | 0 |  | 2019-12-16 |  | 2023-01-01 |  | 83000000 |  |  |  | Amber | Amber | Amber | Overall project status is reported amber due to resources availability during Easter for the cut-overs. 90% of the radio sites are operational. Core subsystem – First Data Centre Go Live planned for April 2022. Second data centre Go Live Preparation underway. Dispatcher system project planning underway.
Q3 21-22 | Department of Transport | DOT | 2931 | Human Capital Management (HCM) Project | Transport and Vehicles | Customer Initiated Assistance,Human Capital / Workforce Management ,Human Resources,Tracking and Workflow | To lead the implementation of SAP SuccessFactors (including Payroll) for DoT as the initial tranche of the broader WoVG program managed by OneVPS. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-02-03 | 2020-06-30 | 2021-07-30 | 2021-08-02 | 0 |  | 2021-08-09 |  | 2022-07-04 | 2023-01-31 | 0 | 25858946 |  |  | Amber | Green | Amber | Overall status of the project is amber due to schedule issues. Sprint-2 testing has commenced successfully after build test and data migration preparation activities. Planning and preparation for system integration test has commenced.
Q3 21-22 | South West Alliance of Rural Health | SWARH | 2932 | SWARH Windows 2003/2008 Server Refresh and SQL server uplift | Health | Data Management,Development and Integration ,Systems Management | To move SWARH and Barwon Health applications and services from Windows 2003/2008 to a supported environment. This will address the risk of operating in a legacy environment. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | PMBoK | 2020-03-30 | 2020-05-30 |  | 2020-05-30 | 60000 |  | 2020-06-22 | 2020-09-30 | 2020-12-24 | 2022-05-30 | 2664660 | 2664660 | Amber | Amber | Amber | Amber | Amber | Overall status is reported as Amber due to technical and system related issues associated with migrating legacy complex systems and staff shortages due to COVID contributing to delays. The project team is working closely with vendors and application owners to identify gaps and implement specific application solutions. A change request has been presented at the Steering Committee meeting to approve the revised delivery end date of 30th May 22.
Q3 21-22 | WorkSafe Victoria | WorkSafe | 2935 | Digital Employee Experience & Intranet | Government and Economy | Communication | Implement a corporate intranet platform that will support WorkSafe's digital employee experience strategy and digital workplace. Delivering the project will drive significant productivity improvements and drive employee engagement. | Closed - Completed | Efficiency/Productivity (Non Financial) | 2022-03-18 | PMBoK | 2019-08-01 | 2020-04-30 | 2021-04-22 | 2021-04-22 | 0 | 903000 | 2021-04-22 |  | 2021-10-12 | 2022-03-08 | 1815440 |  |  | Green | Green | Green | Green | Project has gone live and no major issues identified.
Q3 21-22 | WorkSafe Victoria | WorkSafe | 2937 | ACCS eCAM Replacement | Government and Economy | Customer Relationship Management | Replacement of eCam and Lotus Note systems with SalesForce, and associated applications to manage conciliation cases. Benefits realised include significant reduction in manual effort, improved usability as well as reducing legacy system dependencies. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | PMBoK | 2020-02-03 | 2020-06-30 | 2021-02-12 | 2021-02-26 | 0 | 1278689 | 2021-02-26 |  | 2021-07-30 | 2022-03-31 | 4642607 |  | Green | Amber | Red | Red | Red | Overall the project's build activities have taken longer than originally anticipated due to project complexity. Steering Committee decision is to pause the project and conduct a thorough gap analysis of the build so far.
Q3 21-22 | Greater Western Water Corporation | GW Water | 2939 | Billing and Collection | Environment and Water | Assets/Materials Management,Customer Initiated Assistance,Customer Preferences,Customer Relationship Management,Data Management,Development and Integration ,Document Management ,Financial Management,Knowledge Management ,Management of Process ,Records Management ,Reporting ,Routing and Scheduling,Tracking and Workflow | Replacement of the core Billing and Collections system with a modern ‘fit-for-purpose’ solution to allow CWW to better serve our customers and bring operational efficiencies | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-09-23 | 2021-01-31 | 2021-05-25 | 2021-05-25 | 790000 | 4575000 | 2021-05-25 |  | 2023-06-30 | 2024-03-31 | 39965000 | 70726134 |  | Green | Green | Green | Green | Business Case updated including revised cost and schedule. A single deployment is assumed and a 23% cost contingency has been incorporated. Board approval obtained.
Q3 21-22 | Victorian Funds Management Corporation | VFMC | 2943 | Data and Analytics | Business and Industry | Analyses and Statistics | The project will deliver an Enterprise Data Management Platform to underpin VFMCs comprehensive data and IT transformation strategy which will enrich and validate multiple sources of investment data into one centralised location. | Delivery | Cost Reduction (Financial), Risk Reduction (Non Financial) |  | Agile | 2018-08-13 | 2019-10-02 |  | 2019-10-02 | 778436 |  | 2020-02-03 |  | 2021-06-30 | 2022-06-30 | 19181333 |  | Green | Amber | Red | Green | Green | Priority deliverable is decommissioning of RDW which is on track for June. Progressing integration for four teams. Working with the Business Sponsor on prioritisation of report building for investment teams.
Q3 21-22 | Department of Jobs, Precincts and Regions | DJPR | 2956 | Resources Management System Victoria (RMSVIC) Project | Business and Industry | Analyses and Statistics ,Content Management,Customer Initiated Assistance,Customer Relationship Management,Data Management,Document Management ,Management of Process ,Records Management ,Tracking and Workflow | The Project will deliver a Resources Management System Victoria (RMSVIC) in Salesforce to replace Resource Rights Allocation and Management (RRAM). Key benefits are a fit for purpose, tailored, flexible system supporting industry and the Regulator | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Reputation (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-11-01 | 2019-12-31 | 2020-02-26 | 2020-02-27 | 222500 |  | 2020-02-27 |  | 2021-12-31 | 2023-03-31 | 5920000 | 5122547 | Amber | Red | Red | Red | Red | Despite ongoing challenges in the current labour market recruiting suitably qualified personnel with specialist skills, IT build is well advanced with ~55%of the new system developed.
Q3 21-22 | Yarra Valley Water | YV Water | 2957 | Core Switch Replacement | Environment and Water | Systems Management | Replacement of end of life core switching hardware. | Closed - Completed | Risk Reduction (Non Financial) | 2022-03-31 | PRINCE2 | 2020-01-01 | 2020-05-30 | 2020-05-11 | 2020-05-11 | 150000 |  | 2020-05-12 | 2020-05-12 | 2021-02-28 | 2022-03-31 | 2725600 |  | Green | Green | Green | Green | Green | Project completed
Q3 21-22 | Department of Justice and Community Safety | DJCS | 2978 | Road Safety Package | Law and Justice | Assets/Materials Management | The Victorian Government has provided funding to modernise and expand the Road Safety Camera Program and significantly uplift mobile road safety camera operations. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Project Management Excellence | 2019-06-30 | 2020-09-30 | 2021-05-23 | 2021-05-23 | 2787000 | 2024184 | 2021-05-24 |  | 2022-04-21 | 2023-06-30 | 6967000 |  |  | Green | Green | Green | Green | Solution build is underway. Training plan and training scenarios completed. Schedule at risk due to dependency on third party integration design build and test.
Q3 21-22 | Department of Premier and Cabinet | DPC | 2979 | Automated Briefing and Correspondence (ABC) | Government and Economy | Tracking and Workflow | Design and deploy a single, digital document tracking system to manage all departmental briefings and correspondence, including management of drafting and approval workflows, maintenance of the historical record, and search and reporting capability. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-01-01 | 2020-08-07 | 2020-09-25 | 2020-09-25 | 348000 |  | 2020-09-28 |  | 2021-07-09 | 2022-06-30 | 1897740 |  | Green | Amber | Green | Green | Green | ABC Solution support and continuous improvement processes well established. Testing underway for deployment of PPQ / Parliamentary features to be rolled out by the end of June 2022.
Q3 21-22 | WorkSafe Victoria | WorkSafe | 2986 | People Experience Portal | Government and Economy | Human Capital / Workforce Management | Implementation of a Human Resources Information System to support Worksafe in the effective management of its workforce. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PMBoK | 2019-06-03 | 2020-06-30 | 2020-11-03 | 2020-11-03 | 756031 |  | 2020-11-04 |  | 2022-06-30 |  | 7159514 |  | Green | Green | Green | Amber | Amber | Project is continuing to track as Amber for schedule for current key internal milestones which were initially also a result of prioritisation of Chief Health Officers mandates/implementation for COVID, however are now predominantly for further focus on system design and testing. Core module go live dates are continuing to be under revision with stakeholders for agreement. Anticipating extension of project delivery end date by 3-6 months.
Q3 21-22 | WorkSafe Victoria | WorkSafe | 2987 | Enforcement & Advice | Government and Economy | Customer Relationship Management | Configuration and development of Salesforce CRM for Investigations & Prosecutions, Advisory, Licensing and Digital Channels functions. | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Social Improvement (Non Financial) |  | PMBoK | 2019-11-01 | 2020-04-30 |  | 2020-05-01 | 7000000 |  | 2020-05-01 |  | 2021-12-31 | 2022-06-30 | 60000000 | 69406803 | Green | Green | Amber | Green | Green | Project is on track.
Q3 21-22 | Melbourne Water | MELB Water | 2990 | Geospatial Program | Environment and Water | Assets/Materials Management,Content Management,Data Management,Knowledge Management ,Visualisation | Melbourne Water have wide ranging complex and critical business operations dependent on GIS technology. This project will significantly improve, modernise and extend the spatial capabilities available to business users and our operations. | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-05-15 | 2021-05-12 | 2021-05-19 | 2021-08-17 | 0 |  | 2021-08-17 |  | 2023-06-13 |  | 3718109 | 4363927 |  |  | Green | Green | Amber | Amber status due to additional scope has been added to the Stakeholder, Environment and Public Health assessment requirement. This will be delivered before and post go-live to remove it from critical-path to go-live. Additional scope is being assessed for the changes to the application classification. This may result in an overall schedule re-forecast and potentially a CR on the project budget. Sprints 4-5 in business testing phase, next sprint has commenced. Detailed design, Functional and non-functional specification is near finalisation and approval, confirmation of performance testing commitment has been requested from Vendor before the milestone is reached. .
Q3 21-22 | Transport Accident Commission | TAC | 3000 | AV Uplift TAC | Transport and Vehicles | Communication,Visualisation | AV equipment uplift to meet contemporary business needs of staff so they are able to present digital content from their device to other meeting participants and run web conferences with external parties. | Delivery | Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-04-16 | 2020-04-16 |  | 2020-04-16 | 0 |  | 2020-04-16 |  | 2020-12-31 | 2022-09-30 | 1612500 | 2443877 | Green | Green | Red | Red | Amber | Project is tracking Amber until the completion of the construction RFT & hearing augmentation RFQ. Once these costs are known and re-planning completed a change request will be raised to apply any final budget &/or schedule adjustments. Tactical solution will be in place until the building works have been completed as required for the permanent solution. Go to Green plan - Change request to be raised for Additional scope for lighting and acoustic treatment.
Q3 21-22 | South West Alliance of Rural Health | SWARH | 3003 | Barwon Health Community Electronic Medical Record | Health | Content Management,Data Management,Forms Management,Management of Process ,Security Management ,Systems Management,Tracking and Workflow | Implementation of an Electronic Health Record (EHR) solution as part of Barwon Health (BH) Strategy and supportive of the broader DHHS and Government policy goals and focused on improving the quality and safety of the patient care that BH delivers. | Initiated |  |  | PMBoK | 2018-03-01 | 2020-10-01 | 2022-05-16 |  | 0 | 500000 | [11 empty] | Barwon Health Board has approved the product selection and project proposal. The project is moving into mobilisation, resourcing, and contract negotiation.
Q3 21-22 | Department of Environment, Land, Water and Planning | DELWP | 3024 | Migration to Public Cloud | Emergencies and Safety | Systems Management | DELWP is moving its large suite of emergency management applications away from a legacy hybrid-cloud infrastructure into a corporate Microsoft Azure tenancy. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-09-07 | 2020-12-01 | 2021-02-12 | 2021-02-12 | 70000 |  | 2021-03-15 |  | 2022-06-30 |  | 10200000 | 4841632 | Green | Green | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q3 21-22 | Department of Education and Training | DET | 3025 | eProcurement Solution Implementation | Education | Supply Chain Management ,Management of Process | This project will implement the eProcurement Solution for end-to-end source to contract functionality and contract management replacing the current Ariba platform which is approaching end of life. | Postponed | Compliance (Non Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) | 2021-04-16 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-07-06 | 2020-10-18 |  | 2020-10-18 | 0 |  | 2020-10-19 |  | 2021-06-30 |  | 1573670 |  | Amber | Red | Red | Red | Red | This project, which is part of a WoVG eProcurement initiative, has been paused at the request of the Department of Premier and Cabinet whilst processes are aligned across departments that will enable the benefits of common systems to be realised.
Q3 21-22 | Major Transport Infrastructure Authority | MTIA | 3028 | Reporting & Analytics Project | Transport and Vehicles | Business Intelligence | The project aims to implement a reporting and analytics environment for the Office of the Director-General to aggregate and store data from information systems of MTIA – thus enabling efficiency and accuracy of information reporting and analysis | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-05-01 | 2020-11-20 | 2021-05-26 | 2021-05-27 | 188000 | 486249 | 2021-05-27 |  | 2021-10-29 | 2022-02-09 | 2365751 | 2631800 |  | Green | Amber | Amber | Green | Reporting & Analytics phase 2 project was delivered and completed. The project will be officially closed upon governance approval in Q4.
Q3 21-22 | Fire Rescue Victoria | FRV | 3029 | Fire Rescue Portal | Emergencies and Safety | Systems Management | Design and implement an enterprise Fire and Rescue Services Portal. | Delivery | Compliance (Non Financial) |  | FRV Project Management Framework (PMF) | 2020-06-26 | 2020-12-16 |  | 2020-12-16 | 0 |  | 2020-12-17 |  | 2022-04-30 | 2023-06-30 | 2109000 |  | Amber | Green | Amber | Amber | Green | The project is tracking well against scope budget and schedule.
Q3 21-22 | Fire Rescue Victoria | FRV | 3030 | Rostering and Shift Change | Emergencies and Safety | Systems Management | Purchase and implement a contemporary off the shelf Rostering and Shift Change system to replace multiple legacy systems. | Delivery | Efficiency/Productivity (Non Financial) |  | FRV Project Management Framework (PMF) | 2020-06-26 | 2020-12-08 | 2021-09-14 | 2021-09-14 | 0 |  | 2021-09-15 |  | 2022-11-02 |  | 3760000 |  |  |  | Green | Amber | Amber | The project reported an Amber status as it has been rescoped at a high level. Detailed planning will commence in April 2022.
Q3 21-22 | Department of Justice and Community Safety | DJCS | 3033 | Victims of Crime Financial Assistance Scheme | Community Services | Customer Initiated Assistance | The Project will deliver an ICT system centred around Case Management to deliver funds and support to Victims of Crime. The system will underpin the new financial assistance scheme approved by Cabinet. | Initiated |  |  | Project Management Excellence | 2019-01-04 | 2021-06-30 | 2023-06-30 |  | 3297000 | 2971000 | [11 empty] | The report has been 'rebaslined' to Initiation phase in accordance with the Project Management Excellence Framework. This is as a result of the ICT Plan One being endorsed and funds ($2.971m) held in contingency being approved and released. Once the ICT Plan Two has been developed and the remainder of contingency funds have been approved for release, the project will enter the 'delivery' phase.
Q3 21-22 | WorkSafe Victoria | WorkSafe | 3047 | Data & Analytics Hub | Government and Economy | Analyses and Statistics ,Business Intelligence,Data Management | The Data & Analytics Program will deliver cloud technology platforms to uplift WSV's enterprise data management capabilities including a new enterprise datawarehouse data lake, advanced analytics and business analytics. | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Social Improvement (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-11-01 | 2020-04-30 |  | 2020-05-01 | 0 |  | 2020-05-01 |  | 2021-12-31 | 2022-06-30 | 1169000 | 15015621 | Green | Green | Amber | Amber | Red | Significant progress has been made in re-planning activities to return the program to green. Resource challenges persist with difficulty filling vacant positions due to a competitive market, staff turnover with our vendor partner and COVID impacts. Direction is required from the PGG on a path forward to implement a strategic Business Intelligence tool.
Q3 21-22 | Department of Transport | DOT | 3052 | Automatic Incident Detection (AID) Software Project | Transport and Vehicles | Development and Integration ,Systems Management,Visualisation | The objective of this project is to implement an Automated Incident Detection (AID) system. This system will use data from existing freeway systems and alert the operators and provide a view of road traffic incidents from the nearest CCTV camera. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-07-06 | 2021-02-28 | 2021-07-07 | 2021-07-30 | 0 |  | 2021-08-16 |  | 2022-06-30 | 2022-08-31 | 2100000 |  |  |  | Green | Green | Green | Overall project status is green. Infrastructure set up and detail design completed. Development work is ongoing.
Q3 21-22 | CenITex | CenITex | 3062 | Oracle as a Service – Solaris Sparc platform Refresh | Government and Economy | Assets/Materials Management | The purpose is to modernise the existing platform to remove capacity constraints, improve performance & back up recovery on to a supportable platform in the data centres | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2020-03-04 | 2020-04-22 |  | 2020-04-22 | 0 |  | 2020-05-19 |  | 2021-06-30 | 2022-06-30 | 4306662 |  | Amber | Green | Green | Green | Green | 'Cenitex has established an Oracle hosting platform and migrated all DJCS Business Intelligence production application databases onto the new platform. The migrations to the new infrastructure reduces the risk of failure to business critical services.
Q3 21-22 | Department of Premier and Cabinet | DPC | 3066 | Wage Inspectorate Victoria case management system | Employment and Workplace | Management of Process ,Records Management ,Reporting | Design and build a case management system to support end-to-end regulatory operations of the Wage Inspectorate Victoria. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-05-25 | 2020-12-03 | 2021-01-11 | 2021-01-11 | 135000 |  | 2021-01-11 |  | 2022-03-31 | 2022-11-30 | 1434372 | 1684914 | Green | Green | Green | Green | Green | Requirements specification for Investigations and Audits for Phase 4 (Child Employment) have been completed.
Q3 21-22 | Department of Education and Training | DET | 3070 | Student Insight Platform Establishment & Digital Enrolment Product | Education | Development and Integration ,Management of Process ,Organisational Management | The Digital Enrolment component on the Student Insight Platform will ease the school administrative burden, improve data quality and security and deliver efficiencies for managing student information for parents, schools, and staff. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2020-08-03 | 2021-06-30 | 2021-04-21 | 2021-04-21 | 2553958 | 773357 | 2021-04-21 |  | 2022-06-30 | 2022-06-30 | 15500000 | 9000000 |  | Green | Green | Green | Green | Development of the Digital Enrolment product on the centralised Student Insight Platform is complete with development of the Transition component of the product progressing well. Note: The Initiate cost has been revised to reflect the cost of developing the Proof of Concept (PoC) for the Digital Enrolment product only. The total cost has been reduced as the program has revised the development approach and is building components based on demand using the platform that was delivered through the PoC.
Q3 21-22 | Department of Education and Training | DET | 3071 | Child Link Program | Education | Content Management,Data Management,Human Resources,Management of Process | The project will deliver an IT system to provide a thin layer of key information on Victorian children and families to inform professional practice and to provide authorised professionals the ability to be informed regarding children's welfare. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-07-01 | 2020-10-01 |  | 2020-10-01 | 2214000 | 2214000 | 2020-10-01 |  | 2022-06-30 |  | 35200000 | 56386000 | Amber | Green | Amber | Green | Green | The Child Link program status is green due to the system being stable in production since the legislated commencement date of 31 December 2021. The program is undertaking iterative refinements through post-production releases as part of the ongoing operations. Child Link user onboarding is planned to progress in the next period in line with the initial tranche of users identified in the Implementation Plan.
Q3 21-22 | State Revenue Office | SRO | 3072 | Data Centre Relocation and Uplift | Government and Economy | Systems Management | SRO is relocating and updating our production data centre from the current Ballarat office to a third party 'co-location' site, and uplifting the second data centre in the Melbourne office to maintain parity for IT disaster recovery fallback. | Delivery | Compliance (Non Financial) |  | Waterfall | 2020-04-07 | 2020-05-19 |  | 2020-05-19 | 54791 |  | 2020-05-20 |  | 2021-06-30 | 2022-05-31 | 1666209 | 2504209 | Amber | Amber | Amber | Amber | Green | The Production Data Centre successfully migrated in late January from the Mt Helen Ballarat location to the NextDC third party data centre. The old data centre was decommissioned and the site vacated by end February. The focus now moves to the uplift of the DR data centre in the Melbourne office.
Q3 21-22 | Yarra Valley Water | YV Water | 3076 | Land Development in Salesforce | Environment and Water | Customer Relationship Management | Replacement of the end of life land development customer portal (easyACCESS), including optimisation of the existing processes to deliver productivity savings and uplift the overall customer experience. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-08-05 | 2020-11-30 | 2021-06-30 | 2021-07-01 | 662000 | 1700000 | 2021-07-01 |  | 2026-06-30 |  | 2681995 |  |  |  | Green | Green | Green | Delivery of foundational components underway.
Q3 21-22 | Yarra Valley Water | YV Water | 3078 | Yarra Valley Online Water (YVOW) Replacement | Environment and Water | Customer Relationship Management,Customer Relationship Management | Replacement of the end of life customer self service portal (YVOW), including a redesign of the customer experience. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-08-05 | 2020-11-30 | 2021-06-30 | 2021-07-01 | 330000 | 1400000 | 2021-07-01 |  | 2022-12-31 |  | 1886564 |  |  |  | Green | Green | Green | Delivery of foundational components underway.
Q3 21-22 | Yarra Valley Water | YV Water | 3079 | Distribution Management System (DMS) | Environment and Water | Customer Relationship Management | Distribution Management System which provides staff with a single view of our asset networks including performance data, customer service levels, and contractor interactions. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-07-01 | 2020-09-28 |  | 2020-09-28 | 0 |  | 2020-09-28 | 2020-10-12 | 2023-06-30 | 2023-06-30 | 6002000 | 4851600 | Green | Green | Green | Green | Green | DMS Production Release 1 deployed. Planning for Design of Release 2 in progress.
Q3 21-22 | Wannon Region Water Corporation | WAN Water | 3091 | Billing and Customer Relationship Management Systems | Environment and Water | Customer Relationship Management | The replacement of the organisation's Billing and Customer Relationship Management Systems | Initiated |  |  | PRINCE2 | 2020-01-01 | 2021-03-31 | 2022-07-01 |  | 100000 | 600000 | [11 empty] | RFT issued to the three shortlisted suppliers on 21 Dec 2021. Supplier discovery workshops will run until Apr 2022. Additional task of mapping shortlisted products to CX road-map causing 1 month extension of procurement timeline. Preferred supplier recommendation to Wannon Water Board in May 2022. and business case / final recommendation to Board in June 2022. Subject to Wannon Water Board approval to proceed, implementation to commence CQ3 2022 through to late 2023.
Q3 21-22 | Department of Health | DH | 3094 | Digital Registration for Food Businesses - FoodTrader | Business and Industry | Data Management | Deliver a single online registration portal for Victorian food businesses and an application assessment, compliance management and reporting database for use by councils in managing registrations under the Food Act 1984. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Agile | 2019-06-28 | 2020-04-14 |  | 2020-07-06 | 184000 | 500000 | 2020-08-17 |  | 2022-06-30 |  | 2044600 |  |  |  |  | Green | Green | Project is progressing to cost and schedule.
Q3 21-22 | Department of Health | DH | 3095 | Windows Server Re-Platform and Re-Hosting | Health | Systems Management | The project will upgrade, re-host or decommission outdated servers and database instances to ensure continuity of infrastructure support of services. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-07-01 | 2020-07-12 |  | 2020-07-17 | 494548 |  | 2020-09-10 |  | 2021-06-30 | 2022-06-30 | 1048885 | 1355200 | Amber | Amber | Green | Amber | Green | Project progressing to cost and revised schedule.
Q3 21-22 | Department of Environment, Land, Water and Planning | DELWP | 3100 | Victorian Water Register Transform Project | Environment and Water | Management of Process | The project will deliver a new Victorian Water Register(VWR) to improve service delivery, information sharing and to ensure the equitable sharing of water and continuous improvement in the integrity security and reliability of Victoria's water market | Initiated |  |  | PRINCE2 | 2020-10-25 | 2021-06-30 | 2022-04-29 |  | 1467715 | 2938332 | [11 empty] | The initiation stage has progressed with procurement of an implementation partner nearing completion.
Q3 21-22 | HealthShare Victoria | HealthShare | 3102 | Setup HealthShare in FMIS | Health | Supply Chain Management | Establish HealthShare Victoria as a new operating unit with Oracle eBusiness and configuring Warehouse Management Solution for the new HealthShare Victoria supply chain. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-06-01 | 2020-06-30 |  | 2020-09-21 | 63313 |  | 2020-09-21 | 2020-09-21 | 2021-06-30 | 2022-06-30 | 1200000 | 5634687 | Amber | Red | Amber | Amber | Amber | System went live as planned on 28 March 2022. Currently working through defects during hypercare period that emerge as system functions are fully utilised prior to commencing project closure activities.
Q3 21-22 | CenITex | CenITex | 3107 | Data Centre Core Network Refresh | Government and Economy | Assets/Materials Management | To remediate the biggest risk areas of the Cenitex core datacenter infrastructure through the procurement and installation of high performance and contemporary network infrastructure. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-09-28 | 2020-11-19 |  | 2020-11-19 | 0 |  | 2021-01-11 |  | 2021-09-10 | 2022-06-30 | 2119306 | 2601356 | Green | Green | Green | Green | Green | 4 of 5 major upgrades have been successfully completed at the Ballarat and Burwood data centres.
Q3 21-22 | CenITex | CenITex | 3108 | DJCS – Custodial Site Switch refresh | Government and Economy | Assets/Materials Management | This project is to procure the equipment required to support five customer funded projects that will refresh DJCS custodial sites. | Delivery | Cost Reduction (Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2020-09-01 | 2020-12-03 |  | 2020-12-03 | 0 |  | 2020-12-07 |  | 2021-06-30 | 2022-06-30 | 1200000 | 1324160 | Green | Green | Amber | Green | Green | Hardware has been received for 5 of 5 sites.
Q3 21-22 | Department of Premier and Cabinet | DPC | 3113 | WoVG Common Corporate Platforms - Human Capital Management Program | Government and Economy | Human Capital / Workforce Management | Implementation of a whole of government single instance cloud based HCM system (SAP SuccessFactors) to uplift and modernise the government's human resources systems and deliver consistent human resources services across the Victorian Public Service | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-08-28 | 2020-09-29 |  | 2020-09-29 | 808026 |  | 2020-09-30 |  | 2022-01-31 | 2022-11-01 | 7877290 | 14779707 | Amber | Green | Green | Amber | Amber | Re-alignment of program schedule due to finalising the joint schedule across the program and the first implementing department.
Q3 21-22 | Chisholm Institute of TAFE | Chisholm TAFE | 3114 | Unified Communications & Audio-Visual Refresh (UC/AV) | Education | Collaboration | Deploy a technology solution that improves team productivity through enhanced communications & collaboration. The key components of the solution include deployment of Microsoft Teams Telephony and a refresh of AV equipment across campuses. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Waterfall/Agile | 2020-07-01 | 2020-09-01 |  | 2020-09-01 | 175000 |  | 2020-09-02 |  | 2021-06-30 | 2022-10-31 | 2023554 |  | Green | Green | Amber | Amber | Amber | Project deliverables progressed. Date revision approved by Project Executive.
Q3 21-22 | Department of Health | DH | 3118 | TIBCO Upgrade Implementation | Health | Development and Integration | The project will upgrade the existing TIBCO platform to a more recent supported version, thereby mitigating the risks associated with outdated software and ensuring continuity of Vendor support. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2019-06-01 | 2020-04-17 |  | 2020-11-13 | 271632 | 0 | 2021-06-21 |  | 2022-08-31 | 2022-09-30 | 3900000 | 3400000 |  | Green | Green | Green | Amber | Project is progressing but has had infrastructure setup delays which are impacting schedule.
Q3 21-22 | Western Health | WH | 3125 | Identity Access Management (IAM) | Health | Security Management | An IAM system is the means to provide a secure and trusted identity of employees across Western Health. This is currently housed and managed by Melbourne Health and this project will migrate the IAM from Melbourne Health to Western Health | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-10-30 | 2021-01-29 |  | 2021-04-19 | 0 |  | 2021-04-19 |  | 2022-02-28 | 2023-01-13 | 1896000 | 1773789 |  | Green | Amber | Amber | Amber | Status remains at Amber due to delays to complete preceding project caused by resource availability and reduced appetite for risk in impacting operations during critical Covid period.
Q3 21-22 | Melbourne Water | MELB Water | 3126 | Security access management for Contractors | Environment and Water | Data Management,Human Resources,Security Management | The security access management for contractors project will implement an identity and access management solution for the enterprise. The outcome will deliver further improved digital security and role based permissions. | Postponed |  | 2021-07-14 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-09-30 | 2021-01-28 | 2021-04-20 |  | 0 | [5 empty] | 0 | [6 empty] | Business Case not approved in it's current form. Change request raised and approved on 14th July to move the project from Year 1 to Year 3 of Water Plan 5. Recommencement of project and Business Case re-write to be scheduled for early 2023 calendar year.
Q3 21-22 | Department of Transport | DOT | 3127 | Payments Remediation Project | Transport and Vehicles | Financial Management,Systems Management | Objective of this project is to improve front-end and back-end payments usability and customer experience and resolve technical issues and reduce suspense payments and associated administrative support overheads. | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-09-01 | 2020-10-05 |  | 2020-10-05 | 0 |  | 2020-10-05 |  | 2021-06-30 | 2022-06-30 | 1500000 | 1900000 | Green | Green | Green | Amber | Amber | Overall status is amber due to budget and dependency issues. Scope is being reprioritised and resources reallocated to reduce delivery costs. Integration testing is ongoing.
Q3 21-22 | Department of Transport | DOT | 3128 | Smarter Roads Program - Situational Awareness Platform (formerly-Creating More Road Space) | Transport and Vehicles | Analyses and Statistics ,Business Intelligence,Communication,Knowledge Discovery | Objective of this project is to develop a enterprise wide Situational Awareness (SA) Platform. The platform will provide a view of the metro transport network and provide situational awareness for the operators in the Traffic Management Centre (TMC). | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-10-05 | 2021-06-30 | 2021-06-14 | 2021-06-14 | 0 |  | 2021-06-21 |  | 2022-06-30 | 2022-12-31 | 0 | 35800128 |  | Green | Green | Green | Green | Overall project status is green. Deployment planning Testing communications and change management activities are ongoing.
Q3 21-22 | Department of Transport | DOT | 3129 | Zero Low Emission Vehicles (ZLEV) Project | Transport and Vehicles | Business Intelligence,Development and Integration ,Management of Process | Objective of this initiative is to cover technology changes and preparing options for consideration by DTF regarding funding to replace the fuel excise revenue projected to be foregone as the vehicle market increasing takes up ZLEV. | Delivery | Eco Improvement (Non Financial), Increased Revenue (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-11-02 | 2021-06-30 | 2021-01-29 | 2021-01-29 | 0 |  | 2021-01-29 |  | 2021-09-30 | 2022-05-20 | 1939460 | 2604593 | Amber | Amber | Green | Amber | Amber | Overall project status is Amber due to current scope/budget assessment and resource dependencies. Phase 1 completed successfully. Final stages of delivery scope for Phase 2 being examined with business stakeholders to determine achievability of mid may 2022 completion.
Q3 21-22 | Goulburn Valley Region Water Corporation | GVR Water | 3130 | Billing and Customer Relationship Management System | Environment and Water | Customer Relationship Management | The project will replace Goulburn Valley Water's existing legacy billing and CRM systems with a modern, efficient and customer focused system | Initiated |  |  | Internal project management methodology | 2018-10-01 | 2021-06-30 | 2022-06-30 |  | 75000 | 245000 | [11 empty] | GVW will seek Board approval to progress to market with an open RFT.
Q3 21-22 | Department of Transport | DOT | 3132 | Creating More Road Space- Integrated View of Disruptions | Transport and Vehicles | Analyses and Statistics ,Business Intelligence,Customer Initiated Assistance,Customer Preferences,Visualisation | Objective of this project is to deliver value-add information to end users that will assist in understanding how congestion or disruptions are affecting a car journey and assist in shifting behaviors (i.e. mode of travel) to reduce congestion. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-10-19 | 2021-03-31 | 2022-04-29 |  | 0 | [12 empty] | Project requirements and options analysis activities are ongoing.
Q3 21-22 | Monash Health | Monash H | 3133 | Carestream/Philips Software Upgrade and Hardware Refresh | Health | Systems Management | Upgrade of Radiology Information System and Picture Archiving and Communication System to address risk of legacy operating system and improve system efficiency. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-09-01 | 2020-09-29 |  | 2020-09-29 | 1 | 0 | 2020-10-01 |  | 2021-12-03 | 2022-05-31 | 2570900 |  | Green | Green | Green | Green | Green | The project is tracking GREEN. User Acceptance Testing of the new Radiology Information System (RIS) environment (version 11.5) is progressing to schedule. The Picture Archiving and Communication System (PACS) data migration from the Storage Area Network (SAN) to the new Storage Area Network (SAN) is complete.
Q3 21-22 | Monash Health | Monash H | 3140 | The Victorian Heart Hospital (VHH) Electronic Medical Record (EMR) System | Health | Records Management | Implementation of EMR system for the Victorian Heart Hospital to streamline management of clinical documentation, results and patient medication to enable appropriate patient treatments | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-09-14 | 2020-11-04 |  | 2020-11-04 | 0 | 4867018 | 2021-01-04 |  | 2023-02-17 |  | 26005275 | 21138257 | Green | Green | Amber | Amber | Green | The overall project remains on track for planned Go-Live Feb 2023.
Q3 21-22 | South East Water | SE Water | 3142 | Classic to Lightning Phase 2 | Environment and Water | Customer Relationship Management | Uplift the current Salesforce platform to the Lightning version for the remaining user groups | Closed - Completed | Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) | 2022-03-30 | Agile | 2021-01-04 | 2021-01-15 |  | 2021-01-18 | 10000 |  | 2021-01-18 |  | 2021-05-28 | 2022-04-14 | 1582303 |  | Green | Green | Green | Green | Green | Delivery for the new interface to the content management system is completed
Q3 21-22 | Department of Premier and Cabinet | DPC | 3143 | Single digital solution for coronavirus (COVID-19) reporting (Insights Victoria) | Government and Economy | Analyses and Statistics ,Reporting ,Visualisation | A single digital reporting platform containing whole of government coronavirus (COVID-19) data to increase the Government’s responsiveness during the coronavirus (COVID-19) pandemic. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2020-07-16 | 2020-07-24 |  | 2020-07-24 | 0 |  | 2020-07-27 |  | 2021-01-31 | 2022-06-30 | 4643000 | 15352813 | Green | Green | Green | Green | Green | Successful period of ongoing delivery of InisghtsVictoria.
Q3 21-22 | Department of Transport | DOT | 3147 | Smarter Roads Program - Data Fusion Model | Transport and Vehicles | Analyses and Statistics ,Business Intelligence,Customer Initiated Assistance,Customer Preferences | Objective of this project is to provide: 1.Multi-modal journey planning that encompasses tools to help them re-plan and understand alternative journey options in real time. 2. Real-time disruption information to customers to plan their journey. | Delivery | Efficiency/Productivity (Non Financial), Social Improvement (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-11-02 | 2021-06-30 |  | 2021-06-30 | 0 |  | 2021-08-02 |  | 2022-06-30 | 2022-12-31 | 0 | 12103458 |  |  | Green | Green | Green | Overall project status is green. Delivery continuing, pre-release testing in progress.
Q3 21-22 | Goulburn Ovens Institute of TAFE | GO TAFE | 3148 | Network Infrastructure upgrade | Education | Systems Management | Network infrastructure upgrade includes replacement of all IT network switches across all campuses, to enable a future state of network infrastructure with improved productivity and security. | Closed - Completed | Compliance (Non Financial), Cost Avoidance (Financial) | 2022-03-10 | PMBoK | 2020-08-17 | 2020-10-29 |  | 2020-12-11 | 55000 |  | 2020-12-11 |  | 2021-10-29 | 2022-03-04 | 1350000 |  | Green | Green | Green | Green | Green | Project has successfully delivered within the committed budget and closeout activities are underway.
Q3 21-22 | Kardinia Park Stadium Trust | KPST | 3151 | Connected Stadium - Digital Smart Stadium | Culture, Sport and Recreation | Communication | The project considers both an outward-facing element that addresses the customer and client experiences, and an inward-facing element that will bring the individual stands together and operate via a converged network. | Delivery | Customer Satisfaction (Non Financial) |  | Gantt charts | 2020-10-01 | 2020-12-01 |  | 2020-12-01 | 98000 |  | 2020-12-16 |  | 2022-06-30 |  | 4418000 |  | Green | Green | Green | Green | Green | Project tracking well
Q3 21-22 | Department of Health | DH | 3154 | Digital Visitation Register (DVR) Project | Health | Data Management | Provides free QR Code Service for businesses, workplaces & commercial passenger vehicles to record & share attendance records for contact tracing. Allows contact tracers to notify close contacts of positive cases to test & isolate. | Delivery | Increased Quality (Non Financial), Reputation (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2020-09-09 | 2020-10-06 |  | 2020-10-06 | 0 |  | 2020-10-07 |  | 2023-06-30 |  | 8577000 | 9459238 | Amber | Green | Green | Green | Green | Victorian government QR Code Service is operational and being used by the Victorian Public. The project is progressing to schedule and revised cost in response to the changing needs of managing the COVID-19 Pandemic.
Q3 21-22 | Alfred Health | ALFRED | 3156 | ARIA Database Merge and Managed Service Implementation | Health | Records Management | Database merge and consolidation of Alfred Health Radiation Oncology Application “ARIA” to a single instance, cloud-based, vendor-managed and hosted service | Delivery | Cost Avoidance (Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2021-03-01 | 2021-06-30 |  | 2021-06-30 | 0 | 235544 | 2021-07-01 |  | 2022-12-20 |  | 1708056 |  |  |  | Green | Green | Green | Project is ON TRACK.
Q3 21-22 | Melbourne Health | Melb H | 3159 | Unified Communications – Telephony Upgrade Project | Health | Collaboration ,Communication,Systems Management | This project will upgrade the Melbourne Health telephony system to replace the old existing ISDN / PSTN / analogue PABX and phone infrastructure with digital SIP trunks and VoIP phones that provide unified communication and enhanced collaboration. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2021-02-01 | 2021-06-30 |  | 2021-06-30 | 0 | 50000 | 2021-07-01 |  | 2022-06-30 | 2022-12-15 | 4326000 |  |  |  | Green | Green | Green | Delivery schedule revised due to impact of COVID on resourcing equipment supply and protracted contracting / procurement impacts. Project remains on track to deliver all required outcomes within approved budget.
Q3 21-22 | Melbourne Health | Melb H | 3160 | Office 365 Implementation Project | Health | Collaboration ,Content Management,Systems Management | Extensive technical and change management project to implement the required foundation, application and governance layers for Melbourne Health to deploy and adopt the full collaboration potential of the Microsoft Office 365 suite. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2021-01-04 | 2021-06-30 |  | 2021-06-30 | 0 | 50000 | 2021-07-01 |  | 2022-06-30 | 2022-10-25 | 3532700 |  |  |  | Green | Green | Green | Project approach modified to reduce technical complexity risk and organisational change impact. Project schedule has been extended, remaining on track to deliver all of the O365 benefits and expect outcomes within budget.
Q3 21-22 | Department of Premier and Cabinet | DPC | 3165 | Emergency Management Victoria-VCDI Partnership | Emergencies and Safety | Data Management,Reporting ,Visualisation ,Analyses and Statistics ,Business Intelligence | The primary objective of this partnership is to rapidly and practically enhance EMV (including the State Control Centre) and the emergency management sector’s data and analytics capability in order to help it respond to major and complex emergencies | Delivery | Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2021-01-11 | 2021-01-22 |  | 2021-01-22 | 0 |  | 2021-01-25 |  | 2022-06-30 |  | 2300000 |  | Green | Green | Green | Green | Green | Successful period of working together and product delivery to give EMV enhanced insights into emergency risk locations and where it can target its efforts.
Q3 21-22 | Emergency Services Telecommunications Authority | ESTA | 3167 | Capability & Performance Project | Emergencies and Safety | Human Capital / Workforce Management | The Capability & Performance project is implementing SAP SuccessFactors (Core HR recruitment onboarding performance and goals modules) to provide ESTA with better workforce insights and improve talent and performance oversight | Delivery | Cost Avoidance (Financial) |  | Project Management Excellence | 2020-07-28 | 2020-12-04 |  | 2020-12-04 | 246940 |  | 2020-12-05 |  | 2021-08-30 | 2022-06-30 | 1537583 | 3075778 | Amber | Amber | Red | Red | Red | The project reported a Red status due to the impacts of COVID as front line service delivery was prioritised with resources diverted to where they were needed most - hiring and training of new front line call takers and dispatchers to help manage unprecedented demand.
Q3 21-22 | Department of Justice and Community Safety | DJCS | 3168 | Post Sentence Authority Case Management System | Law and Justice | Tracking and Workflow | This project will deliver a fit-for-purpose case management system for the Post Sentencing Authority. | Initiated |  |  | Agile | 2021-03-30 | 2021-07-15 | 2022-06-30 |  | 150000 | 200000 | [11 empty] | The project has had some changes including moving oversight from the PSA to the Office of the Deputy Secretary. Presently the project is on track
Q3 21-22 | Department of Justice and Community Safety | DJCS | 3169 | Industries Engagement and Enforcement Project | Law and Justice | Tracking and Workflow | This project will deliver a new case management system for managing cases events and incidents for COVID-19 high risk industries. | Delivery | Compliance (Non Financial) |  | Project Management Excellence | 2021-02-01 | 2021-03-01 |  | 2021-03-01 | 550000 |  | 2021-03-02 |  | 2021-11-30 | 2022-06-30 | 7000000 | 12283000 | Green | Green | Amber | Amber | Green | The Victorian Industry Performance Engagement and Emergency Response (VIPEER) project contains two deliverables a Case Management System (CMS) (4 Phase) and Enterprise Data Lake (EDL). Phase 4 of the CMS delivery is complete - including full automation of enforcement technology in Public Sector Foundations and additional mobile application(s). Additional business requirements effecting scope has delayed the delivery of the security uplift on the tenant DateLake and final transition of IEEO to the DJCS EDL but this is not expected to impact the overall delivery end date of 30 June 2022.
Q3 21-22 | Department of Justice and Community Safety | DJCS | 3170 | Technology and resources to support Victoria’s fines system | Law and Justice | Systems Management | Delivery of next generation of fines platform by incrementally implementing functions into the business landscape to complement existing technology, ensuring better revenue collection, assistance for vulnerable Victorians and debtor-centric services. | Delivery | Customer Satisfaction (Non Financial), Increased Revenue (Financial) |  | Hybrid - Waterfall and Agile | 2021-03-10 | 2021-08-30 | 2021-12-16 | 2021-12-16 | 0 | 10367000 | 2022-01-09 |  | 2025-06-30 |  | 131615000 | [5 empty] | Green | The NextGen Program is tracking against budget. Elaboration of the full requirements for Release 1 has highlighted that more of the foundational components have been identified as necessary for inclusion to support the Release and also eliminate future rework. The target date for the Release is currently being reviewed.
Q3 21-22 | Department of Justice and Community Safety | DJCS | 3171 | Better Technology Tools Enabling Responsibility (BTTER) | Law and Justice | Development and Integration | Deliver applications to automate processes, reduce costs and risks associated with existing manual systems to deliver safety and cost benefits. The project will provide access to rehabilitation and reintegration services through in-cell technology. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Project Management Excellence | 2020-07-21 | 2021-02-19 |  | 2021-02-19 | 324114 |  | 2021-02-22 |  | 2023-06-30 |  | 18868800 | 12812547 | Green | Amber | Amber | Amber | Green | Overall the project is on track following endorsement of change request that re-baselined the project plan. - Delivery of minimum viable product for operations is on track. - The automation stream is on track for delivery of 5 modules by June 2023 with Module 1 delivery commencing in January 2022 . Resourcing remains an issue and will have some impact on delivery following loss of key resources that provide continuity to the project.
Q3 21-22 | Department of Justice and Community Safety | DJCS | 3172 | JKE Upgrade & Linux Migration | Law and Justice | Development and Integration | This project is to transition the Justice Knowledge Exchange (JKE) Enterprise Service Bus from Solaris to Linux platforms and upgrades it to webMethods version 10. | Delivery | Compliance (Non Financial) |  | Project Management Excellence | 2020-07-01 | 2020-08-31 |  | 2020-08-31 | 26466 |  | 2020-09-01 |  | 2022-02-28 | 2022-10-19 | 1664286 | 1796869 | Amber | Amber | Green | Red | Amber | Third-party stakeholders resource constraints and outstanding architecture decisions place pressure on the project schedule. Issues are escalated as required. 50 percent of the delivery phase items completed.
Q3 21-22 | Department of Health | DH | 3173 | Identity and Access Management Implementation | Employment and Workplace | Systems Management | Implementation of a cloud based Identity Access Management system to provide a centralised governance capability to manage external business partner access to department systems and information. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-06-01 | 2020-11-13 |  | 2020-11-13 | 0 |  | 2021-01-21 |  | 2022-06-30 |  | 3126591 | 2961587 |  | Green | Green | Green | Amber | Project is progressing however there are some key product constraints which have been identified and now with vendor for review/remediation.
Q3 21-22 | Central Highlands Region Water Corporation | CHR Water | 3174 | SCADA Field Hardware Replacement Program -SCADA Radio Network Asset Replacement Program | Environment and Water | Communication,Business Intelligence,Data Management,Security Management | Replacement of end of asset life hardware used to Monitor and Control Critical Infrastructure Assets | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Internal Framework | 2018-07-01 | 2019-05-17 |  | 2019-05-17 | 0 |  | 2019-07-01 |  | 2023-06-30 |  | 2600000 |  | Green | Green | Green | Green | Green | On Track
Q3 21-22 | South East Water | SE Water | 3175 | Asset Register Phase 3 | Environment and Water | Assets/Materials Management,Data Management | The third and final stage of the Asset Register will build capability to allow network, facility and building assets to be part of the asset register | Closed - Completed | Increased Quality (Non Financial) | 2022-03-30 | Waterfall | 2021-01-11 | 2021-01-21 |  | 2021-01-21 | 75000 |  | 2021-01-25 |  | 2021-12-31 | 2022-02-05 | 2250000 |  | Green | Green | Green | Green | Green | Go live has been completed and the system has been handed over to support teams.
Q3 21-22 | Melbourne Water | MELB Water | 3179 | Incident and Risk System upgrade and migration to cloud | Environment and Water | Reporting | This project will enable the continuing growth in use of Melbourne Waters Incident and Risk system by the business for reporting events completing assessments/checklists and raising completed actions via a mobile app. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-12-01 | 2021-04-30 |  | 2021-05-24 |  |  | 2021-06-24 |  | 2022-05-04 |  | 1067418 | 1630862 |  | Green | Green | Green | Amber | The Amber rating is due to Melbourne Water project metrics with the project timeline and spend expected to finish under the approved upper limit. User Testing was kicked-off on 17 January and is well underway. Integration builds are progressing on schedule. Testing has revealed a deficiency with mobile app usability which requires a user to scroll through multiple assessment checklists rather than being able to isolate the ones that specifically relate to the individual. Project team and vendor are working on a possible change to address this deficiency.
Q3 21-22 | Melbourne Water | MELB Water | 3180 | Digital Education and Engagement Services | Environment and Water | Communication | Melbourne Water has a Water Act obligation through the Statement of Obligations to educate schools about Water Literacy and our range of services. This 3 year program will focus on encouraging water literacy across the school community. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-02-25 | 2021-07-01 | 2021-12-02 | 2021-12-20 | 0 |  | 2021-12-20 |  | 2024-05-30 |  | 1804843 |  |  |  |  | Green | Green | Go-Live for upgrades to the WTP Virtual Tour went ahead on 2 March. Work has progressed on the Frog Census App Upgrades. Contract has been signed for the Digital Learning Gateway and kick-off has been held between MW and Vendor. Discovery phase is now underway.
Q3 21-22 | Department of Jobs, Precincts and Regions | DJPR | 3181 | Jobs Victoria Digital Services build | Employment and Workplace | Customer Initiated Assistance,Customer Relationship Management,Tracking and Workflow | This project will deliver the digital services to support connecting jobseekers and employers smarter, faster and effectively through a tailored and integrated digital platform. | Delivery | Efficiency/Productivity (Non Financial), Social Improvement (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-11-16 | 2021-05-16 |  | 2021-05-17 | 1000000 |  | 2021-05-17 |  | 2022-06-30 |  | 9240675 | 8231549 |  | Green | Amber | Amber | Amber | Program build and launch is on-track. A release and training plan is in place to deliver new capabilities to Jobs Victoria team and partners progressively over the coming months. An iterative deployment approach continues to enable delivery of business benefits incrementally as each business process is transitioned to the new system.
Q3 21-22 | Department of Health | DH | 3182 | Syndromic Surveillance (SynSurv) | Health | Business Intelligence | Primary purpose of the SynSurv platform is to provide advanced warning of new and emerging health threats to epidemiologists, emergency management staff, and public health decision makers in the department to enable a timely response. | Delivery | Increased Quality (Non Financial), Risk Reduction (Non Financial), Social Improvement (Non Financial) |  | PRINCE2 | 2020-07-01 | 2020-09-30 |  | 2020-09-30 | 0 |  | 2020-10-01 |  | 2022-06-30 |  | 3000000 |  | Green | Green | Green | Green | Green | Project is progressing to schedule and cost.
Q3 21-22 | Department of Health | DH | 3188 | Remote Working Capability: Process Digitisation - Software Development | Employment and Workplace | Systems Management | The project will digitise a range of processes including streamlining the digital mailroom and the process for sharing sensitive data between external partners and the department, to better support remote and hybrid working. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Agile | 2020-07-01 | 2020-08-13 |  | 2020-08-14 | 0 |  | 2020-08-14 |  | 2022-06-30 |  | 2886480 | 2461712 | Green | Green | Green | Green | Green | Project is progressing to schedule and revised cost.
Q3 21-22 | Department of Premier and Cabinet | DPC | 3191 | Email Fraud Defence (DMARC) | Government and Economy | Security Management | Implementing DMARC (Domain-based Message Authentication, Reporting and Conformance) will make it significantly harder to send fake emails claiming to be from the Victorian government & will help prevent fraud to the Victorian government & citizens. | Delivery | Cost Reduction (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-10-26 | 2021-05-31 |  | 2021-06-04 | 170672 |  | 2021-06-04 |  | 2023-12-29 |  | 5829328 |  |  | Green | Green | Green | Green | Project tracking well to the approved schedule and budget.
Q3 21-22 | Yarra Valley Water | YV Water | 3192 | Firewall Upgrade | Environment and Water | Security Management | End of life Firewalls to be upgraded as they are our first line of defence against Cyber Security attacks | Delivery | Compliance (Non Financial) |  | Waterfall | 2021-03-15 | 2021-12-31 | 2021-03-31 | 2021-04-01 | 130000 |  | 2021-04-01 |  | 2021-12-31 | 2022-06-30 | 1008000 | 1105020 |  | Green | Green | Green | Green | Delivery end date extended. New remote access being tested. Draft comms being reviewed. Next reporting period expecting to complete remote access testing, roll out to YVW, complete handover documentation and close the project.
Q3 21-22 | Melbourne Convention and Exhibition Centre | MCEC | 3194 | MCEC Core Systems Uplift | Business and Industry | Financial Management,Tracking and Workflow | The CSU project will provide uplifted Finance and Event & Venue Management systems. It will utilise improved technology in the form of cloud infrastructure and software to fit our future state roadmap. | Delivery | Efficiency/Productivity (Non Financial) |  | Agile | 2020-01-13 | 2020-12-18 |  | 2020-12-18 | 150000 | 221600 | 2021-01-15 |  | 2022-04-30 | 2022-09-30 | 1334184 | 2613926 | Green | Amber | Amber | Green | Amber | Upgrade went live as planned however undertaking further actions to de-risk technical integration approach and drive future business efficiencies.
Q3 21-22 | Department of Justice and Community Safety | DJCS | 3199 | Registry System Replacement - RTBA | Community Services | Customer Relationship Management | This project will deliver an enhanced, updated solution to the Residential Tenancies Bond Authority legacy systems which are reaching end of life. The solution will ensure alignment to the business vision. | Initiated |  |  | Hybrid - Waterfall and Agile | 2021-04-12 | 2021-12-31 | 2022-04-22 |  | 900000 | [12 empty] | Project commenced on 12 April 2021 (note this project picks up the now terminated Registry System Replacement (2833) project). Procurement of implementation vendor is near completion with vendor expected to start end of April 2022.
Q3 21-22 | Department of Premier and Cabinet | DPC | 3200 | Local Jobs First Policy Intelligence Engine | Business and Industry | Analyses and Statistics ,Business Intelligence,Data Management | DJPR have partnered with DPC to develop a policy intelligence engine to improve the effectiveness of the Local Jobs First policy. The technology solution will support an uplift in capability to improve the delivery of important policy. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Agile | 2020-12-01 | 2021-02-11 |  | 2021-02-11 | 0 |  | 2021-05-01 |  | 2023-06-30 |  | 2400000 |  |  | Green | Green | Green | Green | Project initiation and planning activities has resulted in a clear roadmap that the delivery team is working towards in alignment with the business owners.
Q3 21-22 | Department of Transport | DOT | 3201 | Dynamics 365 - Permits Customer Portal | Transport and Vehicles | Customer Initiated Assistance,Development and Integration ,Management of Process | Objective of this project is to develop minimum viable product for Permits Customer Portal. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-06-01 | 2021-06-30 |  | 2021-06-30 | 0 |  | 2021-07-01 |  | 2022-06-30 | 2022-10-30 | 3200000 | 3430000 |  |  | Amber | Amber | Green | Overall project status is green. Project steering committee approved the revised schedule and cost. Remediation of authentication solution is ongoing.
Q3 21-22 | Department of Transport | DOT | 3202 | Learners 2 Probationary Mentorship System Procurement (L2P) | Transport and Vehicles | Customer Initiated Assistance,Development and Integration ,Management of Process | Objective of this project is to build a new mentor-ship system to assist learner drivers attain learner hours to be eligible for securing probationary licence. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-04-05 | 2021-07-30 |  | 2021-07-30 | 0 |  | 2021-08-02 |  | 2022-02-19 | 2022-06-30 | 1543840 | 1737325 |  |  | Amber | Green | Green | Overall project status is green. Release 2 development is progressing as per plan.
Q3 21-22 | Department of Education and Training | DET | 3203 | Infrastructure Portfolio Management (IPM) | Education | Investment Management,Management of Process | This project will procure and implement a new SaaS portfolio management system to facilitate effective and efficient infrastructure planning and delivery and improve organisational capability through coordination and delivery of business functions. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-04-22 | 2021-10-31 | 2021-11-30 | 2021-12-01 | 111310 |  | 2021-12-01 |  | 2022-12-31 |  | 6738690 |  |  |  |  | Green | Green | The project is tracking well against scope, budget and schedule. Since the last reporting period the project board has approved the phased implementation approach and release timelines. Project has completed design and configuration activities for scope of the first pilot release and is currently showcasing the solution to seek feedback before progressing to Test stage.
Q3 21-22 | Department of Education and Training | DET | 3205 | ARC Release 1.3 | Education | Content Management,Knowledge Management | ARC will create a comprehensive solution that centralises and integrates the range of high-quality digital services and resources offered by the Department of Education and Training to support learning and teaching in Victorian schools. | Closed - Completed | Customer Satisfaction (Non Financial), Increased Quality (Non Financial) | 2022-02-07 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-01-18 | 2021-04-30 |  | 2021-04-30 | 28782 |  | 2021-05-03 |  | 2022-02-07 |  | 1352229 | 1321061 |  | Green | Green | Green | Green | The project delivered all approved features in January 2022. Project closure activities now underway.
Q3 21-22 | Department of Education and Training | DET | 3207 | VISIT 2-0 | Education | Knowledge Management ,Management of Process | This project will provide additional functionality to the first release of the Victorian International Student Information Tool (VISIT) to enable DET and Government school staff to support the International Student Program processes more efficiently. | Delivery | Compliance (Non Financial), Cost Reduction (Financial) |  | Agile | 2021-04-15 | 2021-08-27 | 2021-10-01 | 2021-10-01 | 65000 |  | 2021-10-01 |  | 2022-06-30 |  | 1500000 |  |  |  |  | Green | Green | Project successfully implemented Release 1 with a number of features going live on 25 February 2022. Early implementation of these features will support important business processes such as homestay accreditation contact nomination and refund & credit management. Development and testing of remaining features is progressing as planned for Release 2 implementation in June 2022.
Q3 21-22 | Department of Education and Training | DET | 3208 | eduSafe Plus – Phase 2 | Education | Human Capital / Workforce Management | The project will deliver the functionality for managing incidents, OHS and workers’ compensation using a platform-based approach. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-04-29 | 2021-06-11 |  | 2021-06-11 | 1 | 0 | 2021-06-14 |  | 2022-06-30 |  | 3192672 | 3192673 |  | Green | Green | Green | Amber | Incident and Hazard Management and OHS Audit functionality successfully went live on 24 January 2022. The implementation of remaining OHS functionality is still work in progress. The project has a delay in the progress of Workers Compensation work due to project resources constraints and additional effort required for the BAU (Business As Usual) support required post Go Live date in January. A revised project plan is being developed along with a new resource plan that will address the resources constraints and will cover the remaining scope of work.
Q3 21-22 | Department of Families, Fairness and Housing | DFFH | 3209 | Homes Victoria and MOG Changes | Property and Planning | Organisational Management | Housing Division has undergone an organisational restructure and is now known as Homes Victoria. This project will deliver updates to affected ICT housing systems, letters and documentation to align with the new structure. | Closed - Completed | Compliance (Non Financial), Reputation (Non Financial), Risk Reduction (Non Financial) | 2022-03-21 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-01-29 | 2021-02-12 |  | 2021-02-12 | 170000 |  | 2021-02-23 |  | 2021-11-28 | 2022-04-29 | 1872000 | 1702000 |  | Green | Amber | Amber | Green | Project has successfully delivered and closeout activities are underway.
Q3 21-22 | CenITex | CenITex | 3212 | DC Exit, Discovery, Re-Architecture and Migration - Stage 1 | Government and Economy | Data Management | To delivery data centre discovery for all Government Shared Platform clients. In addition to the discovery also design a new landing platform and plan for migration of the services. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2021-03-29 | 2021-04-20 |  | 2021-05-06 | 0 |  | 2021-06-10 |  | 2022-06-30 |  | 5600000 |  |  | Green | Green | Green | Green | Discovery, requirements gathering and high level data centre designs are complete.
Q3 21-22 | CenITex | CenITex | 3213 | Hybrid Cloud, Mediation Layer - Stage 1 | Government and Economy | Data Management | Proposal No.1 will cover the uplift of the existing Software Defined Datacentre and VMware for all Government Shared Platform(GSP) clients. Develop service vision for a new Hybrid Cloud hosting solution. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Reputation (Non Financial) |  | PRINCE2 | 2021-03-29 | 2021-05-25 |  | 2021-06-11 | 0 |  | 2021-06-22 |  | 2022-06-30 | 2022-12-31 | 3650000 | 5900000 |  | Green | Green | Green | Green | Workload migrations to the new VMWare Cloud Foundation (VCF) instance of Software Defined Data Centre (SDDC) have commenced and are progressing to schedule.
Q3 21-22 | Melbourne Water | MELB Water | 3214 | Strategic Relationship Management Tool Phase 1-2 | Environment and Water | Collaboration | To enhance delivery of business goals by improvement in business capabilities and relationship management tools to allow ongoing management and continuity of relationships to achieve strategic improvements in organisational goals. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2020-11-25 | 2021-08-01 |  | 2021-11-04 | 0 |  | 2021-11-04 |  | 2022-06-28 |  | 3174023 |  |  |  |  | Green | Amber | Sprint 5 about to commence. Project Coordinator supporting with meetings, vendor, End of Month (EOM), financials. Change Request was presented and approved by steering committee - includes timeline and resource changes. Change Strategy was presented to the steering committee - next steps are for Executive Sponsor to sign off. Business engagement meetings were scheduled, currently in progress and to be completed by mid April. Focus of these is on integration across multiple applications.
Q3 21-22 | Department of Families, Fairness and Housing | DFFH | 3215 | The Integrated Client and Case Management System (ICCMS) Infrastructure Refresh and Software Upgrade | Community Services | Customer Relationship Management,Systems Management | The project will deliver a refreshed hardware/hosting and software solution to the department's primary client and case management business system to ensure a stable, responsive and reliable platform. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2020-10-01 | 2020-11-13 |  | 2020-11-16 | 0 |  | 2021-02-01 |  | 2022-12-31 | 2023-06-30 | 4350000 | 6000000 |  | Green | Green | Amber | Amber | Project is reporting an Amber health status pending approval of rephasing of funding to align with revised schedule.
Q3 21-22 | Department of Jobs, Precincts and Regions | DJPR | 3220 | Fair Jobs Code IT System | Employment and Workplace | Customer Initiated Assistance,Customer Relationship Management,Tracking and Workflow | Delivery of digital services to businesses and suppliers to apply for Fair Jobs Code certificates. It will also provide a public registry for government agencies to confirm the certification status of the suppliers. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-03-09 | 2021-12-31 | 2021-03-23 | 2021-03-23 | 500000 |  | 2021-03-24 |  | 2021-12-31 | 2022-05-30 | 1753225 | 1965808 |  |  | Green | Green | Green | IT Solution has been delivered. Go Live date for Code to be confirmed.
Q3 21-22 | Victorian Managed Insurance Authority | VMIA | 3223 | Client360 Release 5 | Government and Economy | Tracking and Workflow | Client360 Release 5 will focus on completing the remaining items to clear the pathway for decommissioning our legacy system Risk Console and migrate the rest of VMIA’s clients into the Client360 platform | Closed - Completed | Customer Satisfaction (Non Financial) | 2022-03-31 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-04-29 | 2021-07-30 | 2021-07-30 | 2021-07-30 | 0 |  | 2021-08-02 |  | 2021-11-26 | 2022-03-30 | 3660320 | 3671237 |  |  | Amber | Amber | Green | The project's green status reflects completion of project delivery.
Q3 21-22 | South East Water | SE Water | 3225 | Sharepoint Online Migration | Environment and Water | Collaboration ,Content Management,Document Management ,Knowledge Management | Migrate all 2013 sharepoint sites and business content to the sharepoint online platform | Closed - Completed | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) | 2022-02-25 | Waterfall | 2021-04-07 | 2021-04-30 |  | 2021-05-06 | 10000 |  | 2021-05-14 |  | 2021-12-10 | 2022-02-25 | 1184488 |  |  | Green | Amber | Green | Green | The delivery of all releases has been completed and the project is now closed.
Q3 21-22 | Victorian Managed Insurance Authority | VMIA | 3227 | Strategic Data Infrastructure Implementation Phase 3 | Government and Economy | Tracking and Workflow | Client360 is VMIA’s project to replace legacy insurance, claims and client engagement systems and enable new digital capabilities. Release 5 focuses on completing the remaining items to clear the pathway for decommissioning our legacy system Risk Con | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-02-22 | 2021-04-13 |  | 2021-04-13 | 1451000 | 0 | 2021-04-19 |  | 2021-11-26 | 2022-03-31 | 1608500 |  |  | Green | Amber | Amber | Amber | The project status is Amber due to pending approval of change request
Q3 21-22 | Department of Environment, Land, Water and Planning | DELWP | 3234 | Digital Twin Victoria Program (DTV Program) | Property and Planning | Data Management,Knowledge Management | The DTV Program will recreate Victoria online so that government, industry and the community can collaborate to enhance real-world outcomes through shared data and technology leveraging spatial data, artificial intelligence, sensor data and more. | Delivery | Cost Reduction (Financial), Eco Improvement (Non Financial), Increased Revenue (Financial), Social Improvement (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-06-01 | 2020-07-28 |  | 2020-11-15 | 0 |  | 2021-01-01 |  | 2024-06-30 |  | 37431600 |  |  |  | Amber | Green | Green | The Program reported Green status. All workstreams are on track.
Q3 21-22 | Department of Environment, Land, Water and Planning | DELWP | 3238 | Digital Planning Reform Program | Property and Planning | Data Management,Management of Process ,Reporting ,Tracking and Workflow,Visualisation | Digital Reform program will deliver a portal for Victoria with easy access to guidance information and services to reduce complexity and to provide greater consistency and certainty to users. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-07-01 | 2020-11-01 |  | 2020-11-01 | 0 |  | 2021-03-29 |  | 2024-06-30 |  | 15755000 |  |  |  | Green | Amber | Green | The program is now reporting an overall status as green, resourcing issues have been resolved. The program is tracking to schedule.
Q3 21-22 | Department of Justice and Community Safety | DJCS | 3239 | E*Justice Upgrade | Law and Justice | Systems Management | The ​Upgrade of the E*Justice platform will refresh outdated software versions and databases to the latest versions. This will allow better maintenance and support for future initiatives. | Delivery | Compliance (Non Financial) |  | Project Management Excellence | 2021-02-26 | 2021-04-07 |  | 2021-04-07 | 0 |  | 2021-05-14 |  | 2022-04-01 | 2022-06-30 | 1431900 |  |  |  | Amber | Amber | Green | Production release successfully implemented as planned on 28/03. Project end date has been amended to reflect post go-live activities for remaining non-production environments.
Q3 21-22 | Victorian Institute of Forensic Medicine | VIFM | 3241 | Replace Case Management System | Law and Justice | Customer Relationship Management | Case Management System (CRM) will be replaced to meet current business operations and reporting requirements and drive best practice in forensic investigations. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-07-01 | 2022-06-30 |  |  | 0 | 350000 | [11 empty] | Project initiation on track.
Q3 21-22 | Victorian Institute of Forensic Medicine | VIFM | 3242 | ICT Infrastructure Migration to the Cloud | Law and Justice | Systems Management | ICT Infrastructure Cloud Migration project will reduce the risk associated with aging ICT infrastructure | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-07-01 | 2022-06-30 | 2022-03-31 |  | 0 | 585000 | [11 empty] | Project is on track.
Q3 21-22 | Office of Public Prosecutions | OPP | 3243 | Digital Innovation Project Prosecution Case Management | Law and Justice | Tracking and Workflow | Project to upgrade case management system and integrate with other core systems | Initiated |  |  | Agile | 2021-07-01 | 2021-12-31 | 2022-06-30 |  | 300000 | [12 empty] | On track.
Q3 21-22 | Department of Education and Training | DET | 3245 | Disability Inclusion Profile Facilitator | Education | Management of Process | The project will develop an IT system infrastructure that will facilitate the administration of the Disability Inclusion Profile in Victorian government schools from late 2021 to 2024 to support the Disability Inclusion Reform. | Initiated |  |  | Agile | 2021-07-15 | 2022-01-31 |  |  | 0 | [12 empty] | The project is on track with the development of initial business processes and system requirements to support Disability Inclusion Profile activity in 2022. A vendor has been engaged to deliver the new facilitator workforce and has developed IT infrastructure in line with the agreed contractual scope and essential requirements for service delivery.
Q3 21-22 | Department of Education and Training | DET | 3246 | Workplace Management System | Education | Human Capital / Workforce Management | This project will explore the procurement and implementation of a new cloud-based service technology platform to facilitate real-time desk booking, space utilisation, workforce planning, and reporting across all department-owned and leased sites | Initiated | Efficiency/Productivity (Non Financial) |  | Agile | 2021-07-06 | 2022-04-30 |  |  | 0 | [12 empty] | As project requirements are being refined with more specificity, estimated project completion costs are greater than originally anticipated and approved. Mitigation Plan – Budget phasings are being reviewed to align more closely with project requirements.•
Q3 21-22 | Department of Justice and Community Safety | DJCS | 3248 | VicEmergency Uplift | Emergencies and Safety | Communication | The VicEmergency website & mobile app require upgrades and new apps to ensure alignment with key IGEM and Royal Commission recommendations. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-11-13 | 2021-01-02 |  | 2021-03-02 | 700000 | 267000 | 2021-07-01 |  | 2022-06-30 |  | 2500000 |  |  |  | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q3 21-22 | WorkSafe Victoria | WorkSafe | 3249 | Claims and Recovery Strategy - Recovery Service Model Development (RSMD) | Government and Economy | Financial Management | RSMD will develop a future service model with clear target state design and business architecture that provides definition of business benefits and builds foundation technology to enable the implementation of improved recovery and RTW services. | Delivery | Risk Reduction (Non Financial) |  | PMBoK | 2021-07-01 | 2021-10-25 |  | 2021-10-26 | 1172730 |  | 2021-10-27 |  | 2022-06-30 |  | 3818066 |  |  |  |  | Green | Green | Project on track.
Q3 21-22 | WorkSafe Victoria | WorkSafe | 3250 | Claims and Recovery Strategy - Early Online Lodgement (EOL) | Government and Economy | Financial Management | Early Online Lodgement will deliver a digital claim form for workers and employers to submit and track claims via myWorkSafe. Using a phased and scaled rollout with ‘test and learn’ approach and expanding as solution matures and demand grows. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | PMBoK | 2021-07-01 | 2021-09-30 |  | 2021-09-30 | 1078069 |  | 2021-10-01 |  | 2022-06-30 |  | 7028815 |  |  |  |  | Green | Green | Project is on track.
Q3 21-22 | WorkSafe Victoria | WorkSafe | 3251 | Claims and Recovery Strategy - Digitisation of the Claim Form & Medical Certificate (DCFMC) | Government and Economy | Financial Management | DCFMC will deliver the digital registration of paper submitted injury claims and documents using OCR technology and integration ingesting directly into WorkSafe's systems reducing administrative overhead associated with manual data entry. | Delivery | Cost Avoidance (Financial) |  | PMBoK | 2021-07-01 | 2021-09-30 |  | 2021-09-30 | 345138 |  | 2021-10-01 |  | 2022-06-30 |  | 2015981 |  |  |  |  | Green | Green | Project is on track.
Q3 21-22 | WorkSafe Victoria | WorkSafe | 3252 | Claims and Recovery Strategy - Automated Provider Payment Expansion (APPE) | Government and Economy | Financial Management | Automated Provider Payment Expansion will deliver increased access of invoice submissions by Health Providers through implementation of two new digital claim/payment partners enabling increased volumes of invoices submitted via digital channels. | Closed - Completed | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) | 2022-02-09 | PMBoK | 2021-07-01 | 2021-09-30 |  | 2021-09-30 | 474247 |  | 2021-10-01 |  | 2022-06-30 | 2022-02-09 | 1084529 |  |  |  |  | Green | Green | Project was completed and closed 9 February 2022.
Q3 21-22 | Department of Health | DH | 3253 | Security Operations Centre (SOC) 2021-22 | Health | Security Management | Continue the delivery of the Security Operations Centre (SOC) services to the Victorian Community Health Services (CHS's) and nominated allied health agencies | Delivery | Cost Reduction (Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2021-06-01 | 2021-06-30 |  | 2021-06-30 | 0 |  | 2021-07-01 |  | 2022-06-30 |  | 1615000 |  |  |  | Green | Green | Green | Project on budget and on schedule
Q3 21-22 | Fire Rescue Victoria | FRV | 3254 | FRV Operational Station Connectivity | Emergencies and Safety | Assets/Materials Management | The implementation of the FRV network and FRV Station Turn Out systems across ex CFA stations. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | FRV Project Management Framework (PMF) | 2020-09-01 | 2021-03-23 |  | 2021-03-23 | 0 |  | 2021-03-25 |  | 2023-06-30 |  | 16689890 |  |  |  | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q3 21-22 | Department of Premier and Cabinet | DPC | 3255 | Scaling Single Digital Presence (SDP) - Phase Two | Government and Economy | Content Management | Built for government by government SDP offers a common platform for Victorian government content publishing. SDP enables government to consolidate its disparate array of websites to a single platform. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Agile | 2021-07-01 | 2021-07-01 |  | 2021-07-01 | 0 |  | 2021-07-01 |  | 2023-06-30 |  | 29196000 |  |  |  | Green | Green | Green | Finalising the establishment of the ongoing Governance model and continued delivery of onboarding program.
Q3 21-22 | CenITex | CenITex | 3256 | IPS Uplift | Government and Economy | Security Management | To uplift the Intrusion Protection System (IPS) of the Cenitex security services to meet current data throughput and also allow for growth in traffic for coming years. | Delivery | Customer Satisfaction (Non Financial), Eco Improvement (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Increased Revenue (Financial) |  | PRINCE2 | 2021-07-15 | 2021-12-31 | 2021-07-15 | 2021-07-15 | 0 |  | 2021-07-15 |  | 2021-12-31 | 2022-06-30 | 1478085 | 1746949 |  |  | Amber | Amber | Green | Solution Architecture Design complete Cutover analysis and planning complete Variation approved by PCB for budget increase and schedule extension.
Q3 21-22 | Department of Justice and Community Safety | DJCS | 3258 | Distracted Driver Camera Project | Law and Justice | Development and Integration | Procurement and implementation of new road safety cameras capable of automatically detecting mobile phone and seatbelt offences. | Initiated |  |  | Project Management Excellence | 2021-07-01 | 2022-03-31 | 2022-05-04 |  | 2000000 | 1950000 | [11 empty] | The project is tracking well against scope, budget and schedule. New cameras are anticipated to go live by 2023, in line with previous Victorian Government announcements.
Q3 21-22 | Transport Accident Commission | TAC | 3260 | Continuous Delivery 2022 | Transport and Vehicles | Systems Management | Continuous Delivery project is aimed at maturing the TAC Technology delivery model with planned releases to support the system changes and initiatives required in the areas of Business Improvement, Scheme Performance and System Stabilisation. | Delivery | Compliance (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-06-17 | 2021-06-17 |  | 2021-06-17 | 0 |  | 2021-07-01 |  | 2022-06-30 |  | 3290148 | 3829148 |  |  | Green | Green | Green | As at 31 March 2022 the project is tracking green against plan and will continue to focus on delivering business improvements and system changes to support scheme performance over the coming 3 months.
Q3 21-22 | Department of Health | DH | 3261 | Health Information Exchange (HIE) Project | Health | Data Management,Development and Integration | Delivery of a Health Information Exchange (HIE) for the sharing of pathology results within three pathology networks that are being established as part of the LISConnect Pathology Reform program, enabling the efficient sharing of clinical information | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2021-06-01 | 2021-06-30 |  | 2021-06-30 | 0 |  | 2021-07-01 |  | 2025-06-30 |  | 27220000 |  |  |  | Green | Green | Green | Project on schedule, procurement activity nearing completion.
Q3 21-22 | Department of Health | DH | 3262 | Trevi Enhancements | Health | Customer Relationship Management | Enhance the Test, Trace and Isolate Case and Contact Relationship Management solution for COVID-19, with a view to scale the platform across the department to support and align with future healthcare and service requirements. | Delivery | Cost Avoidance (Financial), Risk Reduction (Non Financial), Social Improvement (Non Financial) |  | Agile | 2021-06-22 | 2021-08-12 |  | 2021-08-12 | 0 |  | 2021-08-12 |  | 2022-06-30 |  | 6007500 | 16335850 |  |  | Green | Green | Green | Project is progressing to schedule and cost.
Q3 21-22 | Department of Health | DH | 3263 | COVID-19 Border Directions System (Permits) | Health | Data Management | Uplift the Case Management/Workflow system for border permit and exemption applications received either via the Hotline or ServiceVic app, to improve the Department of Health's ability to track and respond to potential sources of COVID-19 outbreaks. | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2021-05-17 | 2021-06-16 |  | 2021-06-17 | 0 |  | 2021-07-01 |  | 2021-12-31 | 2022-06-30 | 1210000 |  |  |  | Green | Green | Green | The project has developed enhancements in response to Ombudsman's recommendations. In line with changes to restrictions, the Border Directions system is no longer available to the public, however it is available to be re-instated at short notice if required. Project is expected to close in next reporting period.
Q3 21-22 | Southern Metropolitan Cemeteries Trust | SMCT | 3266 | Next Gen Business System Program | Health | Customer Relationship Management,Financial Management | The Next Gen Business System Program will replace existing legacy systems with modern CRM and ERP platforms to fully integrate business processes and data across the enterprise, customers, and partners. | Initiated |  |  | Hybrid - Waterfall and Agile | 2021-07-26 | 2022-02-28 | 2022-04-30 |  | 0 | 1500000 | [11 empty] | Overall project status is green. Solution Exploration commenced in February 2022 as planned, with a slightly later start date due to vendor availability and COVID impacts. Solution Exploration and final tender evaluation were completed in March, with a preferred supplier recommendation to go to Trust for approval in late April 2022. Trust approval will mark the end of Project Initiation.
Q3 21-22 | South East Water | SE Water | 3267 | OpenText Content Server Upgrade | Environment and Water | Content Management | The content server produce, opentext, requires an upgrade to a current version to ensure it is within support parameters. | Delivery | Risk Reduction (Non Financial) |  | Waterfall | 2020-07-13 | 2021-08-02 |  | 2021-08-04 | 60000 |  | 2021-08-04 |  | 2022-04-22 | 2022-06-10 | 1163487 |  |  |  | Green | Green | Green | The new environment build has been completed and initial data loads have occured. Full data loads will be completed next with preproduction systems build also underway.
Q3 21-22 | Ambulance Victoria | AVS | 3268 | ICT One Touch Laptop Upgrade (FY22) | Health | Assets/Materials Management,Organisational Management ,Systems Management | Uplift our information technology, to ensure our patient and business information is secure, improve the reliability of our service to support better patient care, and provide digital capability that meets the needs of our mobile workforce | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-07-01 | 2021-09-30 |  | 2021-09-30 | 0 |  | 2021-09-30 |  | 2022-12-31 | 2022-06-30 | 5150000 |  |  |  | Green | Green | Green | Project tracking to roll out on schedule as anticipated.
Q3 21-22 | Ambulance Victoria | AVS | 3269 | Financial Analytics | Health | Analyses and Statistics ,Business Intelligence,Financial Management,Knowledge Discovery ,Reporting | Transition AV Financial Reporting and Analytics system to Cloud service enabling AV to mitigate the current technology risks associated with operating an out of support system while also providing additional functionality for financial reporting. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - Waterfall and Agile | 2021-07-01 | 2021-12-31 |  | 2021-12-31 | 213850 | 68606 | 2022-01-01 |  | 2022-12-31 |  | 2174650 | 2319894 |  |  |  |  | Green | Project tracking to roll out on schedule as anticipated.
Q3 21-22 | Melbourne Water | MELB Water | 3270 | Audio Visual Remediation | Environment and Water | Collaboration | Melbourne Water has a requirement to update Audio-Visual solutions in meeting rooms across multiple sites in Victoria that will provide a consistent experience for all users and allow for enhanced collaboration. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | PMBoK | 2021-07-08 | 2021-12-03 | 2022-01-20 | 2022-01-20 | 0 |  | 2022-01-20 |  | 2023-01-10 |  | 2424764 | [5 empty] | Green | Finalised the tender evaluation in March. A preferred vendor has been recommended by the Tender Assessment Panel and documented in the Tender Assessment Report which is in the process of Delegation Of Authority approval. SOW to be finalised in April to secure resources for the project. Potential scope additions from the New Normal Ways of Working project to be discussed with PLT in April.
Q3 21-22 | Melbourne Water | MELB Water | 3272 | Cyber Security Uplift Program 2021 | Environment and Water | Security Management | Program of works to uplift the capability in Melbourne Waters cyber security protection. With items around Endpoint protection, documentation uplift and proactive security alert remediation. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-07-01 | 2021-11-30 | 2022-04-20 |  | 0 | [12 empty] | Business Case revisions and review cycles almost complete, final approval meeting from Managing Director scheduled for April.
Q3 21-22 | Melbourne Water | MELB Water | 3273 | Enablement of Information Governance in repositories | Environment and Water | Data Management | Implement effective business rules and governance standards within information management repositories that support the Information Management Strategy, and meets the Public Records Office of Victoria compliance obligations. | Initiated |  |  | PMBoK | 2021-07-01 | 2021-10-04 | 2022-02-21 |  | 0 | [12 empty] | Business Case has been submitted and going through workflow approvals. Final approval expected beginning of April with the project manager to be on-boarded after Easter break to drive the direction of the project.
Q3 21-22 | Melbourne Water | MELB Water | 3274 | Portal New Services | Environment and Water | Communication,Content Management,Customer Relationship Management | Portal went live in 2019 as a minimal viable product (MVP). In line with the Strategy and Pricing Submission 2021 (Water Plan 5) a roadmap of key enhancements will be delivered to improve customers digital experience. | Delivery | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | PMBoK | 2021-07-01 | 2021-10-29 |  | 2021-12-22 | 0 |  | 2022-01-10 |  | 2023-06-30 |  | 2975826 | [5 empty] | Green | Steering Committee has been established and is meeting on a weekly basis covering the Portal New Services and Website New Services as both projects are aligned. Governance RACI is being developed. Implementation plan for the delivery uplift recommendations is being developed with regular review by the steering committee. Hiring for a new Project Manager for both Web & Portal is in progress. Options for Integration are being prepared to be presented to the steering committee for a decision to be made on a way forward.
Q3 21-22 | Melbourne Water | MELB Water | 3275 | Website New Services | Environment and Water | Communication,Content Management,Customer Preferences,Customer Relationship Management | The Melbourne Water Website went live in October 2017 as a minimal viable product (MVP). In line with Strategy and Pricing Submission 2021 (Water Plan 5), a roadmap of key enhancements will be delivered to improve customers digital experience. | Delivery | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | PMBoK | 2021-07-01 | 2021-10-29 |  | 2021-12-22 | 0 |  | 2022-02-10 |  | 2022-06-30 |  | 1243560 | [5 empty] | Green | Steering Committee has been established and is meeting on a weekly basis covering the Portal New Services and Website New Services as both projects are aligned. Governance RACI is being developed. Implementation plan for the delivery uplift recommendations is being developed with regular review by the steering committee. Hiring for a new Project Manager for both Web & Portal is in progress. Options for Integration are being prepared to be presented to the steering committee for a decision to be made on a way forward.
Q3 21-22 | State Revenue Office | SRO | 3276 | Victorian Homebuyer Fund | Government and Economy | Development and Integration | This project supports the administration of the Victorian Homebuyer Fund (VHF) launched in October 2021. | Delivery | Efficiency/Productivity (Non Financial) |  | Agile | 2021-03-08 | 2021-04-30 |  | 2021-04-30 | 529846 |  | 2021-05-03 |  | 2022-06-30 |  | 10579433 | 14716944 |  |  | Green | Green | Green | On Track for Release 3 Delivery and project close in June 2022
Q3 21-22 | Royal Children's Hospital | RCH | 3277 | Wireless Network Infrastructure Refresh | Health | Communication | Refresh of all wireless infrastructure and Wireless Access Points across the Royal Children's Hospital Campus | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2021-05-03 | 2021-11-05 |  | 2021-11-05 | 0 |  | 2021-11-08 |  | 2022-12-16 |  | 1700000 |  |  |  |  | Green | Green | Project tracking to budget scope and plan. No significant issues reported for current reporting period.
Q3 21-22 | Peter MacCallum Cancer Centre | Peter MAC | 3278 | People and Payroll Transformation Program - Rostering Project | Health | Human Capital / Workforce Management ,Human Resources | The People Systems Program will deliver a Rostering solution which will increase efficiency and improve data security and integrity by eliminating paper time sheets and manual processes. | Initiated |  |  | PRINCE2 | 2021-09-01 | 2022-07-01 |  |  | 50000 | [12 empty] | Preferred vendor appointed and contract negotiation in progress
Q3 21-22 | Dental Health Services Victoria | DHSV | 3280 | Electronic Oral Health Record (EoHR) | Health | Development and Integration | The Electronic Oral Health Record (EoHR) aims to replace and consolidate the legacy solution to deliver a single state-wide oral health record to support improved dental health outcomes in Victoria | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-04-01 | 2020-10-30 |  | 2020-10-30 | 390000 |  | 2021-09-22 |  | 2023-06-30 |  | 9490000 |  |  |  | Green | Green | Green | The Steering Committee has been established and endorsed with the PCG Expressions of Interest being collected. Recruiting for the project team has commenced with interviews taking place at the moment. The vendor has completed a Statement of Work with the draft GITC verbally agreed.
Q3 21-22 | Department of Jobs, Precincts and Regions | DJPR | 3281 | Sick Pay Guarantee System Build | Business and Industry | Customer Initiated Assistance,Customer Relationship Management,Tracking and Workflow | Delivery of a platform solution to manage accounts and provide payments to workers accessing the pilot scheme. | Closed - Completed | Efficiency/Productivity (Non Financial) | 2022-03-15 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-11-23 | 2021-08-10 |  | 2021-08-10 | 100000 |  | 2021-11-04 |  | 2022-03-15 | 2022-03-15 | 2400000 |  |  |  |  | Green | Green | The pilot Project phase 1 was delivered within budget and is now live. This Project is now completed.
Q3 21-22 | South East Water | SE Water | 3292 | HSE Project | Environment and Water | Management of Process ,Tracking and Workflow | Implement a new HSE platform to enable capture and management of HSE related risks. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2021-07-05 | 2021-07-14 |  | 2021-07-14 | 25000 |  | 2021-07-14 |  | 2022-06-30 |  | 2979727 |  |  |  | Green | Green | Green | February go live for the first release was completed successfully. The phase 2 release is due in June and is on track to be achieved.
Q3 21-22 | South East Water | SE Water | 3293 | Service Delivery Model | Environment and Water | Management of Process ,Routing and Scheduling | Enhancements to the works management system are needed to support the change in the service delivery model and commercial framework. | Delivery | Compliance (Non Financial) |  | Agile | 2021-07-13 | 2021-10-04 |  | 2021-10-25 | 100000 |  | 2021-10-25 |  | 2022-04-22 | 2022-05-13 | 1214552 |  |  |  |  | Green | Green | UAT has been completed for the major release functionality. New scope items have been approved and are now in development.
Q3 21-22 | Department of Families, Fairness and Housing | DFFH | 3295 | Housing Client Self-Service - Client and Tenancy Updates | Community Services | Customer Preferences | Implementing self serve capability into the Client facing application, Housing Vic Online Services (HVOS), to enable clients of Director of Housing to access information about their tenancy, bond and housing application. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-05-17 | 2021-05-19 |  | 2021-06-04 | 0 |  | 2021-07-01 |  | 2022-06-30 |  | 2094260 | 3647813 |  |  | Green | Green | Green | Project is progressing however schedule and costs revised due to project resourcing issues. Project is on track to deliver in June 2022.
Q3 21-22 | Victorian Building Authority | VBA | 3296 | Practitioner Registration Program (PRP) | Property and Planning | Customer Relationship Management | Our strategic objective is making licensing & registration systems more efficient, simpler & transparent, we plan to create a Practitioner Registration Platform providing online web forms & internal workflows & data integrations | Delivery | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-02-05 | 2021-03-24 |  | 2021-03-24 | 0 |  | 2021-03-24 |  | 2022-01-31 | 2022-09-30 | 2030000 | 1630000 |  |  | Green | Amber | Amber | 80% of the core PRP functionality has been completed
Q3 21-22 | Royal Children's Hospital | RCH | 3297 | Parkville EMR Virtual Care Project | Health | Management of Process | The Virtual Care Project will be implemented across the Parkville precinct supporting the provision of remote care of patients (i.e. Hospital In The Home, etc). Expanding further functionality and applications of current shared EMR. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2021-08-01 | 2023-12-31 | 2021-11-21 | 2021-11-22 | 0 |  | 2021-11-29 |  | 2022-12-31 |  | 3649900 |  |  |  |  | Green | Green | Vendor procurement and contract preparation complete. Recruitment for the project team and training complete. On schedule and on budget.
Q3 21-22 | Greater Western Water Corporation | GW Water | 3298 | Integration - Corporate Systems Platforms FY22 | Environment and Water | Content Management | The merger of CWW and WW requires the consolidation and update of several internal solutions, which has commenced and now requires finalisation | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-07-01 | 2021-07-01 |  | 2021-07-01 | 1 |  | 2021-07-01 |  | 2022-06-30 |  | 2999999 |  |  |  | Green | Green | Green | 2 streams of delivery completed with remaining 4 streams on target for completion in Q4.
Q3 21-22 | Greater Western Water Corporation | GW Water | 3299 | Integration - Our Spatial Odyssey | Environment and Water | Assets/Materials Management,Content Management,Data Management,Development and Integration ,Management of Process | This project will define a new spatial strategy and exploit spatial information, emerging technologies and standards in order to deliver greater value, improve asset information, improve public services and enable an on-demand self-service model. | Initiated |  |  | Waterfall | 2021-07-01 | 2022-06-30 |  |  | 1500000 | [12 empty] | Strategic roadmap defined. Project continues to compile business case and commence platform assessment and procurement options
Q3 21-22 | Greater Western Water Corporation | GW Water | 3300 | Integration - FY22 Unified Communications | Environment and Water | Analyses and Statistics ,Collaboration ,Communication,Customer Initiated Assistance,Human Capital / Workforce Management ,Management of Process ,Organisational Management ,Reporting | GWW contact centre phone services are split across two telephony platforms resulting in significant overheads. To drive operational & efficiencies the initiative will unify contact centre & back office phone services to a single telephony platform. | Delivery | Cost Reduction (Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-07-07 | 2021-08-24 |  | 2021-08-24 | 182901 |  | 2021-08-24 |  | 2022-06-30 |  | 817099 | 1017099 |  |  | Green | Green | Green | Successful migration of IVR self service to CISCO platform. Scope extension to include decommissioning activities - on track to complete by Q4.
Q3 21-22 | Department of Health | DH | 3301 | Disaster Recovery as a Service (DRaaS) | Health | Development and Integration | Enable Victorian public health services to have a fit-for-purpose ICT disaster recovery capability for critical applications in the event of a significant disruption. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2020-09-01 | 2021-07-30 | 2021-05-28 | 2021-05-28 | 1432000 |  | 2021-07-26 |  | 2023-06-30 | 2022-08-30 | 3883000 | 9352325 |  |  | Amber | Amber | Green | The project is tracking to schedule with three agencies in Implementation Phase.
Q3 21-22 | Greater Western Water Corporation | GW Water | 3303 | Cyber Security Uplift FY22 | Environment and Water | Security Management | This project contains seven initiatives to address the security risks identified in the GWW Security Risk Assessment Report and also reduce costs reduce network infrastructure complexity reduce tech debt and reduce the load on the service desk. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Reputation (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-07-01 | 2021-09-09 |  | 2021-09-09 | 100000 |  | 2021-09-09 |  | 2022-06-30 |  | 1150000 |  |  |  | Green | Green | Green | Q3 delivered 4 initiatives as planned remaining 3 initiatives on track to be delivered in Q4
Q3 21-22 | Department of Transport | DOT | 3304 | Heavy Vehicle Hazard Perception Testing | Transport and Vehicles | Content Management,Customer Initiated Assistance,Customer Preferences | Delivery of Hazard Perception Testing (HPT) capability in combination with a framework that will allow for delivery of content and knowledge testing for applicants within the context of the revised National Heavy Vehicle Driver Competency Framework | Postponed |  | 2021-12-06 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-07-01 | 2021-12-30 |  |  | 0 | [5 empty] | 0 | [6 empty] | Project is on hold.
Q3 21-22 | Greater Western Water Corporation | GW Water | 3305 | SPARC Re-Platform FY21 | Environment and Water | Data Management,Systems Management | The project aims to migrate the current ageing Oracle SPARC/Solaris to a new SPARC platform as part of the platform replacement cycle. Additionally the project will migrate data storage from legacy Hitachi to a new NetApp SAN storage platform. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-08-13 | 2021-01-08 |  | 2021-01-08 | 321348 |  | 2021-01-08 |  | 2022-06-30 |  | 1958652 |  |  |  | Green | Green | Green | Migration of final oracle environment completed as planned. Decommissioning of legacy databases and old SPARC platform on track for completion by Q4
Q3 21-22 | Department of Transport | DOT | 3306 | DoT Integration: Identity and Access Join | Transport and Vehicles | Development and Integration ,Systems Management | Enable an integrated and secure Department of Transport (DoT) through ensuring any DoT user from anywhere using a DoT issued device can access data systems and resources across the department. | Delivery | Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2021-06-07 | 2021-07-05 |  | 2021-07-05 | 0 |  | 2021-07-05 |  | 2022-03-25 | 2022-06-30 | 5870000 |  |  |  | Amber | Amber | Amber | Overall status is amber due to schedule risks and multiple dependencies. Working with the project authority and external vendors to address the risks.
Q3 21-22 | Department of Transport | DOT | 3307 | DoT Integration: Transition State Operating Model and SOE Transition | Transport and Vehicles | Development and Integration ,Security Management | Objective of this project is to deliver improved operational support model and SOE management structure to support the distributed nature of DoT operations. | Delivery | Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-06-07 | 2021-07-05 |  | 2021-07-05 | 0 |  | 2021-07-05 |  | 2022-06-30 |  | 1230000 |  |  |  | Amber | Amber | Green | Overall status is green. Go live activities have been completed on schedule across the staff transition, new service desk operating model and supporting processes. Hyper-care activities ongoing prior to closing out the Transition State Operating Model stream and commencing SOE Migration activities.
Q3 21-22 | Department of Transport | DOT | 3308 | DoT Integration: Security Uplift and Remediation | Transport and Vehicles | Security Management | Objectives of this project is to Implement foundational security enhancements to ensure the future state technology landscape of an integrated DoT remains compliant to the operational standards required. | Delivery | Compliance (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-06-07 | 2021-07-05 |  | 2021-07-05 | 0 |  | 2021-07-05 |  | 2023-06-30 |  | 2370000 |  |  |  | Amber | Amber | Green | Overall project status is green. Remediation for Day 1 operations has been completed. Remainder of activities will continue as per the agreed plan.
Q3 21-22 | Victorian Public Sector Commission | VPSC | 3310 | Jobs and Sills Exchange (JSE) digital 2.0 | Government and Economy | Human Capital / Workforce Management ,Knowledge Discovery | The project will uplift the JSE digital platform to improve employment and career services to VPS employees. This will support workforce transition, skills development, mobility and improve workforce effectiveness. | Delivery | Efficiency/Productivity (Non Financial) |  | Agile | 2020-05-01 | 2020-11-30 |  | 2020-11-30 | 0 |  | 2021-07-01 |  | 2022-06-30 |  | 2320000 |  |  |  | Green | Green | Green | Project delivery is structured into fortnightly sprints. Initial focus to strengthen the JSE technical platform has now concluded, with focus now on delivering additional in-scope features. Delivery is in progress and on track.
Q3 21-22 | Department of Transport | DOT | 3311 | Smarter Roads Program - Open Data | Transport and Vehicles | Analyses and Statistics ,Business Intelligence,Data Management | Objective of this project is to improve access to the department’s transport data for use in internal and external (3rd party) customer experience solutions and ensure a wider variety of important data sources are available to be used. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-03-31 | 2021-10-18 |  | 2021-10-18 | 0 |  | 2021-10-18 |  | 2022-06-30 |  | 2070043 | 3100000 |  |  |  | Amber | Amber | Overall project status is amber due to schedule issues. API integration with data sources and testing in progress. API redevelopment scope is being reviewed.
Q3 21-22 | Department of Transport | DOT | 3312 | Smarter Roads Program - Timetable Systems Uplift | Transport and Vehicles | Content Management,Data Management,Systems Management | Objective of this project is to prepare an options analysis brief outlining best of breed solutions for Timetabling and Journey planning. The analysis will inform a recommended solution to build and implement. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-05-03 | 2021-12-30 | 2022-02-07 | 2022-02-07 | 0 |  | 2022-02-07 |  | 2023-03-31 |  | 4739268 | [5 empty] | Green | Overall project status is green. Project development is ongoing.
Q3 21-22 | Department of Transport | DOT | 3313 | Public Transport Real-time Vehicle Location | Transport and Vehicles | Business Intelligence,Data Management,Development and Integration | Objective of this project is to modify A,B & C-Class tram Thoreb units to enable transfer of data to Transnet & trial Traffic Light Prioritisation. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-10-19 | 2021-12-20 | 2022-02-28 | 2022-02-28 | 0 |  | 2022-02-28 |  | 2022-06-30 |  | 2011672 | [5 empty] | Green | Overall project status is green. Development and testing is ongoing.
Q3 21-22 | Lower Murray Urban and Rural Water Corporation | LMUR Water | 3315 | Business Transformation Program - Horizon 1 | Environment and Water | Customer Relationship Management,Data Management,Financial Management,Management of Process ,Tracking and Workflow | The program will uplift capabilities across key business functions, including customer service, data, asset and workforce management, and financial management to enable improved customer service and efficiency.​ | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-01-11 | 2021-04-27 |  | 2021-04-27 | 115137 |  | 2021-07-01 |  | 2023-06-30 |  | 5200000 | 5606626 |  |  | Green | Green | Green | Project continues to track well
Q3 21-22 | Greater Western Water Corporation | GW Water | 3316 | Integration - Customer Website Consolidation | Environment and Water | Assets/Materials Management,Content Management,Customer Preferences,Data Management | To deliver a re-developed website utilising GovCMS platform with a focus on delivering functions & features in accordance with a priority of customer usage & to consolidate and then decommission the GWW Microsite & 2 legacy websites | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Reputation (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-07-01 | 2021-10-11 |  | 2021-10-11 | 311830 |  | 2021-10-11 |  | 2022-06-30 |  | 1188170 |  |  |  |  | Green | Green | UX/UI design for web and applications completed successfully in Q3 along with routing applications. Common services applications are in progress for completion by Q4 along with the finalisation of GovCMS setup and configuration. Project is on target for completion of FY22 commitments in Q4
Q3 21-22 | South West Alliance of Rural Health | SWARH | 3317 | SWARH Modern Workplace Migration and Adoption | Health | Collaboration ,Communication,Content Management,Customer Initiated Assistance,Customer Preferences,Document Management ,Forms Management,Human Capital / Workforce Management ,Knowledge Discovery ,Knowledge Management ,Management of Process ,Organisational Management ,Records Management ,Search ,Security Management ,Tracking and Workflow | To migrate all SWARH-supported Health Services to modern workplace cloud services, and promote the adoption of these services. This will drive improved communication, collaboration and productivity, across and within each of these Health Services. | Initiated |  |  | PMBoK | 2021-12-03 | 2022-05-16 | 2022-06-06 |  | 224344 | [12 empty] | The Request for Information (RFI) has been published and evaluation complete. Workshops have commenced with select vendors, to assist in drafting of response for a select. Request for Tender, to be published end of April.
Q3 21-22 | Department of Transport | DOT | 3318 | Automatic Vehicle Monitoring Sustainment (AVMS) | Transport and Vehicles | Systems Management | Address key short-term challenges affecting Melbourne’s tram network through targeted initiatives to sustain the AVM system in the short-term while the Department continues to develop options for a future Tram Monitoring and Control (TMC) system. | Initiated |  |  | PTV Investment Lifecycle | 2021-07-01 | 2022-04-29 | 2022-07-15 |  | 1785000 | [12 empty] | Operating System Upgrade: Project is tracking well as per the critical path with procurement process in-progress. Schedule revised to reflect porting delivery approach. On-board Sustainment: KDR progressing well with the On-Board sustainment work tracking to current schedule.
Q3 21-22 | Fire Rescue Victoria | FRV | 3320 | Response Monitoring and Move-Up Monitoring | Emergencies and Safety | Business Intelligence | • Improve emergency response benchmarks, predicative deployment analysis and aid decision making to improve operational response utilising historical CAD response data. • Efficient resource planning and use based on real time data to inform operation | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | FRV PMF | 2021-06-01 | 2021-10-01 |  | 2021-10-01 | 1 | 0 | 2021-12-01 |  | 2023-06-30 |  | 3000000 |  |  |  |  | Amber | Amber | The project reported an Amber status due to COVID-related resource constraints. A project variation is underway to rebaseline the project spend across the two financial years and shift the milestones not impacting project forecast end date.
Q3 21-22 | Fire Rescue Victoria | FRV | 3325 | HRIS | Emergencies and Safety | Human Resources | HRIS Project is in the initiation stage, with the primary focus this year to address foundation data issues, collaborate with the Rostering and Shift Change project and build a business case for approval around mid 2022. Scope includes Payroll and HR | Initiated |  |  | FRV Project Management Framework (PMF) | 2021-12-10 | 2022-06-30 |  |  | 0 | [12 empty] | The project is tracking well against scope budget and schedule.
Q3 21-22 | Fire Rescue Victoria | FRV | 3326 | Desktop Replacement | Emergencies and Safety | Assets/Materials Management | Replacement of ex-Metropolitan Fire Brigade (MFB) workplace computing devices in excess of 4 years old. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | FRV Project Management Framework (PMF) | 2021-07-01 | 2021-11-10 |  | 2021-11-10 | 0 |  | 2021-11-11 |  | 2024-06-30 |  | 2520000 |  |  |  |  | Green | Green | The project is tracking well against scope, budget and schedule.
Q3 21-22 | Office of the Special Investigator | OSI | 3327 | Digital Forensic Investigation platform | Law and Justice | Document Management | A digital forensic investigation platform operating a range of forensic evidence processing, analysis and investigation tools will be established and used to provide secure management and use of data obtained by the Office of the Special Investigator | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2021-09-15 | 2021-12-17 |  | 2021-12-17 | 0 |  | 2021-12-23 |  | 2023-06-30 |  | 3254990 |  |  |  |  | Green | Green | The project is in its delivery stage.
Q3 21-22 | Transport Accident Commission | TAC | 3329 | Financial Management & Procurement System | Transport and Vehicles | Financial Management | The project will replace the existing Finance and Procurement management systems in order to ensure compliance requirements are met, mitigate the risk of fraud and corruption and move processes towards industry practice. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-10-19 | 2021-12-16 |  | 2021-12-16 | 270115 |  | 2021-12-16 | 2021-12-16 | 2023-02-06 |  | 2412927 |  |  |  |  | Green | Green | On Track.
Q3 21-22 | Transport Accident Commission | TAC | 3330 | ConTACt | Transport and Vehicles | Communication | The project will deliver an upgrade to the core configuration of the IVR to improve the way we use the phone channel to communicate with our clients & providers. It will provide staff with the right tool to perform their role, ensuring consistency. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Reputation (Non Financial) |  | Waterfall | 2021-05-20 | 2021-10-21 |  | 2021-10-21 | 509322 |  | 2021-10-21 |  | 2022-04-30 |  | 1468774 |  |  |  |  | Green | Amber | Budget and schedule has been amber for the quarter as re-baseline change request continues through internal TAC approval process. Project will go green in late April.
Q3 21-22 | Department of Health | DH | 3333 | Central Immunisation Records Victoria (CIRV) | Health | Security Management | To deliver a state of the art, centralised, long-term strategic solution to replace end of life legacy local immunisation system (ImPS) in use by over 70 councils and 3 health services enabling more seamless delivery of immunisation services. | Delivery | Compliance (Non Financial), Reputation (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-10-01 | 2021-11-30 |  | 2021-11-30 | 0 |  | 2022-01-01 |  | 2022-12-31 |  | 17000000 | [5 empty] | Amber | Main procurement activities were delayed but have now been finalised. Schedule and cost are currently being reviewed and will be rebaselined in the next reporting quarter.
Q3 21-22 | South West Alliance of Rural Health | SWARH | 3334 | SWARH Electronic Health Record Upgrade | Health | Customer Relationship Management,Data Management,Development and Integration ,Management of Process ,Records Management ,Systems Management,Tracking and Workflow | Major upgrade to the Electronic Health Record (EHR) solution that supports 11 health services across South West Victoria. The project will improve clinician and patient user experience, focusing on quality and safety of patient care. | Initiated |  |  | PRINCE2 | 2019-10-16 | 2022-03-31 | 2022-06-30 |  | 180000 | [12 empty] | Upgrade has been approved by all the health service boards. Detailed project delivery schedule and costs to be confirmed post recruitment of a Project Manager.
Q3 21-22 | William Angliss Institute of TAFE | WA TAFE | 3335 | Core Infrastructure Refresh | Education | Systems Management | To replace 5+ year old core infrastructure for Production Backup and Disaster Recovery. This include production servers backup platforms and storage | Postponed |  | 2022-03-02 | Waterfall | 2021-11-01 | 2022-02-28 |  |  | 30000 | [5 empty] | 0 | [6 empty] | The project has been approved internally to William Angliss, but the Department of Education (OTCD Office) have asked that it be placed on hold for now.
Q3 21-22 | Department of Families, Fairness and Housing | DFFH | 3337 | Service Agreements Management System (SAMS2) Reporting Solution | Community Services | Business Intelligence | Project will replace the existing reporting solution with a fit for purpose, cloud based and scalable solution for SAMS2 data including a purpose built data mart that will enable end users to self serve reports. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2021-03-22 | 2021-09-16 |  | 2021-09-16 | 0 |  | 2021-11-01 |  | 2022-12-31 | 2023-02-28 | 1412500 |  |  |  |  | Green | Green | Project is progressing to schedule and cost.
Q3 21-22 | Melbourne Water | MELB Water | 3338 | Electronic Content Management Phase 1 | Environment and Water | Content Management | This project will upgrade Melbourne Waters current document storage repositories and migrate to a new Electronic Document and Records Management System (EDRMS) | Initiated |  |  | PMBoK | 2021-10-08 | 2022-09-22 |  |  | 0 | [12 empty] | Buying tool request and sourcing strategy prepared and pending MW procurement team review and feedback to enable engagement of implementation partner to complete the optioneering.
Q3 21-22 | Melbourne Water | MELB Water | 3339 | Network Hardware Refresh 21/22 | Environment and Water | Security Management | Melbourne Water is ensuring continued investment in our IT network through ongoing refresh of IT Hardware as it approaches end of life rather than extending support reducing risk of unplanned network outages. Priority 1 & 2 devices. | Initiated |  |  | PMBoK | 2021-10-29 | 2022-01-31 | 2022-04-29 |  | 0 | [12 empty] | Updates requested to the Business Case to align scope changes and has been resubmitted through the workflow approvals, expected in April
Q3 21-22 | Austin Health | AH | 3341 | EMR Documentation and Infusions Project | Health | Communication,Document Management ,Forms Management,Tracking and Workflow | The project will implement electronic clinical documentation and the administration of fluid medication and nutrition infusions, reducing the risks associated with paper-based document management and improving patient safety. | Delivery | Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2021-10-04 | 2021-11-02 |  | 2021-11-08 |  |  | 2022-01-24 |  | 2024-01-24 |  | 5381664 | [5 empty] | Green | Commenced the delivery phase of the project. All scheduled tasks completed, namely: - Project team recruited and onboarded. - Project planning.
Q3 21-22 | Department of Health | DH | 3342 | OurService Phase 3 | Health | Tracking and Workflow | Build on existing Service Management Platform to further uplift and modernise the department’s Corporate Service functions delivering a consistent enterprise service management experience for DH & DFFH staff and external agencies who use OurService. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Agile | 2021-07-01 | 2021-07-20 |  | 2021-07-20 | 0 |  | 2021-08-02 |  | 2022-07-31 |  | 2400000 |  |  |  |  | Green | Green | Project is progressing to schedule and cost.
Q3 21-22 | Department of Families, Fairness and Housing | DFFH | 3343 | Housing Integrated Information Program (HiiP) Windows Server Upgrade | Community Services | Systems Management | The project will upgrade outdated application servers to the supported 2019 version which will mitigate risk and enable for future transitioning to the cloud. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-06-08 | 2021-12-01 |  | 2021-12-01 | 0 |  | 2021-12-01 |  | 2022-06-30 |  | 2225000 |  |  |  |  | Green | Amber | Project is progressing however has been impacted by delivery delays of required hardware. Impact to schedule is currently being reviewed.
Q3 21-22 | Department of Families, Fairness and Housing | DFFH | 3344 | Property Acquisition and Sales and Lease-In Management Systems Replacement | Property and Planning | Systems Management | Replace existing systems, used to manage property acquisitions and sales and lease acquisitions, to a fit for purpose solution that will meet the increased demands on property acquisitions to support Homes Victoria initiatives. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-12-16 | 2021-05-31 |  |  | 1 | [12 empty] | Procurement activities are being finalised.
Q3 21-22 | State Revenue Office | SRO | 3345 | Mental Health and Wellbeing Surcharge | Government and Economy | Development and Integration | The Mental Health and Wellbeing Surcharge was announced in the May 2021 budget to support mental health initiatives. It is payable from 1 January 2022 by larger employers and groups with wages over certain thresholds. | Delivery | Increased Revenue (Financial) |  | Agile | 2021-08-31 | 2021-08-31 |  | 2021-08-31 | 0 |  | 2021-08-31 |  | 2022-12-31 |  | 3668000 |  |  |  |  | Green | Green | The first milestone, initial monthly submission of returns by the end of January 2022, was met. On Track to deliver the second milestone of annual reconciliation for July 2022.
Q3 21-22 | Department of Health | DH | 3346 | G2G Now Home Isolation Digital Solution - Proof of Concept | Health | Communication | This project is a proof of concept to utilise a digital solution for compliance check-in within Victoria for members of the public who are required to isolate or quarantine due to COVID-19. | Closed - Completed | Compliance (Non Financial), Cost Avoidance (Financial), Efficiency/Productivity (Non Financial) | 2022-02-15 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-08-03 | 2021-08-07 |  | 2021-08-07 | 0 |  | 2021-09-01 |  | 2022-02-15 |  | 1210687 |  |  |  |  | Green | Green | Project has successfully completed Proof of Concept and is now closed.
Q3 21-22 | Department of Health | DH | 3347 | Consultative Councils Unit (CCU) Project - Phase 2 | Health | Data Management | Implement a robust integrated solution to facilitate secure collection, storage, linkage, analysis and visualization of data for mortality, morbidity and congenital anomalies in Victoria to support timely case resolution and reporting. | Delivery | Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2020-12-14 | 2021-11-24 |  | 2021-11-25 | 0 |  | 2021-11-25 |  | 2022-04-29 |  | 1353750 |  |  |  |  | Green | Green | Project is progressing to schedule and cost.
Q3 21-22 | Bendigo Kangan Institute of TAFE | BKI TAFE | 3348 | Business Intelligence and Enterprise Reporting | Education | Business Intelligence | This project will establish the Enterprise Data Foundation to enable implementation of the Business Intelligence capability. Business Intelligence will provide key insights and visualisations, to enable improvements toward financial sustainability. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Increased Revenue (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-09-11 | 2021-10-29 |  | 2021-10-29 | 0 |  | 2021-10-29 |  | 2022-08-31 |  | 1032346 |  |  |  |  | Green | Green | Overall Status is green project is tracking to plan. Vendor resources have commenced. Project is working through planned work for the three use cases as per the business case. Filling vacant roles within the project is a priority.
Q3 21-22 | Bendigo Kangan Institute of TAFE | BKI TAFE | 3350 | Wide Area Network (WAN) | Education | Communication,Systems Management | This project will replace the current outdated Wide Area Network (WAN) with a transformational uplift in capacity resilience and security, providing upgraded, cost efficient connectivity for the next 5+ years. | Delivery | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-07-30 | 2021-12-16 |  | 2021-12-16 | 40700 |  | 2021-12-16 |  | 2022-09-30 |  | 1602284 |  |  |  |  | Green | Green | Project is currently green. Equipment order has been placed. Detailed planning and designs underway.
Q3 21-22 | Bendigo Kangan Institute of TAFE | BKI TAFE | 3351 | Website Redevelopment | Education | Systems Management | Rebuild and launch Kangan Institute and Bendigo TAFE externally facing websites with focus on customer acquisition. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Revenue (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-05-25 | 2021-12-16 |  | 2021-12-16 | 56350 |  | 2021-12-16 |  | 2022-07-31 |  | 978751 |  |  |  |  | Green | Green | Project is tracking green in overall scope Project has had significant progress within this reporting period. Project is managing dependencies well.
Q3 21-22 | CenITex | CenITex | 3352 | CTX - Cenitex Backup Platform Modernisation | Government and Economy | Assets/Materials Management | The purpose of this initiative is it to refresh and uplift the current Cenitex Backup and Data Protection platform, ensuring that Cenitex can continue to offer contemporary and in demand services to its customer base. | Delivery | Cost Avoidance (Financial) |  | PRINCE2 | 2021-10-27 | 2021-10-30 |  | 2021-10-30 | 0 |  | 2021-11-01 |  | 2022-06-30 |  | 2467000 |  |  |  |  | Green | Green | New backup appliances were commissioned and historical backup data was migrated to the new appliances at the Burwood and Ballarat data centres.
Q3 21-22 | Environment Protection Authority | EPA | 3353 | Waste Tracker Enhancement project | Environment and Water | Tracking and Workflow,Business Intelligence,Data Management | Waste Tracker replaced the Waste Transport Certificate system in July 2021. This project is enhancing the functionality and usability of the existing Waste Tracker system. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Increased Quality (Non Financial) |  | Agile | 2021-12-17 | 2022-02-01 |  | 2022-02-03 | 50000 |  | 2022-02-07 |  | 2022-07-31 |  | 2133255 | [5 empty] | Green | Project currently on track.
Q3 21-22 | Greater Western Water Corporation | GW Water | 3354 | Growth & Development Systems | Environment and Water | Assets/Materials Management,Collaboration ,Data Management,Forms Management,Management of Process ,Records Management ,Reporting ,Tracking and Workflow | This multi-year initiative will adopt a strategic roadmap for the Urban Development ecosystem by performing analysis & prioritisation of work to support the growth of GWW service areas & improve agility to better service our customers. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-07-01 | 2022-06-30 |  |  | 1650000 | [12 empty] | The project concluded expressions of Interest for a platform upgrade. Additionally, there have been three waves of functional improvements to the existing platform to ensure improved integration and efficiencies with immediate benefits.
Q3 21-22 | Victorian Building Authority | VBA | 3357 | Online interactive forms for builder registrations | Property and Planning | Customer Relationship Management | This proposal will create online interactive forms with a simple online payment function, making the application process faster and easier for builders. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-01-03 | 2022-01-31 |  | 2022-01-31 | 0 |  | 2022-01-31 |  | 2023-01-31 |  | 1700000 | [5 empty] | Green | The project is continuing as per plan
Q3 21-22 | Victoria Police | VicPol | 3358 | Electronic Document and Records Management System | Law and Justice | Document Management | The overall objective of the project is to implement a fully integrated enterprise wide Electronic Document and Records Management Solution and an Enterprise Service Management platform. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-10-15 | 2020-11-24 |  | 2020-11-24 | 0 |  | 2020-11-25 |  | 2024-12-31 |  | 8559000 | [5 empty] | Green | On 10 January 2022, project initiation activities including high-level project planning commenced. The project remains on track across all areas. Governance arrangements have been established and key project documentation has been developed. Recruitment of the core project team is underway with 3 resources recruited including the Program Director. Over the coming quarter, the project will continue to recruit key priority roles, as well as undertake detailed project and procurement planning, requirements gathering and system architectural design to enable integration with related Victoria Police systems.
Q3 21-22 | Victoria Police | VicPol | 3359 | Finance Systems Program (Oracle Cloud) | Law and Justice | Investment Management | Technology enablement of Finance and Procurement, including the implementation of Oracle Cloud. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-10-15 | 2020-11-24 |  | 2020-11-24 | 0 |  | 2021-11-25 |  | 2025-06-30 |  | 32453000 | [5 empty] | Amber | The FSP comprises four streams of work in FY22: 1.Common Corporate Platform Co-Design: 2.Invoice Automation Solution (IAS) 3.Contingent Workforce Management (CWM) 4.AP Auditing and Contract Compliance (CC) The overall "Amber" rating reflects the potential delay and risks associated with the Common Corporate Platform.
Q3 21-22 | Victoria Police | VicPol | 3360 | Enterprise Rostering | Law and Justice | Human Capital / Workforce Management | Establishment of a single enterprise wide fit for purpose rostering and timesheet solution for Victoria Police. The solution will support rostering and timesheet management across all sworn and VPS staff and will be on approved mobile devices. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2020-10-15 | 2020-11-24 |  | 2020-11-24 | 0 |  | 2020-11-25 |  | 2024-12-31 |  | 21490000 | [5 empty] | Green | On 10 January 2022, project initiation activities including high-level project planning commenced. The project remains on track across all areas. Governance arrangements have been established and key project documentation has been developed. Recruitment of the core project team is underway with 3 resources recruited including the Program Director. Over the coming quarter, the project will continue to recruit key priority roles, as well as undertake detailed project and procurement planning, requirements gathering and system architectural design to enable integration with related Victoria Police systems.
Q3 21-22 | WorkSafe Victoria | WorkSafe | 3361 | ACCS Arbitration Neo Module | Government and Economy | Customer Relationship Management | A new arbitration function will allow ACCS to make binding determinations for worker's compensation disputes not resolved through the existing conciliation process. The model provides a low-cost, timely and effective alternative to the court process. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-01-17 | 2022-04-14 |  |  | 0 | 610280 | [11 empty] | Project On Track, near completion of the Design phase
Q3 21-22 | Department of Justice and Community Safety | DJCS | 3363 | Network & System Monitoring | Emergencies and Safety | Assets/Materials Management | Investigate, select and implement an appropriate system to monitor and provide failure and exception altering of FRV's ICT environment | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | FRV Project Management Framework (PMF) | 2015-08-11 | 2015-11-10 |  | 2015-11-10 | 0 |  | 2022-02-14 |  | 2023-06-30 |  | 2093427 | [5 empty] | Green | The project is tracking well against scope, budget and schedule.
Q3 21-22 | Department of Justice and Community Safety | DJCS | 3364 | Fire Station Switches | Emergencies and Safety | Assets/Materials Management | Replacement of all end of life (EOL) fire station switches supporting the FRV network to ensure a safe secure and reliable ICT environment | Delivery | Risk Reduction (Non Financial) |  | FRV Project Management Framework (PMF) | 2020-07-01 | 2020-10-05 |  | 2020-10-05 | 0 |  | 2022-02-14 |  | 2023-06-30 |  | 1575000 | [5 empty] | Green | The project is tracking well against scope, budget and schedule.
Q3 21-22 | Department of Justice and Community Safety | DJCS | 3365 | ICS Equipment Refresh - ICT Infrastructure Equipment at End of Life | Emergencies and Safety | Assets/Materials Management | Procure ICT infrastructure equipment to replace existing assets that have reached end of life to ensure ongoing reliability of FRV's ICT infrastructure. | Delivery | Risk Reduction (Non Financial) |  | FRV Project Management Framework (PMF) | 2020-09-01 | 2020-11-30 |  | 2020-11-30 | 0 |  | 2022-02-14 |  | 2024-06-30 |  | 2100000 | [5 empty] | Green | The project is tracking well against scope, budget and schedule.
Q3 21-22 | Department of Justice and Community Safety | DJCS | 3367 | Integration Capability Service | Emergencies and Safety | Systems Management | Provide a new single, vendor agnostic integration platform to interface into multiple ESTA data sources that provides reliability and meet current and future anticipated requirements. | Initiated |  |  | Project Management Excellence | 2021-08-09 | 2021-12-28 |  |  | 570406 | [12 empty] | Project is evaluating Request for Tender responses to select the integration platform.
Q3 21-22 | Country Fire Authority | CFA | 3369 | CFA Radio Replacement Program | Emergencies and Safety | Communication | CFA’s current Tait 9100 series radios are no longer manufactured and are approaching the end of their practical life for operational purposes. These will be replaced across Victoria and will introduce a technology refresh with enhanced functionality. | Initiated |  |  | Project Management Excellence | 2021-07-01 | 2022-03-31 |  |  | 235465 | [12 empty] | The project is tracking well against scope budget and schedule.
Q3 21-22 | Department of Transport | DOT | 3370 | DoT Integration: O365 Tenancy Consolidation | Transport and Vehicles | Collaboration | Objective of the office 365 Tenancy Consolidation project is to deliver a single Microsoft Office instance across DoT to allow for cross entity collaboration. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-01-10 | 2022-04-28 |  |  | 0 | [12 empty] | Project initiation activities are ongoing.
Q3 21-22 | Department of Families, Fairness and Housing | DFFH | 3371 | Fairer Victoria Grants Management Platform | Community Services | Systems Management | Develop new Grants Management System to provide end-to-end grants and contract management capability, to take grants management forward in line with best practices and to mitigate the operational risk of the current unsupported legacy system. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-03-26 | 2021-10-21 |  | 2021-10-21 | 0 |  | 2021-10-25 |  | 2022-10-06 |  | 1126000 | [5 empty] | Green | Project is progressing to schedule and cost.
Q3 21-22 | Department of Health | DH | 3373 | Meeting Room Technology Upgrade | Community Services | Collaboration ,Communication | This project will seek to equip meeting rooms with Microsoft Teams enabled technology and devices to ensure streamlined meetings for staff working in the office, remotely and from hub locations. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2021-06-25 | 2021-11-30 |  | 2021-12-15 | 0 |  | 2022-03-01 |  | 2023-06-30 |  | 6000000 | [5 empty] | Green | Procurement activities are in progress.
Q3 21-22 | Department of Premier and Cabinet | DPC | 3374 | API Marketplace | Business and Industry | Knowledge Management ,Collaboration ,Knowledge Discovery | A connected data sharing platform to help create jobs and grow the Victorian tech economy | Delivery | Reputation (Non Financial) |  | Agile | 2019-09-01 | 2021-02-01 | 2020-12-07 | 2020-12-07 | 200000 |  | 2021-02-01 |  | 2022-12-30 |  | 915000 | [5 empty] | Green | Project is on track. Proceeding towards end of Proof-of-Concept phase and setting up to start scale-up/production build phase once technical architecture reviewand feedback from participants is collated, analysed and complete.
Q3 21-22 | Department of Families, Fairness and Housing | DFFH | 3375 | Tenant Relocation System | Community Services | Systems Management | Deliver an online, centrally managed and operated Tenancy Relocation Support system for Homes Victoria and Community Services Operations Division that will enable more timely and accurate reporting of tenant relocation information. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-10-08 | 2022-01-21 |  | 2022-01-21 | 0 |  | 2022-01-21 |  | 2022-06-30 |  | 1433431 | [5 empty] | Green | Project progressing to schedule and cost.
Q3 21-22 | Department of Families, Fairness and Housing | DFFH | 3376 | New Housing Integrated Information Program (HiiP) Non-Production Environments Phases 2 and 3 | Community Services | Systems Management | The project will extend specialist IT environments capability to allow for more extensive testing of the Homes Victoria ICT projects to ensure the implemented solutions are fit for purpose. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-01-08 | 2021-03-18 |  | 2021-03-19 | 0 |  | 2021-07-21 |  | 2022-06-30 |  | 1005892 | [5 empty] | Amber | Project is progressing however has been impacted by delivery delays of required hardware. Impact to schedule is currently being reviewed.
Q3 21-22 | Department of Premier and Cabinet | DPC | 3377 | Digital Victoria Marketplace | Government and Economy | Collaboration ,Data Management,Records Management | The Marketplace is an initiative by Digital Victoria to provide a simplier, and easier way for Government and Industry to interact through the eServices register and various other SPC's. | Delivery | Customer Satisfaction (Non Financial) |  | TBC | 2021-10-01 | 2021-10-13 |  | 2021-10-13 | 0 | 7708 | 2022-02-01 |  | 2027-06-30 |  | 16790000 | [5 empty] | Green | Project is tracking according to the approved plan.
Q3 21-22 | Monash Health | Monash H | 3378 | Alfred/Monash - Shared Laboratory Information System | Health | Records Management | Delivery of a Shared Pathology Information System supporting the Department of Health Pathology sector reform initiative to consolidate pathology systems and services. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-10-05 | 2022-08-31 |  |  | 2000000 | [12 empty] | The Alfred/Monash Shared LIS Project Implementation Planning Study (IPS) has commenced and is scheduled to be completed in August 2022. The IPS will determine the costs, timeline and requirements of the LIS to support the Shared Pathology service.